## 170926
170926 status
Topic | Responsible | Status | Comments
Arrowhead Framework summer school assignment | Jerker | Presentations, Sept 29 9-12 and Oct 6 13-15, webex. | Recording of presentations will be made. If you have a webex account you will get a link to the recorded session.
Core services
ServiceRegistry v4.0 | Jerker | SysD ready | Comments are appreciated!
Authorisation v4.0 | Jens | SysD distributed. Public key infrastructure. Session control token e.g. X509. | Comment appriiacted. Document to be copied to WP1 and Arrowhead Framework wiki sites. Access problem sto be sorted out by Jerker and Csaba. Ensure that AAA is consistently addresses and differentiated from safety. Connection to block chain specifically for Accounting. Integration/differentiation from Smart service Contract.
Orchestration v4.0 | Csaba | SysD distributed. Orchestration store process is improved. Integration with QoS. Integration with financial aspects. | Comment appreciated. Financial aspect to be synchronised with SEB.
PlantDescription | Simon | Update of the existing SysD 3.0. Draft 4.0 SysD, SD, IDD, SP, CD. New experimental code uploaded. Push of data Orchestration is sketched. | Comment appreciated.
Configuration | Emanuel | SysD and SD document drafts in git repository. Used Node JS for prototyping. | Comment appreciated. Hasan has core system prototyped in Node JS.
SystemRegistry | Ani | SysD, SD, IDD document draft in git repository. REST IDD to be added. | Comment appreciated.
DeviceRegistry | Silia | SysD, SD, IDD document draft in git repository. REST IDD to be added. | Comment appreciated.
Historian | Jens | SysD and other documentation is cleaned up. Code cleaned up code base. Integration with the EventHandler is next step. | Jens i making further updated of documentation.
EventHandler | Michele | merge with Historian.
QoS | Michele | No news
Gatekeeper | Csaba | Cleaned up v3.2. 4.0 prerelease due in 2-3 weeks. | Adi to contribute to testing of 4.0 prerelease.
Translator | Hasan | No news
Core system integration coordination | Hasan | Telco on Translator, Historian and EventHandler | webex meeting Thursday Sept 28 13-14.30
Proposals for support core system
SafetyManager | Simon | Ideas presented. | Send requirements to Oystein. Safety system can be an security attach point.
Gateway service | Csaba | New system for secure inter cloud data path. Based on ANQP brockers. | SysD and other documents available in 2-3 weeks.
Self adapatabiliyt | Markus | No news
Smart Service Contract | Ulf | Requirements definitions in process. Possible new name is “asset broker”. | Draft requirements to be released in a few weeks. Implementation is expected to be using distributed ledger technology.
Engineering tool for legacy adapters | Mario
Docker containers | Fernando | Docker containers for core service deployment. | Please use and provide feedback for improvements. Detailed info to presented Friday 29/9.
Application services

## 171010
Table 1
171010 status
Topic | Responsible | Status | Comments
Arrowhead Framework summer school assignment | Jerker | Presentations, Sept 29 9-12 and Oct 6 13-15, webex. | Recordings uploaded to Arrowhead Framework git.
Core services
ServiceRegistry v4.0 | Jerker | SysD ready | Update of SysD with references and discussion on accepted interface protocols
Authorisation v4.0 | Jens | SysD distributed. Public key infrastructure. Session control token e.g. X509. | No news
Orchestration v4.0 | Csaba | SysD distributed. Orchestration store process is improved. Integration with QoS. Integration with financial aspects. | No news
PlantDescription | Simon | Update of the existing SysD 3.0. Draft 4.0 SysD, SD, IDD, SP, CD. New experimental code uploaded. Push of data Orchestration is sketched. | Work in progress more news to come.
Configuration | Emanuel | SysD and SD document drafts in git repository. Used Node JS for prototyping. | Documentation in finalisation.
SystemRegistry | Ani | SysD, SD, IDD document draft in git repository. REST IDD to be added. | Document updated. Telco yesterday. Defining a use case to build the bootstrapping process. Relations to QoS and PlantDescription to be defined. Plan to write paper on the bootstrapping process. Investigate the usage of security controllers for storing of sensitive data.
DeviceRegistry | Silia | SysD, SD, IDD document draft in git repository. REST IDD to be added. | See SystemRegistry
Historian | Jens | SysD and other documentation is cleaned up. Code cleaned up code base. Integration with the EventHandler is next step. | No news
EventHandler | Michele | merge with Historian. | No news
QoS | Michele | No news | No news
Gatekeeper | Csaba | Cleaned up v3.2. 4.0 prerelease due in 2-3 weeks. | No news
Translator | Hasan | No news | Starting to look att translation to/from Apache Kafka
Core system integration coordination | Hasan | Telco on Translator, Historian and EventHandler | Two webex meetings. MoM uploaded to WP1 and Arrowhead Framework repositories. Eventhandler to handle message log data, event distribution and SoS event notifications.
Proposals for support core system
SafetyManager | Simon | Ideas presented. | Requirements sent to Oystein.
Gateway service | Csaba | New system for secure inter cloud data path. Based on ANQP brockers. | No news
Self adapatabiliyt | Markus | Started to define a SW engineering process for using a control loop approach for adaptability of systems operation based on some deviation detection. | Interest from Michelle and the QoS to cooperate. SysD document is requested.
Smart Service Contract | Ulf | Requirements definitions in process. | Meeting last week with Volvo, SEB, LTU. NXP interested to participate. Currently defining use case. Next meeting Thursday 19/10 15.30. Ulf will invite the WP1 mailing list.
Engineering tool for legacy adapters | Mario |  | No news
ModbusTCP | Christian | Presented a Modbus TCP | Will set up a webex working group. Proposed people to attend is at least Hasan and An Lam + TWT team.
PLC integration | Alois |  | No news
Docker containers | Fernando | Docker containers for core service deployment. | Presentation of docker containers for v3.0. Will update documentation and wiki.
Application services