## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
180807
| Table 1 | 180807
180821
| Table 1 | 180821
180807
| Table 1 | 180807
180724
| Table 1 | 180724
180710
| Table 1 | 180710
180529
| Table 1 | 180529
180515
| Table 1 | 180515
180417
| Table 1 | 180417
180403
| Table 1 | 180403
180320
| Table 1 | 180320
180220
| Table 1 | 180220
180206
| Table 1 | 180206
180123
| Table 1 | 180123
171219
| Table 1 | 171219
171205
| Table 1 | 171205
171121
| Table 1 | 171121
171107
| Table 1 | 171107
171024
| Table 1 | 171024
171010
| Table 1 | 171010
170926
| Table 1 | 170926

## 180821
Table 1
Dissemination | Jerker | Erik leaves the project and Hans Forsberg enters in his place.
Update of Arrowhead Framework wiki site | Csaba | Almost finished. 75% GitHub setup completed.
Service naming convention | Jens | Nothing new since last meeting. There is a need for it to be able to recognize Arrowhead Core and Support Core services. Discussion ongoing between Csaba, Jens and Jerker.
Debian instalation package | Thomas | Meeting last week. Tested and there is some need to improve. Suggestions will be e-mailed to Thomas.
Core services
ServiceRegistry v4.1 | Csaba | No news.
Authorisation v4.1 | Kiran/Csaba | No news.
Orchestration v4.1 | Csaba | No news.
CertificateAuthority | Gabor/Csaba/Ani/Silia | Cooperation started with the certification authority.
Management Tool | Csaba | Under development. Screen shots to be shown.
DataManager | Jens | Available in GitHub now. Open for refactoring to a common Arrowhead Framework style.
Translator |  | Hasan has left the project.
EventHandler v4.1 | -> Csaba | Rewritten and part of the 4.0 release.
QoS v4.1 | Michele/Luis | Should be ready within a couple of weeks. Other than that no news.
Gatekeeper v4.1 | Csaba | No news.
Gateway v4.1 | Csaba | No news.
PlantDescription | Pal | Will start working on it again some time during the fall. Csaba and Pal.
Configuration | Emanuel | No work at all going on presently. Noone "owns" the configuration system right now.
WorkFlowManager/ Choreography | Csaba | No news.
SystemRegistry | Ani | Meeting held in the Austrian team about integrating into the present code base. Csaba, Zoltan and Pal involved. Integration estimated to be ready in mid September. Demo at the meeting in San Sebastian.
DeviceRegistry | Silia
Onboarding | Ani/Silia
Smart Service Contract | Ulf/Emanuel | Working presently with a system called the "Broker". Documentation is available as described in an e-mail sent out to the Wp1 mailing list. Needs reponse on the documentation. There is a working group involving SEB and Volvo.
SafetyManager | -> Daniela | No report.
Self adapatabiliy security | Silia | All documents completed and available in the repo. Review appreciated! Needs to complete onboarding before proceeding.
Engineering tool for legacy adapters | Mario | Started data structure editor started for D1.3. Development in progress. Demo intended for the meeting in San Sebastian.
Datastructure Editor | Mario
Device description editor | Mario
Code generator | Mario
Consumer code generation | Cristina | Paper in progress. Entering development, focusing on documentation, after that.
Autonomic orchestration/configuration | An | Working on implementation. Other than that: No news. SysD document available. Needs updates, though.
ModbusTCP | Nadin/Christian/ Jose | No report.
PLC integration IEC 61499 | Alois/Kiru | Works with integration and trouble shooting right now. Needs and gets support from Csaba.
Docker containers | Haris | No report.
Semi conductor equipment integration | Francois + Agileo | Not discussed.
Smart parking application | Haris | Not discussed.
Heat prediction system | Thomas | Not discussed.
V4.0 integration - SoS Test Tool | Erik | Should we act on the supporting core services?
FiWare - IDS interoperability | Jan/Jerker | No report.

## 180807
Table 1
Dissemination | Jerker | Miren: Submitted Danobat use case from Productive4.0 to Spanish journal
Update of Arrowhead Framework wiki site | Csaba | Updates going on. Can for now not upload figures. Need update of site configuration. Jerker will support Csaba on this.
Service naming convention | Jens | No update
Debian instalation package | Thomas | Issues solve with Csaba. Code to generate Debian installation packages is OK. Thomas will call for a telco on the continuation of this.
Core services
ServiceRegistry v4.1 | Csaba | Suggestions on how to deploy the core system with a single code base. But currently with various MAVEN configurations.
Authorisation v4.1 | Kiran/Csaba
Orchestration v4.1 | Csaba
CertificateAuthority | Gabor/Csaba/Ani/Silia | AITIA will take over a first proof of concept for the CA system.
Management Tool | Csaba | Csaba will share first screen shots to a smaller group via email.
DataManager | Jens | No update
Translator | Hasan | No update
EventHandler v4.1 | -> Csaba | No update
QoS v4.1 | Michele/Luis | Working in the integration to v4.0. Code to be reviewed coming weeks to gather with Csaba.
Gatekeeper v4.1 | Csaba | No update
Gateway v4.1 | Csaba | No update
PlantDescription | Pal | No update
Configuration | Emanuel | No update
WorkFlowManager/ Choreography | Hasan/Csaba | Discussion with Infineon Hungary last week. Requirement input.
SystemRegistry | Ani | Meeting with Csaba yesterday. Minor updates before 4.0 release. Time line late August early Sept.
DeviceRegistry | Silia
Onboarding | Ani/Silia | Time plan is November and meeting in San Sebastian.
Smart Service Contract | Ulf/Emanuel | A protocol for asset transfer is in development. Plan for San Sebastian will be reported next bi-weekly.
SafetyManager | -> Daniela | Meeting Sept. 11
Self adapatabiliy security | Markus | Meeting with AVL and GUP. Ideas documented in a paper, start early Sept.
Engineering tool for legacy adapters | Mario | No update
Datastructure Editor | Mario | No update
Device description editor | Mario | No update
Code generator | Mario | No update
Consumer code generation | Cristina | No update
ModbusTCP | Nadin/Christian/Jose | No update
PLC integration IEC 61499 | Alois/Kiru | No update
Autonomic orchestration/configuration | An | No update
Docker containers | Haris | No update
Semi conductor equipment integration | Francois + Agileo | Meeting last week. No info on progress.
Smart parking application | Haris | No update
Heat prediction system | Thomas | Two out of three providers are working. Possible demo next bi-weekly.
V4.0 integration - SoS Test Tool | Erik | No update
FiWare - IDS interoperability | Jan/Jerker | No update
AOB

## 180724
Table 1
Dissemination | Jerker | SI in IEEE ICPS or IEEE II, Extended version Productive SS in IEEE Infocommunications journal, Paper by Daniela is coming, Paper by Haris submitted to Embedded system week WS on education.
Update of Arrowhead Framework wiki site | Csaba | No update
Service naming convention | Jens | No update
Debian instalaltion package | Thomas | No update
Core services
ServiceRegistry v4.1 | Csaba | Suggestions from TU Vienna and Dokerisation, Code review from Thomas AAU.
Authorisation v4.1 | Kiran/Csaba
Orchestration v4.1 | Csaba
CertificateAuthority | Gabor/Csaba/Ani/Silia | Meeting this or next week.
Management Tool | Csaba | No update
DataManager | Jens | No update
Translator | Hasan | No update
EventHandler v4.1 | -> Csaba | No update
QoS v4.1 | Michele/Luis | Integrated to v4.0, Final test phase to be concluded.
Gatekeeper v4.1 | Csaba | No update
Gateway v4.1 | Csaba | No update
PlantDescription | Pal | No update
Configuration | Emanuel | No update
WorkFlowManager/ Choreography | Hasan/Csaba | No update
SystemRegistry | Ani | Meeting Aug 6. with Csaba and Pal. NXP interested to jon with respect to secure controllers
DeviceRegistry | Silia
Onboarding | Ani/Silia
Smart Service Contract | Ulf/Emanuel | Block server to run at SEB, NXP, LTU.
SafetyManager | -> Daniela | Meeting in Sept. Date not fixed yet.
Self adapatabiliy security | Markus | No update
Engineering tool for legacy adapters | Mario | No update
Datastructure Editor | Mario | No update
Device description editor | Mario | No update
Code generator | Mario | No update
Consumer code generation | Cristina | Paper in progress.
ModbusTCP | Nadin/Christian/Jose | No update
PLC integration IEC 61499 | Alois/Kiru | http layer working,
Autonomic orchestration/configuration | An | No update
Docker containers | Haris | Zoltan Dockerisation of v4.0.
Semi conductor equipment integration | Francois + Agileo | No update
Smart parking application | Haris | Two local clouds working. Suggestion to connect to Erik Karlsson at BnearIT.
Heat prediction system | Thomas | No update
V4.0 integration - SoS Test Tool | Erik | No update
FiWare - IDS interoperability | Jan/Jerker | BaSys integration, meeting mid August.
AOB

## 180710
Table 1
Topic | Responsible | Status
Dissemination | Jerker | Choreography paper to ETFA accepted
Update of Arrowhead Framework wiki site | Csaba, Fernando | No news since Lulea workshop
Service naming convention | Jens
Debian instalaltion package | Thomas | Test by Csaba next week, once OK to be released on the wiki site.
Core services
ServiceRegistry v4.1 | Csaba | Bind server setup.
Authorisation v4.1 | Kiran/Csaba
Orchestration v4.1 | Csaba
CertificateAuthority | Gabor/Csaba/Ani/Silia | No updates
Management Tool | Csaba | Engineering time and run time views. Dev process continues dev style.
DataManager | Jens | No updates
Translator | Hasan | No updates
EventHandler v4.1 | -> Csaba | No updates
QoS v4.1 | Michele | Integration with EventHandler v4.0
Gatekeeper v4.1 | Csaba | Integration to platforms is upcoming
Gateway v4.1 | Csaba | Integration to platforms is upcoming
PlantDescription | Pal | No updates
Configuration | Emanuel | No updates
WorkFlowManager/ Choreography | Hasan/Csaba | No updates
SystemRegistry | Ani | Final integration meeting with Csaba and Pal
DeviceRegistry | Silia | Final integration meeting with Csaba and Pal
Onboarding | Ani/Silia | Waiting for SystemRegsitry and Device Registry finalisation
Smart Service Contract | Ulf/Emanuel | No updates
SafetyManager | -> Daniela | Monthly telcos from September
Self adapatabiliy security | Markus | No updates
Engineering tool for legacy adapters | Mario | No updates
Datastructure Editor | Mario | No updates
Device description editor | Mario | No updates
Code generator | Mario | No updates
Consumer code generation | Cristina | No updates
ModbusTCP | Nadin/Christian/Jose | No updates
PLC integration IEC 61499 | Alois/Kiru | No updates
Autonomic orchestration/configuration | An | Integration to v4.0, integration wit FHB GAMF code.
Docker containers | Fernando | Zoltan is testing TUW docker implementation
Semi conductor equipment integration | Francois + Agileo | No updates
Smart parking application | Haris | No updates
Heat prediction system | Thomas | Uploaded application compatible v3.0. Upgrading to v4.0 is ongoing.
V4.0 integration - SoS Test Tool | Erik | No updates
FiWare - IDS interoperability | Jan/Jerker | No updates
AOB

## 180529
Table 1
Table 1
Topic | Responsible | Status | Comments
P4.0 WS June | Erik
Dissemination | Jerker
Update of Arrowhead Framework wiki site | Csaba, Fernando | Arrowhead Framework Git repo restructured, Productive4.0 OWN cloud should now be the main repo for project documentation.
Core services
ServiceRegistry v4.0 | Jerker | Release of final 4.0, full document.
Authorisation v4.0 | Kiran | Release of final 4.0, full document.
Orchestration v4.0 | Csaba | Release of final 4.0, full document.
CertificateAuthority | Gabor/Csaba/Ani/Silia | Delayed until July/August
DataManager | Jens | Close to v4.0 release
Translator | Hasan | Will move to Scania but will continue to maintain the Translator system
EventHandler | -> Csaba | Release of final 4.0, full document.
QoS | Michele | Integration to v4.0 is ongoing same for QoS Manager and QoS monitor
Gatekeeper | Csaba | Release of final 4.0, full document.
Gateway | Csaba | Release of final 4.0, full document.
PlantDescription | Pal | Break out session in Lulea
Configuration | Emanuel | M.Sc. student work at LTU. paper planed til end of the year.
WorkFlowManager/ Choreography | Hasan/Csaba | Paper presented at ICPS. Code tested at Volvo 2 weeks ago. Will be integrated to v4.0 in due core, Choreography paper submitted to ETFA.
SystemRegistry | Ani | Integration to v4.0 is ongoing. Meeting with Csaba June 8.
DeviceRegistry | Silia | Integration to v4.0 is ongoing. Meeting with Csaba June 8.
Onboarding | Ani/Silia | Connection to Gabor for usage of a TPM device. Implementation and integration v4.0 July August.
Smart Service Contract | Ulf/Emanuel | Meeting with SEB. Csaba, Pal and Emanuell meeting last week. SysD and SD draft will be released soon.
SafetyManager | -> Daniela | Meeting last week. Break out for Lulea meeting.
Self adapatabiliy | Markus | Discussion with An Lam for cooperation
Engineering tool for legacy adapters | Mario | Tools described in D1.3
Datastructure Editor | Mario | Tools described in D1.3
Device description editor | Mario | Tools described in D1.3
Code generator | Mario | Further discussion in Lulea
Consumer code generation | Cristina | Further discussion in Lulea. Position paper being worked-on.
ModbusTCP | Nadin/Christian/Jose | No update
PLC integration IEC 61499 | Alois/Kiru | Implementation of an HTTP communication with 61499
Autonomic orchestration/configuration | An | Need to reorganise the architecture, integration to PlantDescription. Discussion with An Lam for cooperation
Docker containers | Fernando | Meeting with Mondragon. Link to Haris work in Vienna, discussion in Lulea.
Semi conductor equipment integration | Francois + Agileo | Meeting with Hasan and An Lam. Preparing break out for workshop in Lulea.
Smart parking application | Haris | Demo in Lulea. Docker v3.0 and v4.0. Devops status of Arrowhead Framework. Metting with Csaba next week.
Heat prediction system | Thomas | SysD draft in progress, draft ready next week.
V4.0 integration - SoS Test Tool | Erik | Test tool updates on automated testing, recording and playback. Demo of the Test tools in Lulea with air-traffic services related to snow depth and run-way conditions.
FiWare - IDS interoperability | Jan/Jerker | Delayed until mid August.
AOB | Csaba | Please use and test the release v4.0 code in the Arrowhead Framework git repository.

## 180515
Table 1
Topic | Responsible | Status | Comments
P4.0 WS June | Erik | Invitation sent out
Dissemination | Jerker | ICPS 2018, a number of papers accepted. 3 from LTU. Maybe some more from others. No info at the meeting. INDIN, IECON, ETFA
Update of Arrowhead Framework wiki site | Csaba, Fernando | Work is in progress. Available at the soaforge site.Fernando asks for feedback on information structure and contents.
Core services
ServiceRegistry v4.0 | Jerker | Documentation and code is ready. Jens and Zoltan are cooperating with Csaba, debugging and tuning usability.
Authorisation v4.0 | Kiran | Documentation and code is ready. Looking at opportunities to use block chain solution. Work in progress.
Orchestration v4.0 | Csaba | Documentation and code is ready
CertificateAuthority | Gabor/Csaba/Ani/Silia | No update
DataManager | Jens | Working with integration with the rest of the framework. Documentation is a bit outdated, though.
Translator | Hasan | Performing integration with the 4.0 framework in progress. Documentation is up to date.
EventHandler | -> Csaba | No update
QoS | Michele | Integrated with Arrowhead Framework 4.0. June release will slip. Documentation is in progress. Mid June for documentation.
Gatekeeper | Csaba | No update.
Gateway | Csaba | No update.
PlantDescription | Pal | No update.
Configuration | Emanuel | No news this time.
WorkFlowManager/ Choreography | Hasan/Csaba | The paper is being presented soon. The documentation exists but is it in the right place. An implementation exist. Integrated with AF 3.0. Integration and demo done at Volvo. Successful integration!
SystemRegistry | Ani | No update
DeviceRegistry | Silia | No update
Onboarding | Ani/Silia | No update
Smart Service Contract | Ulf/Emanuel | The SD and SysD documents are in progress for what's called "the Broker". The Smart Service Contract is subject to being renamed. Is in an early stage of prototyping and is therefore not integrated with Arrowhead Framework core systems.
SafetyManager | -> Daniela | Miren reported: Meeting next week. No updates other than that.
Self adapatabiliy | Markus | No update
Engineering tool for legacy adapters | Mario | No update
Consumer code generation | Cristina | Work in progress with a paper on the subject.
ModbusTCP | Nadin/Christian | No progress since last meeting. Nadin is on a leave. A new resource is being searched for.
PLC integration IEC 61499 | Alois/Kiru | Integration with AF 4.0 started up, assisted by Csaba.
Autonomic orchestration/configuration | An | No update
Docker containers | Fernando | No update
Repository | Fernando | No updates on that. The repository will only contain code and feature branches will be introduced. Erik to arrange a meeting with Fernando, Jerker and Csaba.
Semi conductor equipment integration | Francois + Agileo | The set of systems to be reviewed at our bi-weekly needs to be updated with this. Working with documentation updates. Exploring the OPCUA standard. Development of IDD documentation now. Need support from OPCUA expert. Hasan is proposed. Will arrange a meeting off-line.
AOB
V4.0 integration - SoS | Erik | No update
FiWare - IDS interoperability | Jan/Jerker | No update (according to Jan)

## 180417
Table 1
Table 1
Table 1
Topic | Responsible | Status | Comments
P4.0 WS June | Jerker | Invitation to be distributed end of this week.
Dissemination | Jerker | ICPS news: at least 6 papers in our SS accepted. Tutorial accepted. At least 1 paper submitted to INDIN 2018.
Eclipse foundation | Jerker | Jens and Csaba reported. Update of report based on todays discussion. Report will be available in the repository.
Core services
ServiceRegistry v4.0 | Jerker | Documentation and code is ready
Authorisation v4.0 | Jens | Documentation and code is ready
Orchestration v4.0 | Csaba | Documentation and code is ready
CertificateAuthority | Gabor/Csaba/Ani/Silia | No update
DataManager | Jens | Code is ready, documentation in progress. A demo system using the DataManager is in progress
Translator | Hasan | No update
EventHandler | -> Csaba | No update
QoS | Michele | Development still ongoing. June release may slip.
Gatekeeper | Csaba | Code works well. Documentation need to finalised. Now DNS-SD included.
Gateway | Csaba | Code works well. Documentation need to finalised. Now DNS-SD included.
PlantDescription | Pal | No resource currently assigned to the PlantDescription. Eventually a PhD student from Pal.
Configuration | Emanuel | Work prototype has been demonstrated at LTU. Students work is currently on hold.
WorkFlowManager/Choreography | Hasan/Csaba | Hasan paper accepted to ICPS. Csaba paper rejected. First generation of demo at Volvo.
SystemRegistry | Ani | Documentation for D1.3, Code updates ongoing
DeviceRegistry | Silia | Documentation for D1.3, Code updates ongoing
Onboarding | Ani/Silia | On-boarding paper accepted to ICPS.
Smart Service Contract | Ulf/Emanuel | Meeting last week at NXP with SEB, Sintef. NXP started on a prototype. Specification is the main focus still, SysD. BME is also providing input here, merge to the NXP, SEB, LTU work is necessary.
SafetyManager | -> Daniela | Telco planed for May.
Self adapatabiliyt | Markus | No updates. Telco planed for May with Norway.
Engineering tool for legacy adapters | Mario | Specification is uploaded to OwnCloud. Waiting to be included into D1.3.
Consumer code generation | Cristina | Still specification phase.
ModbusTCP | Nadin | No udpdate
PLC integration IEC 61499 | Alois | Work in progress. Meeting with David Hästback.
Autonomic orchestration/configuration | An | Implementation in the works. SD and IDD ready v001. Meeting with Jerker Monday discussion on interaction with existing Arrowhead Framework core systems.
Docker containers | Fernando | Documentation to D1.3. Chap 6.3. Feedback from thus who have used the Docker installation is highly welcome.
Security evaluation | Samer/Adi | Work ongoing. Finding to be shared early May. Slot on agenda in June?
Applications
Tank level control system | Jens | See above
V4.0 integration - SoS | Erik | No update
FiWare - IDS interoperability | Jan/Jerker | LTU to contract a company to provide a proposal and first implementation on this.
Wiki and repository clean-up |  | Csaba volunteered to help out. Jerker and Csaba telco Friday May 4. Fernando also volunteered.
Semi equipment integration | CEA + Agileo | OPC-UA as protocol.
Flexoffer | Thomas | Arrowhead cloud made in Mantis. Heat prediction for buildings. Used for pre-heating a building to prevent problem during maintenance of the heating system.

## 180403
Table 1
Table 1
Topic | Responsible | Status | Comments
P4.0 WS June | Jerker | Invitation to be distributed end of this week.
Dissemination | Jerker | ICPS news: at least 7 papers in our SS accepted. Tutorial accepted. Erkki: Productive4.0 has published Arrowhead Makes You Productive.
Eclipse foundation | Jerker
Core services
ServiceRegistry v4.0 | Jerker | Documentation ready this week. Feed back from pre-release users.
Authorisation v4.0 | Jens | Documentation ready this week. Feed back from pre-release users.
Orchestration v4.0 | Csaba | Documentation ready this week. Feed back from pre-release users.
CertificateAuthority | Gabor/Csaba/Ani/Silia | No update
DataManager | Jens | No update
Translator | Hasan | No update
EventHandler | -> Csaba | No update, Erkki will set up a meeting with Jens and Csaba to conclude the interaction between DataManager and Eventhandler.
QoS | Michele | Development team no established. Concrete results expected shortly.
Gatekeeper | Csaba | Code works well. Documentation need to finalised.
Gateway | Csaba | Code works well. Documentation need to finalised.
PlantDescription |  | No resource currently assigned to the PlantDescription. Eventually a PhD student from Pal.
Configuration | Emanuel | Work prototype has been demonstrated at LTU. Code may be shared shortly.
WorkFlowManager/Choreography | Hasan/Csaba | Paper accepted to ICPS. Use prototype in real pilot i May at Volvo. Discussion Hasan/Csaba. Commonalities and differences found. Discussion ongoing.
SystemRegistry | Ani | Documentation for D1.3
DeviceRegistry | Silia | Documentation for D1.3
Onboarding | Ani/Silia | On-boarding paper accepted to ICPS.
Smart Service Contract | Ulf/Emanuel | SysD draft will be ready for June meeting. SysDD in the works. Meeting in Hamburg Monday April 9-10, with NXP, SEB and LTU. BME is also providing input here.
SafetyManager | -> Daniela | Break out at June meeting.
Self adapatabiliyt | Markus | Technology discussion on-going with implementation in parrallel.
Engineering tool for legacy adapters | Mario | No update
Consumer code generation | Cristina | No update
ModbusTCP | Nadin | Initial implementation tested with some progress. Possible demonstration in June.
PLC integration IEC 61499 | Alois | No update
Autonomic orchestration/configuration | An | Implementation in the works. SD and IDD ready by next week.
Docker containers | Fernando | No update
Security evaluation | Samer/Adi | Questions put to Csaba,… Response is needed before next step. Presentation of repport at June meeting.
Applications
Tank level control system | Jens | No update
V4.0 integration - SoS | Erik | Documentation is becoming avaialble. Unfortunate no update on the implementation of this into the test and integration tools.
FiWare - IDS interoperability | Jan/Jerker

## 180320
Table 1
Table 1
Topic | Responsible | Status | Comments
P4.0 WS June | Jerker
Dissemination | Jerker | a number of ICPS papers accepted, Papers prepared for submission to INDIN, IECOn and ETFA. IEEE II submission by Daniela.
Eclipse foundation | Jerker | Jens, Csaba to report April 17.
Core services
ServiceRegistry v4.0 | Jerker | Auto cleaning in works
Authorisation v4.0 | Jens | NGAC HMI in the works
Orchestration v4.0 | Csaba | OrchestrationStore is separated from Orchestration, meta data considerations
CertificateAuthority | Gabor/Csaba/Ani/Silia | Gabor will lead
DataManager | Jens | Direct service interface between DataManager and EventHandler. IDD to be updated
Translator | Hasan | No update not integrated to v4.0, IDD exists
EventHandler | -> Csaba | Move responsibility to who, Event distribution focus
QoS | Michele | Integration with 4.0 is ongoing, IDD old v3.2 - v4.0 in progress
Gatekeeper | Csaba | Examining MQTT solution
Gateway | Csaba | Examining MQTT solution
PlantDescription | Simon | No update
Configuration | Emanuel | Demo of working system using AA to restrict which data to use. No integration with v4.0 yet. No time line defined. No IDD yet.
WorkFlowManager | Hasan | Prototype. Results for June is expected v3.0 ev v4.0. IDD
Choreography | Csaba | No update. Discussion with Hasan and WorkFlowManager
SystemRegistry | Ani | Documentation + onboarding, IDD in git
DeviceRegistry | Silia | Documentation + onboarding, IDD in git
Onboarding | Ani/Silia | Documentation + onboarding, next step is intergration with v4.0
Smart Service Contract | Ulf | Meeting tomorrow with a use case, meeting v15, LTU, NXP, SEB. Meetings on identity, and inter cloud authorisation. Architecture not stable yet. no IDD until June.
SafetyManager | Simon
Self adapatabiliyt | Markus | Further updates of GAMF code and documentation. No IDD yet
Engineering tool for legacy adapters | Mario | No update
Consumer code generation | Cristina | Starting up
ModbusTCP | Nadin | No update
PLC integration IEC 61499 | Alois | No update
Autonomic orchestration/configuration | An | Semantic web tech integrated to Arrowhead Framework. Set up telco with Hartwig Baumgartel, WP7. No IDD yet.
Docker containers | Fernando | Dockerisation of v3.0. v4.0 design document support the design of the dockerisation. Individual dockers for each core system. Integration with Pal and Csaba. Template for what info is need to create a docker container for a core system. First version distributed next week.
Issue | Erkki | Csaba to take over the EventHandler development. Jens to take lead on integration between EventHandler and DataManager.
Applications
Tank level control system | Jens
V4.0 integration - SoS | Erik | No progress - Do need IDD for each core system
FiWare - IDS interoperability | Jan/Jerker | Work on-going in MiDIH. Prel report on IDS- Arrowhead Framework made by Infineon. MIDIH to write report on FiWare-IDSS-Arrowhead Framework comparison

## 180220
Table 1
Topic | Responsible | Status | Comments
P4.0 WS June | Jerker | WP2 will join Dates June 19-20 + ev 21.
Dissemination | Jerker | 13 papers submitted to our SS at ICPS. We will request reviews from several of you. Invitation will be distributed tonight.
Demonstrations Athens |  | 2 poster + 1 demo Austria, 1+1 demo + 3/2 posters Csaba, 1 poster + 1 demo P4.0 + FAR-EDGE Hasan, 1 demo + ev. 1 poster Kiran, 1 poster + 1demo? Jens, 1 poster Mario, 1+1 QoS + ev EventHandler Michele, 1 poster Simon, 1 demo +1 poster test tool Erik, 1 demo NXP,
Core services
ServiceRegistry v4.0 | Jerker | 4.0 pre-release of ServiceRegistry (DNS-SD not included), Authorisation, Orchestration, Gatekeeper and Gateway.
Authorisation v4.0 | Jens
Orchestration v4.0 | Csaba
PlantDescription | Simon | No update
Configuration | Emanuel | No update
SystemRegistry | Ani | Code update in progress for both
DeviceRegistry | Silia
DataManager | Jens | Integration to 4.0 pre-release version, time line March
EventHandler | Michele | On-hold due to funding reason
QoS | Michele | Integration to 4.0 pre-release version, time line April/May
Gatekeeper | Csaba
Gateway | Csaba | Requires RabbitMQ
Translator | Hasan | Integration to 4.0 pre-release version, time line March
Core system integration coordination | Hasan | Closed this action
Proposals for support core system
SafetyManager | Simon | MoM from Lisbon, on-hold till end of March.
Self adapatabiliyt | Markus | No update
Smart Service Contract | Ulf | Meetings with NXP and AAA. Demo by NXP through SEB in Athens. Draft specification is prepared.
Engineering tool for legacy adapters | Mario | Implementation work done by one programmer. First version by end of April. Defining semantics + variables. Code generation will be connected to the Arrowhead Framework.
ModbusTCP
PLC integration IEC 61499 | Alois
Docker containers | Fernando
Midi-Arrowhead |  | First workshop on Fiware-Arrowhead integration Feb 26 11-12
IoT Cloud? |  | Csaba reposted on an IoT cloud that is now provided with Arrowhead Framework interfaces.
Meeting Bosch IoT and Eclipse |  | Jerker to meet Bosch and Eclipse Feb 22-23 in Berlin
Contribution from FAR-EDGE |  | A WorkFlow manager is being defined. A more through presentation to come in upcoming bi-weekly.

## 180206
Table 1
Topic | Responsible | Status | Comments
Dissemination |  | Paper from Öystein, 2 Markus, 2 from LTU, 2 from Budapest coming up for St.Petersburg. One paper coming up from Mondragon, not scheduled for any specific conference yet.
Demonstrations Athens |  | Daniela: Needs more information about the meta model from Csaba and Pal perform the demo. A two hour would probably do it. Kiran/Csaba: Will probably be unable to demo the authorization system. NGAK integration will probably not work.
Core services
ServiceRegistry v4.0 | Csaba | The three core system (and gateway and gate keeper) having a next release next week. Info will be e-mailed by Csaba. Pre-release in next week of 4.0.
Authorisation v4.0
Orchestration v4.0
Gatekeeper/ gateway
Data Manager |  | Not reported
Translation |  | Not reported
PlantDescription | Simon | No news.
Configuration | Simon | No news.
Safety Manager | Simon | There is an update in the minutes from the Lisbon meeting. Have a look at that.
Smart Service Agreement | Ulf | No news.
SystemRegistry |  | Not reported
DeviceRegistry |  | Not reported
Historian |  | Not reported
EventHandler | Michele | No news. Allocating a developer. News expected in two weeks from now.
QoS | Michele | No news. Allocating a developer. News expected in two weeks from now.
Onboarding procedure | Csaba | A paper has been submitted and that's all. Awaiting accept.
Self Adaptability |  | Not reported
Translator, Historian, …Hasan, |  | Not reported
Proposals for support core system
ModbusTCP |  | Not reported
Engineering tool for legacy adapters |  | Not reported
PLC integration | José | No news.
Smart Service Contract |  | Not reported
Self adapatability |  | Not reported
SafetyManager |  | Not reported
Docker containers | Fernando | Work continues.
v4.0 SoS | Erik | No news.
Integration P4.0 WP | Erik | Nothing special to mention. Pal is unable to participate in the WP8 telco on Thursday due to a lecture.
AoB | Csaba | WP1 in the WP2 use case Philips
Next meeting |  | Tuesday February 20th, 15:30-17:00 (CET)

## 180123
Table 1
Topic | Responsible | Status | Comments
WP1 Lisbon WS followup | Jerker/Pedro | Time line for v4.0 reelse. Components by Early March. Working SoS for most core components by Mid June.
Dissemination | Jerker | Ani+Silia On-boarding procedure, Kiran/Cristina AAA paper + NGAC, Csaba 2 papers workflow management + gateway,
Demonstrations Athens | Jerker | Update of MoM to be distributed
Core services
ServiceRegistry v4.0 | Jerker | No major updates
Authorisation v4.0 | Jens | Integration of Csaba code + Kiran/Cristina code
Orchestration v4.0 | Csaba | Integration with gateway and gatekeeper
PlantDescription | Simon | No update
Configuration | Simon | No update
SystemRegistry | Ani | No update
DeviceRegistry | Silia | No update
Historian | Jens | No update
EventHandler | Michele | No update
QoS | Michele | No update
Gatekeeper/gateway | Csaba | Integration with orchestration
Translator | Hasan | No update
Onboarding procedure | Ani/Silia | Draft paper in the works
Translator, Historian, …Hasan, | Hasan | Group concluded in Lisbon
Proposals for support core system
ModbusTCP | Christian/Nadin | No update
Engineering tool for legacy adapters | Mario | No update
PLC integration | Alois | Discussion with Hasan. 61499 integration. Sync with students working with Hasan.
Smart Service Contract | Ulf | No update
Self adapatabiliyt | Markus | No update
SafetyManager | Simon | No update
Docker containers | Fernando | 3.2 docker in progress
v4.0 SoS | Erik | First meeting Friday Jan 26.
Integration P4.0 WP | Jerker | WP2 telco Thursday Jan 25, 10.30, WP3 no updates, WP4-5 waiting for invitation from WP4-5. WP7 will attend WP1 June workshop. WP8 & 9 March 6 afternoon meeting in Athens.
AoB |  | Nothing
Next meeting |  | Feb 6, 15.30, CET and then bi-weekly.

## 171219
Table 1
Topic | Responsible | Status | Comments
WP1 Lisbon WS | Jerker/Pedro | Agenda agreed with minor adjustments. Will be updated in repository by tomorrow.
Requirements | Oystein | Deliverable almost on time, D1.2, Daniel and Markus will review and are available. The questioner section is being completed by Csaba and Pal. Draft for internal review will be real later on today.
Dissemination | Jerker | SS by Pal, paper dead line end of January, 2018, INDIN, EFTA, WSFC call for papers will be distributed by Jerker to the mailing list.
Core services
ServiceRegistry v4.0 | Jerker | Implementation team Csaba, Erik. Documentation Jerker
Authorisation v4.0 | Jens | Offline discussion Csaba, Kiran, Jens, Jan on implementation of AA and AAA systems
Orchestration v4.0 | Csaba | No update
PlantDescription | Simon | Preparation for Lisbon demo
Configuration | Simon | Preparation for Lisbon demo
SystemRegistry | Ani | Prepare WS before Lisbon. Preparing break out session in Lisbon. A paper is prepared for ICPS SS by Pal.
DeviceRegistry | Silia | Prepare WS before Lisbon. Preparing break out session in Lisbon. A paper is prepared for ICPS SS by Pal.
Historian | Jens | Some documentation addressing interaction with the Translator.
EventHandler | Michele | For Lisbon: like to discuss new ideas based on requirements.
QoS | Michele | For Lisbon: like to discuss new ideas based on requirements. Inter cloud QoS is upcoming.
Gatekeeper | Csaba | Work in progress, secure version is in progress. Release expected early Jan. Demo in Lisbon.
Translator | Hasan | No update.
Core system integration coordination
Translator, Historian, …Hasan, | Hasan | Documentation will be sent out before Lisbon.
Proposals for support core system
ModbusTCP | Christian | Preparing break out session for Lisbon. Possible presentation in Lisbon Tuesday.
Engineering tool for legacy adapters | Mario | Workgroup meet every 2-3 week. Some commonalities found with Semantics interoperablility. IFAK writing specs. Presentation Tuesday in Lisbon, 5 min.
PLC integration | Alois | Integration to IEC 61499 using MQTT. OPC-UA will be targeted later on.
Smart Service Contract | Ulf | WS last week to prepare Lisbon.
Self adapatabiliyt | Markus | First draft of a SysD uploaded today. Review appreciated. Reviewing interaction with QoS and PlantDescription.
SafetyManager | Simon | Break out session in Lisbon. Preparing use cases which need safety considerations.
Docker containers | Fernando | Work on integrating application samples. Feedback on further improvement for ease of use.
Application services
Next meeting |  | Jan 9 15.30 CET an d then bi-weekly.

## 171205
Table 1
Topic | Responsible | Status | Comments
WP1 Lisbon WS | Jerker/Pedro
Requirements | Oystein
Dissemination | Jerker
Core services
ServiceRegistry v4.0 | Jerker
Authorisation v4.0 | Jens
Orchestration v4.0 | Csaba
PlantDescription | Simon
Configuration | Simon
SystemRegistry | Ani
DeviceRegistry | Silia
Historian | Jens
EventHandler | Michele
QoS | Michele
Gatekeeper | Csaba
Translator | Hasan
Core system integration coordination
Translator, Historian, …Hasan, | Hasan
Proposals for support core system
ModbusTCP | Christian
Engineering tool for legacy adapters | Mario
PLC integration | Alois
Smart Service Contract | Ulf
Self adapatabiliyt | Markus
SafetyManager | Simon
Docker containers | Fernando
Application services

## 171121
Table 1
Topic | Responsible | Status | Comments
WP1 Lisbon WS | Jerker/Pedro | Agenda v02 is in MoM
Requirements | Oystein
Dissemination | Jerker | SS proposal from Pal abstract is on its way deadline Dec 15, Tutorial proposal to be submitted by Feb. Paper to TII. David Hästback take lead for Finish partners. Felix to check in Spain. Markus Tauber action towards ETFA.
Core services
ServiceRegistry v4.0 | Jerker | Next WS on internal Wednesday Now 22.
Authorisation v4.0 | Jens | No update
Orchestration v4.0 | Csaba | Internal WS planed after finalisation fo the ServieRegistry
PlantDescription | Simon | No update
Configuration | Simon | Not update
SystemRegistry | Ani | Updated document in git, working code still not final
DeviceRegistry | Silia | Updated document in git, working code still not final
Historian | Jens | No update
EventHandler | Michele | No update
QoS | Michele | No update
Gatekeeper | Csaba | Progress on documentation and code, no release yet
Translator | Hasan | Working on injection identification
Core system integration coordination
Translator, Historian, …Hasan, | Hasan | No update
Proposals for support core system
ModbusTCP | Christian | No update
Engineering tool for legacy adapters | Mario | Meeting to coordinate ifak and LTU efforts | Hasan to initiate further detailed discussions
PLC integration | Alois | Initial meeting done.
Smart Service Contract | Ulf | No update
Self adapatabiliyt | Markus | Working on the SysD doc. Using a simple use case and tries to connect it to existing adaptability code.
SafetyManager | Simon | No update. Will need to review other standards. | Still interest from Mondragon and Miren
Docker containers | Fernando | Exploring cloud integration using Docker container. Cumolocity, Amazon, … are considered.
Application services

## 171107
Table 1
Topic | Responsible | Status | Comments
WP9 meeting | Pal | Presentation made at WP9 meeting in San Sebastian. Arrowhead Framework differentiation form other | Each WP9 task has now plans to use Arrowhead Framework
WP1 Lisbon WS | Jerker/Pedro | Agenda v02 is in MoM
Requirements | Oystein | Presentation of final work to D1.2. Introduction of requirements related to nano payment and financial services introduced by Christian L (SEB)
Dissemination | Jerker
Core services
ServiceRegistry v4.0 | Jerker | Time line to be define next Wednesday.
Authorisation v4.0 | Jens | Some discussion with Csaba on comment from Kiran to v4.0
Orchestration v4.0 | Csaba | No comments
PlantDescription | Simon | Investigation of tools for SoS engineering, sysML, automML, BIM, discussion with Oscar Carlsson of Midroc. Investigating graf database for implementing the current structure. | automML is based on legacy tools and equipment
Configuration | Emanuel | No updates
SystemRegistry | Ani | Meeting yesterday. First draft on the on-boarding registry SysD. | Doodle for next meeting out.
DeviceRegistry | Silia
Historian | Jens | No updates
EventHandler | Michele | No updates
QoS | Michele | Waiting for master student, a person will be on-board in a few weeks.
Gatekeeper | Csaba | Presentation of Gatekeeper/gateway v4.0 update. Implementation of the Gateway within 5 weeks.
Translator | Hasan | No updates
Core system integration coordination
Translator, Historian, …Hasan, | Hasan | No updates
On-boarding | Ani | See System and DeviceRegistry
Proposals for support core system
SafetyManager | Simon | No updates
Gateway service | Csaba | See Gatekeeper
Self adapatabiliyt | Markus | No updates
Smart Service Contract | Ulf | No updates
Engineering tool for legacy adapters | Mario | Will to specify a semantic definition editor. | Make contact to Jakob Nilsson at LTU
ModbusTCP | Christian | First discussion with An Lam on the issue.
PLC integration | Alois | No update
Docker containers | Fernando | Rasberrypy running core services.
Application services
New topics
Security and Safety | Daniela | See slides distributed by Daniella, Short report from Michele. Paper to be completed in 1 week.

## 171024
Table 1
Topic | Responsible | Status | Comments
Dissemination | Jerker | IEEE ICPS St Petersburg, May 15-18; IEEE INDIN, Porto, July 18-20. | JD and Fredrik will investigate our participation in IEEE ICPS.
Core services
ServiceRegistry v4.0 | Jerker | BnearIT will make the implementation of ServiceRegistry v4.0.
Authorisation v4.0 | Jens | No news
Orchestration v4.0 | Csaba | No news
PlantDescription | Simon | Will present an update next meeting
Configuration | Emanuel | No news
SystemRegistry | Ani | Addressing comment on documentation. Ready mid Nov. Code in development. Will be submitted to Fernando for making docker container while ready.
DeviceRegistry | Silia | Addressing comment on documentation. Ready mid Nov. Code in development. Will be submitted to Fernando for making docker container while ready.
Historian | Jens | New design will be available Nov.
EventHandler | Michele | No news
QoS | Michele | No news
Gatekeeper | Csaba | No news
Translator | Hasan | MQTT in focus. Looking for a better approach for injecting the translator on demand. OPC-UA service by An Lam can be in combination with the Translation system. | Complex functionality/information models in OPC-UA does not have counter parts in other protocols. Semantic translation will be needed to capture e.g. information models.
Core system integration coordination
Translator, Historian, …Hasan, | Hasan | Waiting pattern for the next Historian SysD
- SystemRegistry, DeviceRegistry, Ani | Ani | On-boarding procedure. Proposal from Csaba, comments from Fredrik and Silia. Next meeting probably 6/11.
Proposals for support core system
SafetyManager | Simon | No news
Gateway service | Csaba | No news
Self adapatabiliyt | Markus | SysD documentation preparation.
Smart Service Contract | Ulf | Limiting the work to an Asset broker including payments, SEB, Volvo, LTU, NXP. Comparing with AIOTA, progress on the similar topic. | Presentation at next bi-weekly meeting on potential integration along the supply chain and the product life cycle.
Engineering tool for legacy adapters | Mario | No news
ModbusTCP | Christian | First meeting Oct 26 13.00
PLC integration | Alois | First telco done. Tool from Fortis can be part of interoperability together with Arrowhead Framework
Docker containers | Fernando | Documentation in repository. Wiki is updated. Next step is to deploy container in an embedded systems.
Application services
New topics
Security and Safety | Daniela |  | Will present next bi-weekly meeting

## 171010
Table 1
171010 status
Topic | Responsible | Status | Comments
Arrowhead Framework summer school assignment | Jerker | Presentations, Sept 29 9-12 and Oct 6 13-15, webex. | Recordings uploaded to Arrowhead Framework git.
Core services
ServiceRegistry v4.0 | Jerker | SysD ready | Update of SysD with references and discussion on accepted interface protocols
Authorisation v4.0 | Jens | SysD distributed. Public key infrastructure. Session control token e.g. X509. | No news
Orchestration v4.0 | Csaba | SysD distributed. Orchestration store process is improved. Integration with QoS. Integration with financial aspects. | No news
PlantDescription | Simon | Update of the existing SysD 3.0. Draft 4.0 SysD, SD, IDD, SP, CD. New experimental code uploaded. Push of data Orchestration is sketched. | Work in progress more news to come.
Configuration | Emanuel | SysD and SD document drafts in git repository. Used Node JS for prototyping. | Documentation in finalisation.
SystemRegistry | Ani | SysD, SD, IDD document draft in git repository. REST IDD to be added. | Document updated. Telco yesterday. Defining a use case to build the bootstrapping process. Relations to QoS and PlantDescription to be defined. Plan to write paper on the bootstrapping process. Investigate the usage of security controllers for storing of sensitive data.
DeviceRegistry | Silia | SysD, SD, IDD document draft in git repository. REST IDD to be added. | See SystemRegistry
Historian | Jens | SysD and other documentation is cleaned up. Code cleaned up code base. Integration with the EventHandler is next step. | No news
EventHandler | Michele | merge with Historian. | No news
QoS | Michele | No news | No news
Gatekeeper | Csaba | Cleaned up v3.2. 4.0 prerelease due in 2-3 weeks. | No news
Translator | Hasan | No news | Starting to look att translation to/from Apache Kafka
Core system integration coordination | Hasan | Telco on Translator, Historian and EventHandler | Two webex meetings. MoM uploaded to WP1 and Arrowhead Framework repositories. Eventhandler to handle message log data, event distribution and SoS event notifications.
Proposals for support core system
SafetyManager | Simon | Ideas presented. | Requirements sent to Oystein.
Gateway service | Csaba | New system for secure inter cloud data path. Based on ANQP brockers. | No news
Self adapatabiliyt | Markus | Started to define a SW engineering process for using a control loop approach for adaptability of systems operation based on some deviation detection. | Interest from Michelle and the QoS to cooperate. SysD document is requested.
Smart Service Contract | Ulf | Requirements definitions in process. | Meeting last week with Volvo, SEB, LTU. NXP interested to participate. Currently defining use case. Next meeting Thursday 19/10 15.30. Ulf will invite the WP1 mailing list.
Engineering tool for legacy adapters | Mario |  | No news
ModbusTCP | Christian | Presented a Modbus TCP | Will set up a webex working group. Proposed people to attend is at least Hasan and An Lam + TWT team.
PLC integration | Alois |  | No news
Docker containers | Fernando | Docker containers for core service deployment. | Presentation of docker containers for v3.0. Will update documentation and wiki.
Application services

## 170926
170926 status
Topic | Responsible | Status | Comments
Arrowhead Framework summer school assignment | Jerker | Presentations, Sept 29 9-12 and Oct 6 13-15, webex. | Recording of presentations will be made. If you have a webex account you will get a link to the recorded session.
Core services
ServiceRegistry v4.0 | Jerker | SysD ready | Comments are appreciated!
Authorisation v4.0 | Jens | SysD distributed. Public key infrastructure. Session control token e.g. X509. | Comment appriiacted. Document to be copied to WP1 and Arrowhead Framework wiki sites. Access problem sto be sorted out by Jerker and Csaba. Ensure that AAA is consistently addresses and differentiated from safety. Connection to block chain specifically for Accounting. Integration/differentiation from Smart service Contract.
Orchestration v4.0 | Csaba | SysD distributed. Orchestration store process is improved. Integration with QoS. Integration with financial aspects. | Comment appreciated. Financial aspect to be synchronised with SEB.
PlantDescription | Simon | Update of the existing SysD 3.0. Draft 4.0 SysD, SD, IDD, SP, CD. New experimental code uploaded. Push of data Orchestration is sketched. | Comment appreciated.
Configuration | Emanuel | SysD and SD document drafts in git repository. Used Node JS for prototyping. | Comment appreciated. Hasan has core system prototyped in Node JS.
SystemRegistry | Ani | SysD, SD, IDD document draft in git repository. REST IDD to be added. | Comment appreciated.
DeviceRegistry | Silia | SysD, SD, IDD document draft in git repository. REST IDD to be added. | Comment appreciated.
Historian | Jens | SysD and other documentation is cleaned up. Code cleaned up code base. Integration with the EventHandler is next step. | Jens i making further updated of documentation.
EventHandler | Michele | merge with Historian.
QoS | Michele | No news
Gatekeeper | Csaba | Cleaned up v3.2. 4.0 prerelease due in 2-3 weeks. | Adi to contribute to testing of 4.0 prerelease.
Translator | Hasan | No news
Core system integration coordination | Hasan | Telco on Translator, Historian and EventHandler | webex meeting Thursday Sept 28 13-14.30
Proposals for support core system
SafetyManager | Simon | Ideas presented. | Send requirements to Oystein. Safety system can be an security attach point.
Gateway service | Csaba | New system for secure inter cloud data path. Based on ANQP brockers. | SysD and other documents available in 2-3 weeks.
Self adapatabiliyt | Markus | No news
Smart Service Contract | Ulf | Requirements definitions in process. Possible new name is “asset broker”. | Draft requirements to be released in a few weeks. Implementation is expected to be using distributed ledger technology.
Engineering tool for legacy adapters | Mario
Docker containers | Fernando | Docker containers for core service deployment. | Please use and provide feedback for improvements. Detailed info to presented Friday 29/9.
Application services