## 200512
Table 1
Item | Responsíble | Comments
Ecplise process | Marco/Jerker | Project management team. Mentor to be done this week.
Demonstrations at ICPS in Tampere, | Peter/Ulf/Markus/… | Jiri: demo is ready. Demo for Arrowhead Tools is in preparation. Silia: Integration with TestTool. Meeting next week. Emanuel: Will be announced within 2 weeks.
Architecture and implementation updates | Jerker | First within hopefully 2 weeks.
Special session | Felix | IEEE IECON The 46th Annual Conference of the IEEE Industrial Electronics Society October 18-21, 2020 Marina Bay Sands, Singapore from Txema Felix MGEP to Everyone: 3:38 PM Deadline for submission of special session papers: May 17, 2020 May 26, 2020 from Txema Felix MGEP to Everyone: 3:40 PM Special Session on: "IoT Automation Technologies, Tools and Applications"
Released Core Systems
ServiceRegistry v4.1.3 | AITIA | No updates
- MQTT and CoAP interface | Jens/Pablo
- DNS-SD | Jens
Authorisation v4.1.3 | AITIA | No updates
Orchestration v4.1.3 | AITIA | No updates
Gatekeeper v4.1 | AITIA | No updates
Gateway v4.1 | AITIA | No updates
Management Tool | AITIA | No updates
EventHandler v4.1.3 | AITIA | Finally related today
Chorepgraphy system | AITIA | No updates
QoS v4.1 | AITIA | Finally related today
Documentation in GitHub | Jerker/Szvetlin | Update of documentation
Updates release candidates
DataManager | Jens/Jerker/Jonny | Some documentation is missing.
Translator | Pablo/Jerker/Jonny | Still to be reviewed by CI/CD process
FiWare interoperability | Pablo/Jerker/Jonny | Still to be reviewed by CI/CD process
CertificateAuthority | Gabor/Ani/Silia | Replicate interface under dev. Pull request planed for next week.
WorkFlowManager | Jaime | Ready for testing next week. Connected to the Fischer technique factory.
SystemRegistry | Ani | Ready for merging to the master branch. Comments on documentation from Jerker
DeviceRegistry | Silia | Ready for merging to the master branch. Comments on documentation from Jerker
Onboarding | Ani/Silia | Ready for merging to the master branch. Comments on documentation from Jerker
PLC integration IEC 61499 | Jose/Kirill | No updates
Open API formalisation | Michele | No updates
OPC-UA | Fortis/LTU | No updates
BaSyS interoperability | Markus | No updates
Test-tool | Hans | No updates
Sandboxing tool | Hans | No updates
Python Skeletons | Jacob | Hopefully ready for presentation 2 weeks.
Kalix lib | Emanuel | v0.3 is out bugg fixes.
C++ | Balint | Under development, release by end May!!
Updates to prototypes
ESB-CPN | Felix | Interface to core service 4.1.3. to BPMN is being updated.
PlantDescription | Olov/Johan | Updates rewetted to ServiceRegistry and Orchestration system by Appy. Integration to PD is still to be made.
Configuration | Javad | No update
Engineering tool for legacy adapters | Mario | No update
Datastructure Editor | Mario | No update
Device description editor | Mario | No update
Code generator | Mario | No update
Consumer code generation | Cristina | No update on code.
Exchange network/ContractProxy | Ulf/Emanuel | Delayed. Complicated problem. Too many variable to integrate.
SafetyManager | Mirren/Daniela | Safety Manager: Miren is working on a demo for Productive4.0. She will try to publish the findings and work there.
Autonomic orchestration/configuration | An | No update
Security mitigation tool | Silia | Implementation in progress
Security standard compliancy | Ani | Defined 3 possible use cases.
Translation - sermantics | Jacob | A paper accepted ICN conference. Plan for journal for SI of IEEE II.
ModbusTCP, | Ireneus | Unit tests to published with Modbus TCP.
SysML 2 | Oystein/Geza
SysML models/library/profile | Jerker/Geza | Working on an Arrowhead development suit.
Hono, Hawkbit, Ditto | Johannes/Sven | No major updates
Kura & Kapua | Paolo | No update
Updates on engineering tools
Engineering process | Jan/Gianvito | Working on a viewer for the process. Meeting Friday this week.
Engineering tool chain | Marek/Federico | No updates
Engineering tools | Hans/Pal | No updates
Updates on training
Training planing | Mathew/Mats
Training HW,SW, littérature | Mathew/Mats | Uploaded the first version of training catalog upload the Arrowhead Tools repo.
Applications
Semi conductor equipment integration | Francois + Mark, Agileo
Zinq based accelerator of local nodes. | Jiri
ROS | Jan
SysML application models
AoB

## 200414
Table 1
Item | Responsíble | Comments
Ecplise process | Marco/Jerker | Process Started
Demonstrations at ICPS in Tampere, | Peter/Ulf/Markus/… | Hans Management tool integration to Markus and Ulfs team.
Arrowhead Tools demos | Mats | Some 20 demos confirmed
Architecture and implementation updates | Jerker | New group to be started to look at architecture updates. rated to issues and suggestions being stated at GitHub and slack.
Solution engineering | Emanuell/Gabor
- Kalix Library | Emanuel | Presentation available at meeting folder. Clear connection to SysML and code generation
- evopro Arrowhead adopters | Balint | Presentation available at meeting folder. Library for integration of legacy systems and for high level configuration of SoS.
Released Core Systems
ServiceRegistry v4.1.3 | AITIA
- MQTT and CoAP interface | Jens/Pablo
- DNS-SD | Jens
Authorisation v4.1.3 | AITIA
Orchestration v4.1.3 | AITIA
Gatekeeper v4.1 | AITIA
Gateway v4.1 | AITIA
Management Tool | AITIA
EventHandler v4.1.3 | AITIA
Chorepgraphy system | AITIA | Almost ready for final testing.
QoS v4.1 | AITIA | Is going through final testing.
Documentation in GitHub | Jerker/Szvetlin | Updated documentation provided by Szvetlin, Jerker to review.
Updates release candidates
DataManager | Jens/Jerker/Jonny | Code review, 2-3 minor issues found. Will be ready for release in 1-2 weeks
Translator | Pablo/Jerker/Jonny | Soon to go to review to Szvetlin
FiWare interoperability | Pablo/Jerker/Jonny
CertificateAuthority | Gabor/Ani/Silia | Krustof is waiting for pull request by Szvetlin.
WorkFlowManager | Jaime | Demo in Productive4.0. Meeting with Jan and Fischer technique demo. Interaction with Contract Proxy is planed.
SystemRegistry | Ani | In review process by Szvetlin, Release time line end April.
DeviceRegistry | Silia | In review process by Szvetlin, Release time line end April.
Onboarding | Ani/Silia | In review process by Szvetlin, Release time line end April.
PLC integration IEC 61499 | Jose/Kirill | No updates
Open API formalisation | Michele | Meeting on Thursday with Geza Thursday April 16.
OPC-UA | Fortis/LTU | No updates
BaSyS interoperability | Markus | No updates
Test-tool | Hans | Test tool focus. Internal demonstration today. Design review on the GUI on Thursday.
Sandboxing tool | Hans
Python Skeletons | Jacob | Code on GitHub. Updates in early May. Presnrtion in May meeting.
Updates to prototypes
ESB-CPN | Felix | Prototype is ready. Integration to Productive demos is being analysed.
PlantDescription | Olov/Johan | Working prototype by June. Alignement with core system functionality and development.
Configuration | Javad | No updates
Engineering tool for legacy adapters | Mario
Datastructure Editor | Mario
Device description editor | Mario
Code generator | Mario
Consumer code generation | Cristina | Code germination system as a first draft by end of April. Planing for introduction of the security part.
Exchange network/ContractProxy | Ulf/Emanuel | Prototype ready by next week.
SafetyManager | Mirren/Daniela | No updates. Working on safety scenarions
Autonomic orchestration/configuration | An | Meeting with Jan to integrate the Fischer technique plant to see how semantic policy can be used to describe the workflow. Work with Jamie already opened.
Security mitigation tool | Silia | Review of prototype tailored for WP8 use case.
Security standard compliancy | Ani | Prototype working. Arrowhead adaptation. Paper accepted in Int. journal of Sensors.
Translation - sermantics | Jacob | Meeting with An and Jan.
ModbusTCP, | Ireneus | No updates
SysML 2 | Oystein/Geza
SysML models/library/profile | Jerker/Geza | Demo i MIlan meeting. Simple exporter and documentation. SysML working group
Hono, Hawkbit, Ditto | Johannes/Sven | Prototypes working at Bosch.
Kura & Kapua | Paolo | No updates
Updates on engineering tools
Engineering process | Jan/Gianvito | No updates
Engineering tool chain | Marek/Federico | No updates
Engineering tools | Hans/Pal | Determining Tool demos for Milan meeting
Updates on training
Training planing | Mathew/Mats | No updates
Training HW,SW, littérature | Mathew/Mats | No updates
Applications
Semi conductor equipment integration | Francois + Mark, Agileo | No updates
Zinq based accelerator of local nodes. | Jiri | Trying to abstract the HW such that SW can be easily debugged. Connected to Xylinc open source tools chain. Work with Arcelik on data acquisition an oscoliscope.
ROS | Jan | On ice
SysML application models
AoB

## 200331
Table 1
Ecplise process | Marco/Jerker | Proposal submitted today.
Demonstrations at ICPS in Tampere, | Peter/Ulf/Markus/… | Peter C: Successful integration made last week. Integration between OPC-UA PLC and Modbus PLC successful. Silia: On-boarding demo fully functional. Integration with Ulf, telco next week. Similar work on-going with Hans. Ulf: Use of ContractProxy together with several other systems in a production setting. Hans: Good integration between legacy integration, test tool and consumer code generation. Will involve the ContractProxy system. Jiri: Integrating with Turkey partners. Zinq device integrated with Arrowhead Framework.
Arrowhead Tools demos | Mats | Request for input to the Milan meeting. Please respond to Mats regarding demo description.
Solution engineering | Emanuell/Gabor | Simplifying a programmers work using Arrowhead Framework platform. 15+15 minutes for next bi-weekly.
Released Core Systems
ServiceRegistry v4.1.3 | AITIA
- MQTT and CoAP interface | Jens/Pablo | First release checking is made waiting ofr filan updates.
- DNS-SD | Jens
Authorisation v4.1.3 | AITIA
Orchestration v4.1.3 | AITIA
Gatekeeper v4.1 | AITIA
Gateway v4.1 | AITIA
Management Tool | AITIA
EventHandler v4.1.3 | AITIA
Chorepgraphy system | AITIA | Final update before release, video made at the Eisenstadt meeting.
QoS v4.1 | AITIA | Final update before release
Documentation in GitHub | Jerker/Szvetlin | Jerker to check updates from Szvetlin
Updates release candidates
DataManager | Jens/Jerker/Jonny
Translator | Pablo/Jerker/Jonny | Documentation is missing
FiWare interoperability | Pablo/Jerker/Jonny | Documentation is missing
CertificateAuthority | Gabor/Ani/Silia | Bug fixing. Develop certificate management service in progress. Time line second half of April.
WorkFlowManager | Jaime | Integration with Fischer teknik plant. Time line for release is end of.
ESB-CPN | Felix | Move to prototype
SystemRegistry | Ani | No update, ready to move to release procedure.
DeviceRegistry | Silia | No update, ready to move to release procedure.
Onboarding | Ani/Silia | No update, ready to move to release procedure.
PLC integration IEC 61499 | Jose/Kirill | Working on demo. Paper to Tampere + video on the demo. Demo at EclipseCon.
Open API formalisation | Michele
OPC-UA | Fortis/LTU | No update
BaSyS interoperability | Markus | No update
Test-tool | Hans | Interface integration with the back end. Time line for demo and presentation in May.
Sandboxing tool | Hans | No update
Python Skeletons | Jacob | Move to release with Szvetlin within early May.
Kalix and c++ library, | Gabor and Emanuell
Updates to prototypes
ESB-CPN | Felix
PlantDescription | Olov/Johan | Progressing: first version will come as local. Data to come from SysML model.
Configuration | Javad | A white paper regarding requirement configuration, from Ghofrani to Everyone: 4:25 PM https://arxiv.org/pdf/2003.13618.pdf .
Engineering tool for legacy adapters | Mario | Cristina to get more detailed input from mario.
Datastructure Editor | Mario | Cristina to get more detailed input from mario.
Device description editor | Mario | Cristina to get more detailed input from mario.
Code generator | Mario | Cristina to get more detailed input from mario.
Consumer code generation | Cristina | Use info from demo. Code update. Debugging in progress. Reasonably robust. Performance data in progress. Interaction with Gabor and his team on C++ library.
Exchange network/ContractProxy | Ulf/Emanuel | No update. Time plan April 17. On-line demo 22/4.
SafetyManager | Mirren/Daniela | No update
Autonomic orchestration/configuration | An | Meeting tomorrow regarding integration with semantic stranslation and the Fishcer technic plant at LTU (Jan & Aparajita)
Security mitigation tool | Silia | First prototype is ready. Documentation in the works. Working on generic support
Security standard compliancy | Ani | Integration to the information building technology. Paper accepted.
Translation - sermantics | Jacob | Submitted paper to INES yesterday. Early test results.
ModbusTCP, | Ireneus | No update
SysML 2 | Oystein/Geza | Presentation by Oystein at OMG meeting last week. Very essential detail of SysML2 language is stil lunder heavy discussion.
SysML models/library/profile | Jerker/Geza | SysML 1.6 profile and library to be releases during spring.
Hono, Hawkbit, Ditto | Johannes/Sven | Started integration of Ditto. Adjustments of Ditto to work with Arrowhead Authorisation system. All three systems working. Will be tested in an Arrowhead Tools meeting.
Kura & Kapua | Paolo | No update
Updates on engineering tools
Engineering process | Jan/Gianvito | No update
Engineering tool chain | Marek/Federico | No update
Engineering tools | Hans/Pal | Looking for demos to the Milan meeting
Updates on training
Training planing | Emanuell/Mats | Telco this Thursday. Feedback on training requirements. Content for drafting the coming 6 months work.
Training HW,SW, littérature | Emanuell/Mats | Wiki for installation and execution of Arrowhead Framework. In German for today.
Applications
Semi conductor equipment integration | Francois + Mark, Agileo
Zinq based accelerator of local nodes. | Jiri
ROS | Jan | On ice.
SysML application models
AoB

## 200317 - Table 1-1
Table 1-1
Table 1
Ecplise process | Marco/Jerker | Submission this week
Demonstrations at ICPS in Tampere, | Peter/Ulf/Markus/… | Work in progress, cooperation with several use cases. C-coded clients in secure mode. VPN connection might be an issue with PLC involved. SensML semantics service exchanges is working. Working on a manufacturing story.
Solution engineering | Emanuell/Gabor
Released Core Systems
ServiceRegistry v4.1.3 | AITIA | No update
- MQTT and CoAP interface | Jens/Pablo | No update
- DNS-SD | Jens | No update
Authorisation v4.1.3 | AITIA | No update
Orchestration v4.1.3 | AITIA | No update
Gatekeeper v4.1 | AITIA | No update
Gateway v4.1 | AITIA | No update
Management Tool | AITIA | No update
EventHandler v4.1.3 | AITIA | No update
QoS v4.1 | AITIA | Updates on going unit and integration test ongoing.
Documentation in GitHub | Jerker/Szvetlin | No update
Updates release candidates
DataManager | Jens/Jerker/Jonny | No update
Translator | Pablo/Jerker/Jonny | No update
FiWare interoperability | Pablo/Jerker/Jonny | No update
CertificateAuthority | Gabor/Ani/Silia | Still waiting for final push to Svetlin
WorkFlowManager | Jaime | Refactor from scratch
ESB-CPN | Felix | No updates to be moved to prototypes
Choreography | Pal | No updates
SystemRegistry | Ani | Documentation in progress
DeviceRegistry | Silia | Documentation in progress
Onboarding | Ani/Silia | Documentation in progress
PLC integration IEC 61499 | Jose/Kirill | Integration to demo. Connecting with TWT mode bus
Open API formalisation | Michele | Open API interaction with corer systems. Connect to Geza and SysML modelling.
OPC-UA | Fortis/LTU | No update. Cooperation with UzL and Infineon in progress.
BaSyS interoperability | Markus | No updates
Test-tool | Hans | No updates
Sandboxing tool | Hans | No updates
Python Skeletons | Jacob | No updates
Updates to prototypes
PlantDescription | Olov/Johan | No updates
Configuration | Javad | No update
Engineering tool for legacy adapters | Mario | No updates
Datastructure Editor | Mario | No updates
Device description editor | Mario | No updates
Code generator | Mario | No updates
Consumer code generation | Cristina | Integration with the test tool. Mario contact with no success. Performance testing in progress.
Exchange network | Ulf/Emanuel | Focus on the Eisenstadt meeting. ForecastEngine in focus.
SafetyManager | Mirren/Daniela | No update.
Autonomic orchestration/configuration | An | No update.
Security mitigation tool | Silia | Code development + paper
Security standard compliancy | Ani | Addressing some buggs
Translation - sermantics | Jacob | Connection to Infineon/VIF and large data sets for training purposes
ModbusTCP, | Ireneus | Confident with Modbus TCP adapter. Try to publish this to githut.
SysML 2 | Oystein/Geza | OMG meeting next week. A SysML library will be presented next week.
SysML models/library/profile | Jerker/Geza | Providing a publishable profil in progress. Soon to be released at best next week. Code generation in progress. Export of models into the Management Tools. Update on this att the Milan meeting. Open API will tested later.
Hono and Hawkbit | Johannes/Sven | No updates
Kura & Kapua | Paolo | No updates
Updates on engineering tools
Engineering process | Jan/Gianvito | No update.
Engineering tool chain | Marek/Federico | No update.
Engineering tools | Hans/Pal | Report on Arrowhead Tools D5.2
Updates on training
Training planing | Emanuell/Mats | Up and running.
Training HW,SW, littérature | Emanuell/Mats | On öine meetings and training with WP9, Wp8 and WP7
Applications
Semi conductor equipment integration | Francois + Mark, Agileo | No update
Zinq based accelerator of local nodes. | Jiri | No progress
ROS | Jan | This on ice
SysML application models |  | Several SysML models for WP9 use cases are in progress.
AoB

## 200303 - Table 1-1
Table 1-1
Table 1
Ecplise process | Marco/Jerker | Moving with some smaller hick ups
Demonstrations at ICPS in Tampere, | Peter/Ulf/… | Weekly calls between groups.
Released Core Systems
ServiceRegistry v4.1.3 | AITIA | No updates
- MQTT and CoAP interface | Jens/Pablo | Presentation by Jens in 2 weeks time. Architecture for the implementation is gartered between Szvetlin, Pal, Pablo, jens and Jerker
- DNS-SD | Jens | Initial investigation being made. Implementation strategy/architecture as above.
Authorisation v4.1.3 | AITIA | No updates
Orchestration v4.1.3 | AITIA | No updates
Gatekeeper v4.1 | AITIA | No updates
Gateway v4.1 | AITIA | No updates
Management Tool | AITIA | No updates
EventHandler v4.1.3 | AITIA | No updates
QoS v4.1 | AITIA | In progress
Documentation in GitHub | Jerker/Szvetlin | Plan to update ServiceRegistry doc as a pilot to be confirm with Arrowhead Framework documentation structure.
Updates release candidates
DataManager | Jens/Jerker/Jonny | Releases held due to security documentation ambiguities. Plan toghather with Szvetlin to resolve this.
Translator | Pablo/Jerker/Jonny | Releases held due to security documentation ambiguities. Plan toghather with Szvetlin to resolve this.
FiWare interoperability | Pablo/Jerker/Jonny | Depends on DatanManager and Translator.
CertificateAuthority | Gabor/Ani/Silia | Available for testing. Still no documentation.
WorkFlowManager | Jaime | No updates
ESB-CPN | Felix | Accepted in journal, minor revision.
Choreography | Pal | Second version almost ready. Will be ready for Eisenstadt.
SystemRegistry | Ani | First review from Szvetlin. Doc to be committed today
DeviceRegistry | Silia | First review from Szvetlin. Doc to be committed today
Onboarding | Ani/Silia | Demo scenario in the preparation. Journal paper in preparation. Waiting for CertificateAuthority.
PLC integration IEC 61499 | Jose/Kirill | Trying with legacy support. Pull request to the GitHub, Internal demo work.
Open API formalisation | Michele | No updates
OPC-UA | Fortis/LTU | Still pending call fro telco for the group. OPC-UA - Arrowhead integration in operation. A wrapper solution
BaSyS interoperability | Markus | No updates
Test-tool | Hans | Work on-going. Work with Cristina and Mario for the demo in Tampere. Things can be tested in Tampere.
Sandboxing tool | Hans | Test with 4.1.3. A few thing are working. Will possibly not be ready for Eisenstadt.
Python Skeletons | Jacob | Working Pyton library. Link https://github.com/ajoino/python-arrowhead. EPL 2 license. Introduced to the CI/CD process. Will be completed by Szvetlin.
Updates to prototypes
PlantDescription | Olov/Johan | Meeting this morning. Multi vendor use case based on a factory scenario. Eisenstadt presentation of architecture but no working code. Working code in June.
Configuration | Javad | No updates
Engineering tool for legacy adapters | Mario | No updates
Datastructure Editor | Mario | No updates
Device description editor | Mario | No updates
Code generator | Mario | No updates
Consumer code generation | Cristina | No updates
Exchange network | Ulf/Emanuel | Work ongoing on prototype. Plan to have something in Eisenstadt. Plan for talk on a client library for ExchangeNetwork. Will be open to anyone interested. Possibly in EISENSTADT
SafetyManager | Mirren/Daniela | No updates
Autonomic orchestration/configuration | An | Integration of to the TWT modbus. Evaluating integration to the Peter Cramer demo.
Security mitigation tool | Silia | Prototype integrated with AVL use case.
Security standard compliancy | Ani | Meeting with AIT integrating it to the building use case. Meeting last week in eisenstadt.
Translation - sermantics | Jacob | Work on-going.
ModbusTCP, | Ireneus | No updates
SysML | Jerker/Geza | Two track project. 1) Profile SysML 1.6, 2) Profile SysML-2. https://atmospheres.research.ltu.se/owncloud/index.php/apps/files/?dir=/Arrowhead_Tools/WP3%20Arrowhead%20Framework/Task%203.1/Work/SysML_Arrowhead_profile/Profile&fileid=1577190
Hono and Hawkbit | Johannes/Sven | Presentation by Sven on Hono last week. Adaptor for both Hono and Hawkbit. Enabling both to be used with in an Arrowhead local cloud. Demo in MIlan
Kura & Kapua | Paolo | No updates
Updates on engineering tools
Engineering process | Jan/Gianvito | Updating the survey. Follow up in progress.
Engineering tool chain | Marek/Federico | No updates
Engineering tools | Hans/Pal | D5.2 finished. A lot of input from partners. Possible to follow tool development progress. Presentation next meeting.
Updates on training
Training planing | Emanuell/Mats | Standin for Emmanuel. Mats action for an update til next meeting
Training HW,SW, littérature | Emanuell/Mats
Applications
Semi conductor equipment integration | Francois + Mark, Agileo | No updates
Zinq based accelerator of local nodes. | Jiri | No updates
ROS | Jan | No updates
AoB

## 200218
Table 1
Table 1
Ecplise process | Marco/Jerker | Process ongoing.
Demonstrations at ICPS in Tampere, | Peter/Ulf/… | LTU, SEB, Volvo, Mondragon, AITIA, BME, Peter Cramer, DataManager, TWT, Modbus, Norway, Fortis, OPC-UA,
Released Core Systems
ServiceRegistry v4.1.3 | AITIA
Authorisation v4.1.3 | AITIA
Orchestration v4.1.3 | AITIA
Gatekeeper v4.1 | AITIA
Gateway v4.1 | AITIA
Management Tool | AITIA
EventHandler v4.1.3 | AITIA | Will by mid March
QoS v4.1 | AITIA | Will by mid March, paper from Luis and Haris
Documentation in GitHub | Jerker/Szvetlin | Work in progress in connection with SysML work
Updates release candidates
DataManager | Jens/Jerker/Jonny | Most issues are fixed. Still some documentation is pending.
Translator | Jens/Jerker/Jonny | No update
FiWare interoperability | Jens/Jerker/Jonny | No update
CertificateAuthority | Gabor/Ani/Silia | Not pushed for release yet.
WorkFlowManager | Jaime | No update.
ESB-CPN | Felix
Choreography | Pal
SystemRegistry | Ani | Revived for release
DeviceRegistry | Silia | Revived for release
Onboarding | Ani/Silia | Revived for release
PLC integration IEC 61499 | Jose/Kirill | Paper for ICPS, to be included in demo
Client library proposal | Szvetlin | Seams to be working fine
Open API formalisation | Michele | Module developed in C code in no-secure mod.
OPC-UA | Fortis/LTU
BaSyS interoperability | Markus | No update
Test-tool | Hans | No update
Sandboxing tool | Hans | No update
Python Skeletons | Jacob | Working code in secure mode, ready fro release,
Updates ion installation |  | To be closed for next meeting.
Linux installation | Szvetlin/Javad
Windows instalaltion | Szvetlin
Mac installation | Szvetlin
Docker + Jenkins | Haris
Updates to prototypes
PlantDescription | Olov/Johan | Weekly meetings every Tuesday. Will revolve around Fischer tech use case.
Configuration | Javad | Telco on architecture last week.
Engineering tool for legacy adapters | Mario | No update
Datastructure Editor | Mario | No update
Device description editor | Mario | No update
Code generator | Mario | No update
Consumer code generation | Cristina | Meeting with BnearIT one the demo. To generate the a dummy consumer for the ExchangeNetwork to be tested in the TestTool. More advance payload description and encoding.
Exchange network | Ulf/Emanuel | No update. Working code will be around in Eisenstadt
SafetyManager | Mirren/Daniela | No update
Autonomic orchestration/configuration | An | First prototype is in migration to 4.1.3 secure mode. Integration to Modbus TCP in progress.
Security mitigation tool | Silia | Will be used in use case with AVL.
Security standard compliancy | Ani | Journal paper in progress together with on-boarding
Translation - sermantics | Jacob | We've done more experiments related to the results shown during my licenciate thesis. Had a meeting yesterday with Jerker, Fredrik Sandin, and Marcus Liwicki about how to progress
ModbusTCP, | Ireneus | No update
SysML | Jerker/Geza | 2 day WS in Budapest.
Hono and Hawkbit | Johannes/Sven | Slide presentation.
Kura & Kapua | Paolo
Updates on engineering tools
Engineering process | Jan/Gianvito | No update
Engineering tool chain | Marek/Federico | No update
Engineering tools | Hans/Pal | No update
Updates on training
Training planing | Emanuell/Mats | No update
Training HW,SW, littérature | Emanuell/Mats | No update
Applications
Semi conductor equipment integration | Francois + Mark, Agileo | No update
Smart parking application | Haris | Coming to an end. Services for parking is ready, Demo and video i Tampere
Vertical farming | Haris | Closed
Zinq based accelerator of local nodes. | Jiri | Demo on 60 x acceleration of video processing. Working with Szvetlin to provide integration for Arrowhead service integration.
ROS | Jan | No update
AoB

## 200121
Table 1
Ecplise process | Marco/Jerker | Eclipse process start this or next week.
Demonstrations at ICPS in Tampere, | Peter/Ulf/… | Larger discussion next meeting
Released Core Systems
ServiceRegistry v4.1 | AITIA
Authorisation v4.1 | AITIA
Orchestration v4.1 | AITIA
Gatekeeper v4.1 | AITIA
Gateway v4.1 | AITIA
Management Tool | AITIA
EventHandler v4.1 | AITIA
QoS v4.1 | AITIA
Updates release candidates
DataManager | Jens/Jerker/Jonny | IN CI/CD process for release
Translator | Jens/Jerker/Jonny | Release plan end of February
FiWare interoperability | Jens/Jerker/Jonny | Release plan end of February
CertificateAuthority | Gabor/Ani/Silia | No update
WorkFlowManager | Jaime | No update
ESB-CPN | Felix | Decision on release plan needed.
Choreography | Pal | By end of Feb a demo will be available. Yellow duckytown demo.
SystemRegistry | Ani | Upgrading to Java spring. Send to CI/CD process in Jan
DeviceRegistry | Silia | Upgrading to Java spring. Send to CI/CD process in Jan
Onboarding | Ani/Silia | Upgrading to Java spring. Send to CI/CD process in Jan
PLC integration IEC 61499 | Jose/Kirill | Paper in process. Integrating 61499 and OPC-UA. Jose to set up telco for the release process.
Client library proposal | Michele | No update
OPC-UA | Fortis/LTU | Need to be revisited to get i released. JD responsible.
BaSyS interoperability | Markus | No updates
Test-tool | Hans | New graphical interface i developed. Making it web based.
Sandboxing tool | Hans | Test this week with v4.1.3. More internal info coming Friday.
Python Skeletons | Jacob | Producing services is working. Consumer skeleton in the works.
Updates ion installation
Linux installation | Szvetlin/Javad | A server damage happened during Christmas. It should be up again this week.
Windows instalaltion | Szvetlin | A server damage happened during Christmas. It should be up again this week.
Mac installation | Szvetlin | A server damage happened during Christmas. It should be up again this week.
Docker + Jenkins | Haris | A server damage happened during Christmas. It should be up again this week.
Updates to prototypes
PlantDescription | Jerker | Meeting in Oslo with some 12 people.
Configuration | Javad | First architecture presented. Recommendation to review Eclipse projects Kura and Kapua.
Engineering tool for legacy adapters | Mario | No update
Datastructure Editor | Mario | No update
Device description editor | Mario | No update
Code generator | Mario | No update
Consumer code generation | Cristina | Journal paper on service interface coding system. Looking into CDL specificaitons.
Exchange network | Ulf/Emanuel | No update
SafetyManager | Mirren/Daniela | No update
Autonomic orchestration/configuration | An | No update
Security mitigation tool | Silia | Under development, no major update. Feb/March first prototype
Security standard compliancy | Ani | Under development, no major update, prototype code is working.
Translation - sermantics | Jacob | Improving the auto encoder architecture.
ModbusTCP, | Ireneus | No update
SysML | Jerker | Progress on Arrowhead Framework SysML profile. A validation phase for SysML2 is expected.
Updates on engineering tools
Engineering process | Jan/Gianvito | No update
Engineering tool chain | Marek/Federico | No update
Engineering tools | Hans/Pal | D5.2 from Arrowhead Tools in progress. Ready by end o next week.
Updates on training
Training planing | Emanuell/Mats | Promotion training activities pushed within the Arrowhead Tools project. Large workshop in Milan end of April. Collection of training material is in progress. FAQ area is discussed.
Training HW,SW, littérature | Emanuell/Mats
Applications
Semi conductor equipment integration | Francois + Mark, Agileo | No update
Smart parking application | Haris | No update
Vertical farming | Haris | No update
Zinq based accelerator of local nodes. | Jiri | Connected to Turkish use case in Arrowhead Tools. First prototype installation is made. Looking into how to abstract HW. Provide mechanisms to HW acceleration of software functionalities having Arrowhead services.
Music on the new web. | Erkki | No update
ROS | Jan | No update
Thingwave | Jens
AoB | Pal | Integration of other Eclipse tool with Arrowhead.

## 200107
Table 1
Table 1
Ecplise process | Marco/Jerker | Telco with Eclipse either this or next Thursday
Migration 4.1.2 -> 4.1.3, | Szvetlin | Migration: 4.1.2 and 4.1.3 compatibilty via legacy support library: https://github.com/arrowhead-f/core-java-spring-legacy-support
Released Core Systems
ServiceRegistry v4.1 | AITIA
Authorisation v4.1 | AITIA
Orchestration v4.1 | AITIA
Gatekeeper v4.1 | AITIA
Gateway v4.1 | AITIA
Management Tool | AITIA
EventHandler v4.1 | AITIA | Core System Updates: Event Handler: improvements to startup time and subsciber authorization, and documentation is ready. Other systems no update, our focus was on the legacy support.
QoS v4.1 | Luis+AITIA | No update
Documentation in Github | Jerker | A small working group to be formed with core people from the documentation paper lead by Michele.
Updates release candidates
DataManager | Jens/Jerker/Jonny | Code is on-line in Github, will work with Szvetlin to get it released.
Translator | Jens/Jerker/Jonny | Pablo is working Translator 4.1.3. Plan for release in 2-3 weeks.
FiWare interoperability | Jens/Jerker/Jonny | Pablo is working FiWare use case into v4.1.3. Plan for release in 2-3 weeks.
CertificateAuthority | Gabor/Ani/Silia | No update
WorkFlowManager | Jaime | No update
ESB-CPN | Felix | No update
Choreography | Pal | Has been demoed. New version for the ICPS demo.
SystemRegistry | Ani | Updating to java-spring. Plan to release end of this month. Work on a journal paper for the on-boarding procedure
DeviceRegistry | Silia | “
Onboarding | Ani/Silia | “
PLC integration IEC 61499 | Jose/Kirill | Plan to publish at ICPS. Will be released as both 4DIAC and Arrowhead. OPC-UA 4.1.2 implemented. Kiril to get in contact with Szvetlin
Client library proposal | Michele | No update
OPC-UA | Niklas | No update
BaSyS interoperability | Markus | No update
Test-tool | Hans | No update on Sandboxing tool but will be updated to 4.1.3 in January Working on new web based interface for test tool, will be released in March.
Sandboxing tool | Hans | -“-
Python Skeletons | Jacob | No update
Updates ion installation
Linux installation | Szvetlin/Javad | Windows guide is coming soon.Debian installers are ready (for Linux/Raspberry Pi) common problem during installation: people don't read the guide carefully
Windows instalaltion | Szvetlin
Mac installation | Szvetlin
Docker + Jenkins | Haris
Updates to prototypes
PlantDescription | Jerker | Meeting in Oslo 29-30/1.
Configuration | Javad | No update
Engineering tool for legacy adapters | Mario | No update
Datastructure Editor | Mario | No update
Device description editor | Mario | No update
Code generator | Mario | No update
Consumer code generation | Cristina | No update
Exchange network | Ulf/Emanuel | Work on a UserRegistry system
SafetyManager | Mirren/Daniela | No updates
Autonomic orchestration/configuration | An | No updates
Security mitigation tool | Silia | Implementing in the AVL use case.
Security standard compliancy | Ani | Journal paper in the works
Translation - sermantics | Jacob | No update
ModbusTCP, | Ireneus | No update
SysML | Jerker | Telco on SysML2 validation work. Model available in AHT owncloud. The modelling approach will also be discussed in Oslo.
Updates on engineering tools
Engineering process | Jan/Gianvito | Paper for IEEE NOMS WS in Budapest
Engineering tool chain | Marek/Federico
Engineering tools | Hans/Pal | Deliverable 5.2. Will make use of WP2 and 4 data to form the appropriate tools and the associated tool chain integration. D5.3 is coming i April.
Updates on training
Training planing | Emanuell/Mats | No update
Training HW,SW, littérature | Emanuell/Mats | No update
Applications
Semi conductor equipment integration | Francois + Mark, Agileo | No update
Smart parking application | Haris | No update
Vertical farming | Haris | No update
Zinq based accelerator of local nodes. | Jiri | No update
Music on the new web. | Erkki | No update
ROS | Jan | Not tested on devices, yet. A ROS wheel loader is currently functional.
Thingwave | Jens | Arrowhead 4.1.3. in Thingwave products.
Integrated demo eat ICPS in Tampere | Peter | First version description is written. Connection to the other demo groups is requested. All demo group in the agenda for next telco.
AoB