## Tabelle1
Issue Owner | Mail | Company | Subject | Description | Proposed Solution
Paul Patolla | paul.patolla@htw-dresden.de | HTW Dresden | Missing project-wide Arrowhead community | Currently each WP working on their own strategy how to integrate or implement solutions into arrowhead. The biggest problem here is that the WPs are encapsulated from each other. | 1) community wiki (e.g. mediawiki) to share information between members and public. So we can decrease the pressure for trainigs from the developers. This means that every member can create pages or edit other pages. 2) a repository/project for community demonstrators because the current examples in the repositories are too high level or misleading. Another advantage is that the community itself maintain their own demonstrators.
Paul Patolla | paul.patolla@htw-dresden.de | HTW Dresden | Missing core-client-skeleton library | To build the repository "client-library-java-spring" you need the library core-client-skeleton which has no repository and there is no description how to build this library | create a repository for this library
Paul Patolla | paul.patolla@htw-dresden.de | HTW Dresden | make use of wiki module for repositories | The problem is especially with the arrowhead core repository. The readme is much too long. Information can be found only with difficulty, since one simply does not see, when necessary passages begin and end. | Use the wiki tab for deeper explainations and use the Readme for short explainations like how to build/contribute and usage.
Thomas Wagner (Jonathan Seitz) | thomas.wagner2@tu-dresden.de | TU Dresden | Missing a simple tutorial ("Hello World") for a better Access into the AH FW development | Existing examples are too complex, simple examples just using, e.g., 1 provider, 1 consumer (1 side button press, one side event) would be of much more help | For example, IoTivity provides such examples. Some examples of variing difficulty would be appreciated, e.g., one with orchestrator usage, one without
Thomas Wagner (Jonathan Seitz) | thomas.wagner2@tu-dresden.de | TU Dresden | Constants within the code (e.g., IP's of core services) in one central place, not in every single module | Constants within the code (e.g., IP's of core services) have to be used in every single module. Which increases complexity, overhead and are error prone (must not forget to change e.g. IPs of core service in each module ) | There exists a workaround of Paul Patolla (HTW), could be already in place within the code base or could be added?
Thomas Wagner (Jonathan Seitz) | thomas.wagner2@tu-dresden.de | TU Dresden | Time synchronisation service | Time synchronisation of different devices is very beneficial, especially if several time based data (e.g., time series of measurement and cont) | Provide a time Service provider as a default (core?) service, where other services could synchronize with
Johannes Kristan | Johannes.Kristan@bosch.io | Bosch.IO | Decrease size of repository | The repository seems to contain old binary files in its git history, which results in a repository size of over 1 GB. This leads to a long waiting time when cloning it. | Large binary files could be removed from the git history.
Johannes Kristan | Johannes.Kristan@bosch.io | Bosch.IO | Add License File to the repository | The repository has no License file included. | Include a license file into the repository (EPL)
Johannes Kristan | Johannes.Kristan@bosch.io | Bosch.IO | main pom.xml references Apache License | In the main pom.xml file, there is still a reference to the Apache License | Change the license reference to EPL 2.0
Johannes Kristan | Johannes.Kristan@bosch.io | Bosch.IO | Master branch is ahead of the development branch | As of 15.02.21 The master branch is ahead of the development branch by 10 commits | merge the master branch into the development branch
Johannes Kristan | Johannes.Kristan@bosch.io | Bosch.IO | The README in the development branch still says v4.1.3 | The README file in the development branch still refers to version 4.1.3 | merge the master branch into the development branch
Johannes Kristan | Johannes.Kristan@bosch.io | Bosch.IO | Make build server accessible | Unfortunately, we are not aware of the build infrastructure yet and it is not linked in the GitHub page. While evaluating a project, developers often also want to check the current build status. Moreover, when running into issues with a local build, accessing the build service makes it easier to exclude issues with the upstream code. | It would be nice to be able to at least see the outcomes of the build processes, e.g. by applying a batch in GitHub to the README. We could make use of GitHub actions, which offers CI/CD completely free to public repositories.
Johannes Kristan | Johannes.Kristan@bosch.io | Bosch.IO | Kubernetes Deployment | There is no Kubernetes deployment description as part of the repository | It would be nice to be able to deploy the Arrowhead core systems to a Kubernetes cluster (e.g. by creating a Helm chart)
Johannes Kristan | Johannes.Kristan@bosch.io | Bosch.IO | Service generation implies System generation | When a new systems registers one of it's services at the service registry, a new system entry is generated implicitly as well. However, a system cannot register itself directly through the respecitve API, as this API-endpoint is reserved for the admins of the local cloud (sysop certificate). Please tell us, in case we misunderstood the undelying concept. | It would be nice to let a system register itself without the need to register one of ist services. For instance, if a system does not provide any services, it still could be a service consumer and therefore might need to rely on orchestration rules, which can only be created if a consuming system exists in the registry.