## 220111
Table 1
Table 1
Enhanced QoS | Daniel
Management tool chain | Tamas/Rajmond/ Pal
v4.6.0 release | Tamas
Roadmap WG v5.0
The new release process | Pal
v5.0 black box SoSD, SysD, SD | Pär O
Documentation wiki updates | Szvetlin
Adapters | Mats
Updates on core systems
GO version of mandatory core system Jens/Pablo/JanvD | Jerker/Geza
WorkFlowManager | Jaime
ESB-CPN, NodeRed | Felix
Device hub | Johannes/Sven
Hono | Johannes/Sven
Autonomic re-orchestration | Hua
Power of attorny | Sree
NGAC - data sharing | Alex/Ulf
QoS | Daniel
C++ v4.5 | Szvetlin/Pal
Updates on adaptors and translators
Translation - sermantics | Jacob/Pedro/Rogerio
OPC-UA adaptor | Aparajita
Z-wave adaptor | Salman
Modbus TCP. adaptor | Salman
ISO 10303 adaptor skeleton. | Kjell
Simulator (FMI) adaptor | Jan vD
Command line tool adaptor OSLC | Jan Feidor
C++ v4.2 | Szvetlin/Pal
GO version of mandatory core system | Jens/Pablo/JanvD
Code generation from SysML | Geza/Saadia/Cristina
Consumer code generation | Cristina
WorkFlowManager | Jaime
Contract Proxy | Ulf/Emanuel
Autonomic re-orchestration | Hua
ESB-CPN, NodeRed | Felix
Translation - sermantics | Jacob/Pedro/Rogerio
SysML 2 | Oystein/Geza
Kura & Kapua | Paolo
User authentication | Tomas/Jan
OPC-UA adaptor | Aparajita
Z-wave adaptor | Salman
Modbus TCP. adaptor | Salman
Thing of web adaptors | Federico/Szvetlin
ISO 10303 adaptor skeleton. | Kjell
Simulator (FMI) adaptor | Jan vD
Test-tool | Hans
Sandboxing tool | Hans
Command line tool adaptor OSLC | Jan Feidor
Power of attorny | Sree
NGAC - data sharing | Alex/Ulf
QoS | Daniel
C# and .net libraries | Jerker
Updates on engineering tools
SysML 1.6 profile & core system models | Jerker/Cristina/Saadia/Fawda
Code generation from SysML | Geza/Saadia/Cristina
Engineering process | Gianvito/Jan
Engineering tools | Hans/Pal
Web based SysML tool | Geza
SysMD tool | Christoph Grimm
Updates on training
Training tool, | Sebastian/Marcello/Saadia
Next meeting |  | Oct 25 at 15.30
Next feature presentation:

## 220913
Table 1
New projects supporting Eclipse Arrowhead | All
v4.5.0 release | Szvetlin
GO implementation of core systems | Jens
Roadmap WG v5.0
v5.0 black box SoSD, SysD, SD | Pär O | Per: SysD's created, and new SD's are coming; GitHub issues to solve
Documentation wiki updates | Szvetlin
Basic documentation | Mats | QUESTION to Mats: Do we have the Adaptor listings? - where exactly ? :)
Adapters | Mats | Paper on Power of attorney - IETF draft proposed
Updates release candidates
SysML models/library/profile | Jerker/Geza
SysML 1.6 profile & core system models | Jerker/Fadwa
Updates to prototypes
C++ v4.2 | Szvetlin/Pal
GO version of mandatory core system | Jens/Pablo/JanvD
Code generation from SysML | Geza/Saadia/Cristina
Consumer code generation | Cristina
WorkFlowManager | Jaime
Contract Proxy | Ulf/Emanuel
Autonomic re-orchestration | Hua
ESB-CPN, NodeRed | Felix | NodeRed - Felix: Published an article (BPNM, AAS)
Translation - sermantics | Jacob/Pedro/Rogerio
SysML 2 | Oystein/Geza
Kura & Kapua | Paolo
User authentication | Tomas/Jan
OPC-UA adaptor | Aparajita
Z-wave adaptor | Salman
Modbus TCP. adaptor | Salman
Thing of web adaptors | Federico/Szvetlin
ISO 10303 adaptor skeleton. | Kjell
Simulator (FMI) adaptor | Jan vD
Test-tool | Hans
Sandboxing tool | Hans
Command line tool adaptor OSLC | Jan Feidor
Power of attorny | Sree | Paper on Power of attorney - IETF draft proposed
NGAC - data sharing | Alex/Ulf
QoS | Daniel
C# and .net libraries | Jerker
Updates on engineering tools
Engineering process | Jan/Gianvito
Engineering tool chain | Marek/Federico
Engineering tools | Hans/Pal
Model based engineering | Cristina
Web based SysML tool | Geza
SysMD tool | Christoph Grimm
Updates on training
Training HW,SW, database | Emmanuel
Training tool, | Sebastian/Marcello/Saadia
Arrowhad Tools review | Cristian
Next meeting
Next feature presentation:

## 220830
Table 1
New projects supporting Eclipse Arrowhead | All | Mine.io, AI Redgio 5.0, Comercial eco system group meeting Stockholm Nov 9 2022. Webinar in Sweden end f OCt early Nov targeting Automation and digitalisation manager.
v4.5.0 release | Szvetlin | 4.5.0 on GitHub, source code and jar files. IPR clearance from Eclipse not ready.
GO implementation of core systems | Jens
Roadmap WG v5.0
v5.0 black box SoSD, SysD, SD | Pär O | JD to contact Per O on status and progress.
Documentation wiki updates | Szvetlin | wiki pages does not contain the correct links to SysD, documents.
Basic documentation | Mats | No updates. Will make another round on this.
Adapters | Mats | No updates. Will make another round on this.
Updates release candidates
SysML models/library/profile | Jerker/Geza | Updates to the profile in Papers now include UML meta models to guid a designer to adhere to the Eclipse Arrowhead Architecture.
SysML 1.6 profile & core system models | Jerker/Fadwa
Updates to prototypes
C++ v4.2 | Szvetlin/Pal | No updates
GO version of mandatory core system | Jens/Pablo/JanvD
Code generation from SysML | Geza/Saadia/Cristina | Instalation site in the works enabling direct installation of the plug-ins into Eclipse IDE
Consumer code generation | Cristina | Student work generated a paper at IECON.
WorkFlowManager | Jaime | No updates
Contract Proxy | Ulf/Emanuel
Autonomic re-orchestration | Hua | No updates
ESB-CPN, NodeRed | Felix | No updates
Translation - sermantics | Jacob/Pedro/Rogerio | No updates
SysML 2 | Oystein/Geza | No updates
Kura & Kapua | Paolo | No updates
User authentication | Tomas/Jan
OPC-UA adaptor | Aparajita | No updates
Z-wave adaptor | Salman | Ready for release
Modbus TCP. adaptor | Salman | Oscar is working on the Modbus TCP adaptor
Thing of web adaptors | Federico/Szvetlin
ISO 10303 adaptor skeleton. | Kjell | No update
Simulator (FMI) adaptor | Jan vD | No update
Test-tool | Hans | No update
Sandboxing tool | Hans | No update
Command line tool adaptor OSLC | Jan Feidor | Integrated to Eclipse Arrowhead. Security is next step. Java spring client in the works for Visual studio code.
Power of attorny | Sree | Submitted paper to IEEE ComSoc. Next to create branch for the code.
NGAC - data sharing | Alex/Ulf | Improving implementation demoed in Coventry. No release plan of the code yet concrete
QoS | Daniel | No update
C# and .net libraries | Jerker | No update
Updates on engineering tools
Engineering process | Jan/Gianvito | New paper published in MDPI journal
Engineering tool chain | Marek/Federico | No updates
Engineering tools | Hans/Pal | No updates
Model based engineering | Cristina | See above
Web based SysML tool | Geza | No updates
SysMD tool | Christoph Grimm | No updates
Updates on training
Training HW,SW, database | Emmanuel | No updates
Training tool, | Sebastian/Marcello/Saadia | No updates
Arrowhad Tools review | Cristian
Next meeting |  | Sept 13. 15.30
Next feature presentation: |  | JD to inquiry some one.

## 220816
Table 1
New projects supporting Eclipse Arrowhead | All | Scvetlin has left Aitea
v4.5.0 release | Szvetlin | Noting to Report
Future presentation
Demo fo QoS system | Daniel
GO implementation of core systems | Jens | Good state on the core system
Roadmap WG v5.0
v5.0 black box SoSD, SysD, SD | Pär O | Work ongoing
Documentation wiki updates | Szvetlin | Work ongoing updated ti fit release version
Basic documentation | Mats
Adapters | Mats | No Update
Updates release candidates
SysML models/library/profile | Jerker/Geza | No Update
SysML 1.6 profile & core system models | Jerker/Fadwa | No Update
Security mitigation tool | Silia/Mario | No Update
Security standard compliancy | Ani/Mario | No Update
Hawkbit, | Johannes/Sven/Lucas | No Update
Ditto
Hono
Updates to prototypes
C++ v4.2 | Szvetlin/Pal | Basic doc is there. Testing
GO version of mandatory core system | Jens/Pablo/JanvD | No Update
Code generation from SysML | Geza/Saadia | One paper accepted , Missmatch analyser.
Consumer code generation | Cristina
WorkFlowManager | Jaime
Contract Proxy | Ulf/Emanuel
Autonomic re-orchestration | Hua | No Update
ESB-CPN, NodeRed | Felix
Translation - sermantics | Jacob/Pedro/Rogerio | No Update
SysML 2 | Oystein/Geza | No Update
Kura & Kapua | Paolo | No Update
User authentication | Tomas/Jan
OPC-UA adaptor | Aparajita | No Update
Z-wave adaptor | Salman | No Update
Modbus TCP. adaptor | Salman | No Update
Thing of web adaptors | Federico/Szvetlin
ISO 10303 adaptor skeleton. | Kjell | No Update
Simulator (FMI) adaptor | Jan vD | No Update
Test-tool | Hans | Some work is done during summer.
Sandboxing tool | Hans | No Update
Command line tool adaptor | Jan Feidor | Nothing during summer. More fetures will come.
Power of attorny | Sree | No Update
NGAC - data sharing | Alex/Ulf | No Update
QoS | Daniel | No Update
C# and .net libraries | Jerker | No Update
Updates on engineering tools
Engineering process | Jan/Gianvito | No Update
Engineering tool chain | Marek/Federico | No Update
Engineering tools | Hans/Pal | No Update
Model based engineering | Cristina | No Update
Web based SysML tool | Geza | No Update
SysMD tool | Christoph Grimm | No Update
Updates on training
Training HW,SW, database | Emmanuel | No Update
Training tool, | Sebastian/Marcello/Saadia | No Update
Arrowhad Tools review | Cristian
Next meeting | July 5 15.30
Next feature presentation:

## 220621
Table 1
v4.5.0 release | Szvetlin | GAMS, MFCV, Eclipse Hono, Eclipse Ditto, Hawkbit configuration. V4.5.0 will be pushed for IPR check and official release early next.
Roadmap WG v5.0 | Jerker
v5.0 black box SoSD, SysD, SD | Pär O | SysD and SD’s for <service Registry are in GitHub roadmap directory.
Documentation wiki updates | Szvetlin | No update. Szvetlin consider it as acceptable.
Basic documentation | Mats | No updates
Adapters | Mats | Updates to issue #41. Content is there but need quality check before release of the document.
Updates release candidates
SysML models/library/profile | Jerker/Geza | No update
SysML 1.6 profile & core system models | Jerker/Fadwa | No update
Security mitigation tool | Silia/Mario | v.4.5.0
Security standard compliancy | Ani/Mario | v.4.5.0
Hawkbit, | Johannes/Sven/Lucas | v.4.5.0
Ditto |  | v.4.5.0
Hono |  | v.4.5.0
Updates to prototypes
C++ v4.2 | Szvetlin/Pal | compliant with v4.2. The plan is to update it to v.5.0 after the Java version v5.0 is done.
GO version of mandatory core system | Jens/Pablo/JanvD | Work is ongoing by Jens. Jens is in currently in Australia. The plan is to have working v.5 version during July.
Code generation from SysML | Geza/Saadia | Paper on Studio4Education submitted to IEEE IECON. First trial with students. They do have a number of issues.
Consumer code generation | Cristina | No update
WorkFlowManager | Jaime | No update
Contract Proxy | Ulf/Emanuel | Not active for the time being
Autonomic re-orchestration | Hua | Code is far from be release. The main development is done on the Knowledge based part of MAPE-K. Looking into fussy rule instead of SparQL.
ESB-CPN, NodeRed | Felix | No updates
Translation - sermantics | Jacob/Pedro/Rogerio | Not active for the time being
SysML 2 | Oystein/Geza | No update
Kura & Kapua | Paolo | Discussion next week in Lulea
User authentication | Tomas/Jan | Not active for the time being.
OPC-UA adaptor | Aparajita | Preparing for a demo at the Arrowhead review. Will be ready for 5.0 release
Z-wave adaptor | Salman | Preparing for a demo at the Arrowhead review. Will be ready for 5.0 release
Modbus TCP. adaptor | Salman | Preparing for a demo at the Arrowhead review. Will be ready for 5.0 release
Thing of web adaptors | Federico/Szvetlin | Jerker to talk to Federico regarding release plans.
ISO 10303 adaptor skeleton. | Kjell | Jerker to talk with Kjell after summer holidays
Simulator (FMI) adaptor | Jan vD | No update
Test-tool | Hans | No update
Sandboxing tool | Hans | No update
Command line tool adaptor | Jan Feidor | Presented at HIPEC this week with good visibility. The Unite and Uniqe tools was presented.
Power of attorny | Sree | Two paper in the pipe line, journal and conference papers.
NGAC - data sharing | Alex/Ulf | Demo presented in Warwick. Goal to release it with v5.0. Alex go this Licentiate degree.
QoS | Daniel | Done with first implementation.
C# and .net libraries | Jerker | Not active for the time being.
Updates on engineering tools
Engineering process | Jan/Gianvito | New paper submitted, will be resubmitted after review updates by end of this week.
Engineering tool chain | Marek/Federico | No update
Engineering tools | Hans/Pal | No updates
Model based engineering | Cristina | No updates
Web based SysML tool | Geza | No updates
SysMD tool | Christoph Grimm | No updates
Updates on training
Training HW,SW, database | Emmanuel | Cleaning of the training meeting in progress.
Training tool, | Sebastian/Marcello/Saadia
Arrowhad Tools review | Cristian | No on-line possibility for the review meeting.
Next meeting | July 5 15.30 | Then break until August 16
Next feature presentation: |  | Demo of QoS by Daniel

## 220607
Table 1
IEEE ICPS Warwick | Jerker | Mnitors not provided fro the demos. One day was to short.
v4.5.0 release | Szvetlin | Will be pushed for the IPR check submission in 2 weeks time.
Roadmap WG v5.0 | Jerker
v5.0 black box SoSD, SysD, SD | Pär O | SysD and Sd for mandatory core system ready by end of June.
Documentation wiki updates | Szvetlin | Szvetlin is pushing.
Basic documentation | Mats | No update
Adapters | Mats | No update
Updates release candidates
SysML models/library/profile | Jerker/Geza
SysML 1.6 profile & core system models | Jerker/Fadwa | Added the profile for Studio4Education
Security mitigation tool | Silia/Mario | Still not merged in to the master branch
Security standard compliancy | Ani/Mario | Still not merged in to the master branch, JD to kick on Markus tauber
Hawkbit, | Johannes/Sven/Lucas | v4.5.0
Ditto |  | v.4.5.0 to be merged
Hono |  | v.4.5.0 to be merged
Updates to prototypes
C++ v4.2 | Szvetlin/Pal | C++ v4.2 was released. v4.5.0 will be worked on during the summer.
GO version of mandatory core system | Jens/Pablo/JanvD | No update
Code generation from SysML | Geza/Saadia | No update
Consumer code generation | Cristina | Miss match identification. Summer student will work on this.
WorkFlowManager | Jaime | No updates
Contract Proxy | Ulf/Emanuel
Autonomic re-orchestration | Hua | No updates
ESB-CPN, NodeRed | Felix | No updates
Translation - sermantics | Jacob/Pedro/Rogerio | Not updates
SysML 2 | Oystein/Geza | No update
Kura & Kapua | Paolo | No update
User authentication | Tomas/Jan | No updates - close this point
OPC-UA adaptor | Aparajita | No update
Z-wave adaptor | Salman | Z-wave adaptor
Modbus TCP. adaptor | Salman | Will be restarted after june 28.
Thing of web adaptors | Federico/Szvetlin
ISO 10303 adaptor skeleton. | Kjell | No updates
Simulator (FMI) adaptor | Jan vD | No updates is with aparajita
Test-tool | Hans | No updates - will become commercial tools. part of these tool may be open source
Sandboxing tool | Hans | No updates - will become commercial tools.
Command line tool adaptor | Jan Feidor | No updates
User authentication/authorisation | Jan Feidor | No updates
Power of attorny | Sree | Work on publication. Target is v5.0 release.
NGAC - data sharing | Alex/Ulf | NGAC policy server was demonstrated in Warwick. Next step is to move too the v5.0. User contract also demoed in Warwick. Also targeted for v5.0 release.
QoS | Daniel | No update
C# and .net libraries | Jerker
Updates on engineering tools
Engineering process | Jan/Gianvito | Journal paper submitted. First reviewer comments achieved. Not to complicated to respond to.
Engineering tool chain | Marek/Federico | No update
Engineering tools | Hans/Pal | 157 tools being worked with. Check D5.7 last pages. very impressive numbers.
Model based engineering | Cristina | Demoed in Warwick. Missing is plug-in in to the IDE.
Web based SysML tool | Geza | Dissemination ongoing today.
SysMD tool | Christoph Grimm | No updates
Updates on training
Training HW,SW, database | Emmanuel
Training tool, | Sebastian/Marcello/Saadia | Video demo available.
Next meeting | June 7 15.30 | Runtime verification using SysMD in July.
Next feature presentation:

## 220510
Table 1
IEEE ICPS Warwick | Mats
Feature presentation: Studio4Educaiton | Saadia/Sebastian/Fadwa | Great demo. How to make this more visible. Include in D11.4 and documentation in the wiki of the profile directory of eclipse-arrowhead.
Feature presentation: QoS | Daniel
Roadmap WG v5.0 | Jerker
v5.0 black box SoSD, SysD, SD | Pär O
Documentation wiki updates | Szvetlin
Basic documentation | Mats
Adapters | Mats
Updates release candidates
SysML models/library/profile | Jerker/Geza | No updates
SysML 1.6 profile & core system models | Jerker/Fadwa | No updates
Security mitigation tool | Silia/Mario | No updates
Security standard compliancy | Ani/Mario | No updates
Hawkbit, | Johannes/Sven/Lucas | Internal lega audit in Bosch before release. Soon to be finished.
Updates to prototypes
C++ v4.2 | Szvetlin/Pal | Ready as v4.4.1. In arrowhead-f. IPR check still needed. Pal to push the IPR check.
GO version of mandatory core system | Jens/Pablo/JanvD | Looking into backward compatibility tested by Jan.
Code generation from SysML | Geza/Saadia | Remove consider it released.
Consumer code generation | Cristina | No updates
WorkFlowManager | Jaime | No updates
Contract Proxy | Ulf/Emanuel
Autonomic re-orchestration | Hua | No updates
Digital twin - Ditto | Johannes/Lukas/Abdulla | No updates
Device hub and Hono | Johannes/Sven/Lukas | Internal lega audit in Bosch before release. Soon to be finished.
ESB-CPN, NodeRed | Felix | Presented at NOMS WS.
Translation - sermantics | Jacob/Pedro/Rogerio | Jacob PHD thesis successfully defended.
SysML 2 | Oystein/Geza | Oystein presentaiton of SysML 2 model for the Arrowhead SOA validation use case yesterday. Model is uploaded into the official SysML repo. Some semantic issues still open but expected to be solved shortly.
Kura & Kapua | Paolo | Move to new bi-weekly
User authentication | Tomas/Jan | Move to new bi-weekly
OPC-UA adaptor | Aparajita | Move to new bi-weekly
Z-wave adaptor | Salman | Move to new bi-weekly
Modbus TCP. adaptor | Salman | Move to new bi-weekly
Thing of web adaptors | Federico/Szvetlin | Move to new bi-weekly
ISO 10303 adaptor skeleton. | Kjell | Move to new bi-weekly
Simulator (FMI) adaptor | Jan vD | Move to new bi-weekly
Test-tool | Hans | Move to new bi-weekly
Sandboxing tool | Hans | Move to new bi-weekly
Command line tool adaptor | Jan Feidor | Move to new bi-weekly
User authentication/authorisation | Jan Feidor | Move to new bi-weekly
Power of attorny | Sree | Move to new bi-weekly
NGAC - data sharing | Alex/Ulf | Move to new bi-weekly
QoS | Daniel | Move to new bi-weekly
C# and .net libraries | Jerker | Move to new bi-weekly
Updates on engineering tools
Engineering process | Jan/Gianvito | Move to new bi-weekly
Engineering tool chain | Marek/Federico | Move to new bi-weekly
Engineering tools | Hans/Pal | Move to new bi-weekly
Model based engineering | Cristina | Move to new bi-weekly
Web based SysML tool | Geza | Move to new bi-weekly
SysMD tool | Christoph Grimm | Move to new bi-weekly
Updates on training
Training HW,SW, database | Emmanuel | Move to new bi-weekly
Training tool, | Sebastian/Marcello/Saadia | Move to new bi-weekly
Next meeting | June 7 15.30 | June 7 15.30
Next feature presentation: |  | No proposals yet

## 220426
Table 1
23 participants
IEEE ICPS Warwick | Mats | Slides for virtual exhibition presented.
Feature presentation: Power of attorney | Sree | Presented by Sree, Olov and Niclas. Emanuel have questions (How is PoA different from regular token? Etc.), will continue in other forum.
Feature presentation: Sandboxing tool | Ulf Slunga | Presenting the "Sandboxing concept" for Arrowhead. Packaging of core systems… (Not a tool demo)
Roadmap WG v5.0 | Jerker
v5.0 specifications | Szvetlin | No updates
Documentation wiki updates | Szvetlin | No updates
Basic documentation | Mats | Will be another meeting soon, for documentation overview. No updates from Emanuel.
Adapters | Mats | Work ongoing. Indentifying candidates for v4.5 and for the Commersial Ecosystem
Updates release candidates
SysML models/library/profile | Jerker/Geza | No Comment
SysML 1.6 profile & core system models | Jerker/Fadwa | No updates
Security mitigation tool | Silia/Mario | No Comment
Security standard compliancy | Ani/Mario | No Comment
Hawkbit, | Johannes/Sven/Lucas | No Comment
Updates to prototypes
C++ v4.2 | Szvetlin/Pal | Service registry done, Auth done, Orchestration almost done. Event handler, cert auth, device reistry, all done.
GO version of mandatory core system | Jens/Pablo/JanvD | Designed to make it easy to make application systems. Based on ideas from Jan. Planning ongoing, hopefully work during June, release after vacation, TBC. The Arrowhead control tool released as open source on Github.
Code generation from SysML | Geza/Saadia | No Comment
Consumer code generation | Cristina | Working on students on a paper for code generation with Orchestrator.
WorkFlowManager | Jaime | No updates
Contract Proxy | Ulf/Emanuel | No ongoing work now. Remove from agenda.
Autonomic re-orchestration | Hua | Testing ongoing. Preparing for demo in May.
Digital twin - Ditto | Johannes/Lukas/Abdulla | Olov: Demo in Warwick planning. Plan for full release candidate.
Device hub and Hono | Johannes/Sven/Lukas | No comment
ESB-CPN, NodeRed | Felix | Workflow manager. Presented in NOMS, will demo in Warwick. Availible in GitHub.
Translation - sermantics | Jacob/Pedro/Rogerio | No comment
SysML 2 | Oystein/Geza | No Comment
Kura & Kapua | Paolo | No comment
User authentication | Tomas/Jan | No comment
OPC-UA adaptor | Aparajita | No Comment
Z-wave adaptor | Salman | No Comment
Modbus TCP. adaptor | Salman | No Comment
Thing of web adaptors | Federico/Szvetlin | Ready since February. Remove from agenda.
ISO 10303 adaptor skeleton. | Kjell | No Comment
Simulator (FMI) adaptor | Jan vD | No Comment
Test-tool | Hans | No Comment
Sandboxing tool | Hans | See Feature presentation
Command line tool adaptor | Jan Feidor | No Comment
User authentication/authorisation | Jan Feidor | No Comment
Power of attorny | Sree | See Feature presentation
NGAC - data sharing | Alex/Ulf | Preparing new demos for Warwick.
QoS | Daniel | Still working to finalise. Preparing for a feature presentation.
C# and .net libraries | Jerker | No Comment
Updates on engineering tools
Engineering process | Jan/Gianvito | No Comment
Engineering tool chain | Marek/Federico | No Comment
Engineering tools | Hans/Pal | No Comment
Model based engineering | Cristina | Working on the demo
Web based SysML tool | Geza | No Comment
SysMD tool | Christoph Grimm | Offer a demo, ready.
Updates on training
Training HW,SW, database | Emmanuel | Partners still need some time to finalise. Working to finalise deliverable.
Training tool, | Sebastian/Marcello/Saadia | Working on a paper for ETFA. Working on demo for Warwick. Propose for a feature presentation next meeting.
Next meeting |  | May 10
Next feature presentation: | Johannes/Lukas/Abdulla/Olof | QoS presentation - Daniel Studio4Education - Saadia/Fadwa/Sebastien

## 220412
Table 1
Eclipse Arrowhead commercial eco system webinar March 30 | Jerker
Feature presentation: Sandboxing tool | Hans
Feature presentation: Experiences from usingArrowhead - System | Alexander
Roadmap WG v5.0 | Jerker
v5.0 specifications | Szvetlin
Documentation wiki updates | Szvetlin
Basic documentation | Mats
Adapters | Mats
Updates release candidates
SysML models/library/profile | Jerker/Geza
SysML 1.6 profile & core system models | Jerker/Fadwa
Security mitigation tool | Silia/Mario
Security standard compliancy | Ani/Mario
Hawkbit, | Johannes/Sven/Lucas
Updates to prototypes
C++ v4.2 | Szvetlin/Pal
GO version of mandatory core system | Jens/Pablo/JanvD
Code generation from SysML | Geza/Saadia
Consumer code generation | Cristina
WorkFlowManager | Jaime
Contract Proxy | Ulf/Emanuel
Autonomic re-orchestration | Hua
Digital twin - Ditto | Johannes/Lukas/Abdulla
Device hub and Hono | Johannes/Sven/Lukas
ESB-CPN, NodeRed | Felix
Translation - sermantics | Jacob/Pedro/Rogerio
SysML 2 | Oystein/Geza
Kura & Kapua | Paolo
User authentication | Tomas/Jan
OPC-UA adaptor | Aparajita
Z-wave adaptor | Salman
Modbus TCP. adaptor | Salman
Thing of web adaptors | Federico/Szvetlin
ISO 10303 adaptor skeleton. | Kjell
Simulator (FMI) adaptor | Jan vD
Test-tool | Hans
Sandboxing tool | Hans
Command line tool adaptor | Jan Feidor
User authentication/authorisation | Jan Feidor
Power of attorny | Sree
NGAC - data sharing | Alex/Ulf
QoS | Daniel
C# and .net libraries | Jerker
Updates on engineering tools
Engineering process | Jan/Gianvito
Engineering tool chain | Marek/Federico
Engineering tools | Hans/Pal
Model based engineering | Cristina
Web based SysML tool | Geza
Updates on training
Training HW,SW, database | Emmanuel
Training tool, | Sebastian/Marcello/Saadia
Next meeting
Next feature presentation: | Johannes/Lukas/Abdulla/Olof

## 220329
Table 1
Eclipse Arrowhead commercial eco system webinar March 30 | Jerker | Please check the link to the progremme and registration in the agenda.
Feature presentation: Digital twin by Abdhulla | Abdhulla | Presented and demoed. Slides, integration spec and more is in owncloud (see link). Note: Pal has another demo development ongoing and may use the adapter presented here.
Roadmap WG v5.0 | Jerker
v5.0 specifications | Szvetlin | Workshop w 5.0 wg, sys registry, dev registry etc. documentation is taken over by Per (Sinetiq)
Documentation wiki updates | Szvetlin | Minor updatdes done
Basic documentation | Emanuel | Concepts refs to be finalized TBD, will be handled in the roadmap WG
Updates release candidates
SysML models/library/profile | Jerker/Geza | No comments.
SysML 1.6 profile & core system models | Jerker/Fadwa | No comments.
Security mitigation tool | Silia/Mario | No comments.
Security standard compliancy | Ani/Mario | No comments.
Hawkbit, | Johannes/Sven/Lucas | No major updates, pull request has been merged, should be part of next release. DONE, item can be closed.
C# and .net libraries | Jerker | No comments.
Updates to prototypes
C++ v4.2 | Szvetlin/Pal | No updates
GO version of mandatory core system | Jens/Pablo/JanvD | No comments.
Code generation from SysML | Geza/Saadia | No comments.
Consumer code generation | Cristina | Supervising how to identifying mismatches
WorkFlowManager | Jaime | No comments.
Contract Proxy | Ulf/Emanuel | No ongoing work as of now, perhaps restarted this fall with Husqvarna
Autonomic re-orchestration | Hua | Request sent about potential release. Internal meeting on handling this request is tomorrow.
Digital twin - Ditto | Johannes/Lukas/Abdulla | Todays feature presentation
Device hub and Hono | Johannes/Sven/Lukas | Hopefully a pull request in the next month.
ESB-CPN, NodeRed | Felix | Inplemented workflow manager in NodeRed, tested. Demo and video is ongoing, should be ready before Easter.
Translation - sermantics | Jacob/Pedro/Rogerio | No comments.
SysML 2 | Oystein/Geza | No comments.
Kura & Kapua | Paolo | No comments.
User authentication | Tomas/Jan | No comments.
OPC-UA adaptor | Aparajita | No big news, there is an issue in Eclipse AH. Waiting for response.
Z-wave adaptor | Salman | No comments.
Modbus TCP. adaptor | Salman | No comments.
Thing of web adaptors | Federico/Szvetlin | Contribution was accepted 2 months ago. Item should be closed.
ISO 10303 adaptor skeleton. | Kjell | No comments.
Simulator (FMI) adaptor | Jan vD | No comments.
Test-tool | Hans | No comments.
Sandboxing tool | Hans | No comments.
Command line tool adaptor | Jan Feidor | No comments.
User authentication/authorisation | Jan Feidor | No comments.
Power of attorny | Sree | Progressing, started implementation, demo of onboarding to AH using PoA. Feature presentation in 2-4 weeks? TBD.
NGAC - data sharing | Alex/Ulf | Bachelor thesis project initiated to develop a PoC of an Arrowhead policy server based on the OpenGroup NGAC implementation. The Policy server will provide Policy Decision Pont (PDP) services for applications systems to implement based on a library Policy Enforcement Point (PEP) functionalities that use the policy server / PDP services. Bachelor thesis project initiated to develop a PoC of an Arrowhead policy server based on the OpenGroup NGAC implementation. The Policy server will provide Policy Decision Pont (PDP) services for applications systems to implement based on a library Policy Enforcement Point (PEP) functionalities that use the policy server / PDP services. Bachelor thesis project initiated to develop a PoC of an Arrowhead policy server based on the OpenGroup NGAC implementation. The Policy server will provide Policy Decision Pont (PDP) services for applications systems to implement based on a library Policy Enforcement Point (PEP) functionalities that use the policy server / PDP services.
QoS | Daniel | No comments.
Adaptor list reporting | Mats | Request for AH-Ditto adapter sent. 27 adapters in the list, received the info about 12 of them. Roadmap issue #41. ALL concerned, please respond to the survey.
Updates on engineering tools
Engineering process | Jan/Gianvito | No comments.
Engineering tool chain | Marek/Federico | No comments.
Engineering tools | Hans/Pal | Having wp5 deliverable. Will be a complete catalogue now (meeting was Friday morning). Will show many chains of AH tools.
Model based engineering | Cristina | Now on documentation. Will be shown in the UK meeting.
Web based SysML tool | Geza | No comments.
Updates on training
Training HW,SW, database | Emmanuel | Progressing to wrap up material. Remaing work from the Lübeck meeting. Still working on the organisation.
Training tool, | Sebastian/Marcello/Saadia | No comments.
Next meeting
Next feature presentation: | Johannes/Lukas/Abdulla/Olof | Sandboxing tool - Hans Experiences from usingArrowhead - System (Alexander 10 minutes to get feedback)

## 220315
Table 1
28 participants
Eclipse Arrowhead commercial eco system webinar March 30 | Jerker | Announcement of the Eclipse Arrowhead commercial ecosystem webinar.
Feature presentation: Lowering the entry step: preconfigured intercloud VM. | Gabor | Ready to be tested. Plan to published a new version in i few weeks. Here is the link to the download links of the virtual machine: https://github.com/MaGaMeGa/helloAHworld/blob/development/os/docs/intercloud_machine_v_beta.01.links.txt A Read Me overview? Not yet User documentation? Some documentation in the repository.
Roadmap WG v5.0 | Jerker
v5.0 specifications | Szvetlin | Discussion in Roadmap GitHub repo.
Documentation wiki updates | Szvetlin | No update
Basic documentation | Emanuel
Updates release candidates
SysML models/library/profile | Jerker/Geza | No comment
SysML 1.6 profile & core system models | Jerker/Fadwa | No comment
Security mitigation tool | Silia/Mario | No comment
Security standard compliancy | Ani/Mario | No comment
Hawkbit, | Johannes/Sven/Lucas | Ready for release, Close the point
C# and .net libraries | Jerker | No progress on this.
Updates to prototypes
C++ v4.2 | Szvetlin/Pal | No comment
GO version of mandatory core system | Jens/Pablo/JanvD | No updates
Code generation from SysML | Geza/Saadia | No updates
Consumer code generation | Cristina | No update
WorkFlowManager | Jaime | No update, working with modifying rejected paper.
Contract Proxy | Ulf/Emanuel | No update
Autonomic re-orchestration | Hua | No update,
Digital twin - Ditto | Johannes/Lukas/Abdulla | A early proof of concept. Feature presentation next. Ready for presentation in 2 weeks.
Device hub and Hono | Johannes/Sven/Lukas | No major updates. Plan to finish soon.
ESB-CPN, NodeRed | Felix | Demo in progress, almost finished. A video will be produced. NOMS paper accepted.
Translation - sermantics | Jacob/Pedro/Rogerio | No updates
SysML 2 | Oystein/Geza | No comment
Kura & Kapua | Paolo | No update
User authentication | Tomas/Jan | No update
OPC-UA adaptor | Aparajita | Still waiting for CI/CD process to start
Z-wave adaptor | Salman | No comment
Modbus TCP. adaptor | Salman | No comment
Thing of web adaptors | Federico/Szvetlin | No comment
ISO 10303 adaptor skeleton. | Kjell | No comment
Simulator (FMI) adaptor | Jan vD | No updates
Test-tool | Hans | Work on using a new Java version. Starting to prepare a demo. Can make a feature presentation with a couple of weeks notice.
Sandboxing tool | Hans | Hans to check with Sinetiq.
Command line tool adaptor | Jan Feidor | No comment
User authentication/authorisation | Jan Feidor | No comment
Power of attorny | Sree | Progressing, protocol flow is in design. Now doing implementation. Plan to be ready in 4 weeks.
NGAC - data sharing | Alex/Ulf | Olof: Progressing for a paper Arrowhead implementation not started.
QoS | Daniel | No real updates. Can make a feature presentation soon.
Adaptor list reporting | Mats | 26 adaptors and some few adapted tools. Information recieved from some. Please, if you havent responded, do so.
Updates on engineering tools
Engineering process | Jan/Gianvito | Video in progress, draft in 2 weeks time
Engineering tool chain | Marek/Federico | No comment
Engineering tools | Hans/Pal | Waiting for survey response for D5.7 (miss ~30)
Model based engineering | Cristina | Eclipse Plug-in is progressing. Will be ready for demo in Coventry. Documentation and tutorial will ve ready for the next release
Web based SysML tool | Geza | No comment
Updates on training
Training HW,SW, database | Emmanuel | Request for documentation and training material. List update ongoing. Deliverable a little late.
Training tool, | Sebastian/Marcello/Saadia | No comment
Next meeting |  | March 29 at 15.30
Next feature presentation: | Johannes/Lukas/Abdulla/Olof | Digital twin

## 220301
Table 1
Eclipse Arrowhead commercial eco system webinar March 30 | Jerker | Announcement of the Eclipse Arrowhead commercial ecosystem webinar.
Feature presentation: GO version of core system | Jan vD, Jens | Cool presentation of prototype GO version of some of the core systems. Code not ready for prime time. Contact Jan or Jens for possibilities to test and participate.
Roadmap WG v5.0 | Jerker
Documentation wiki updates | Szvetlin
Basic documentation | Emanuel
Updates release candidates
SysML models/library/profile | Jerker/Geza | Paper by Geza and Bosch on SysML modelling and
Security mitigation tool | Silia | No updates
Security standard compliancy | Ani | No updates
Hawkbit, | Johannes/Sven/Lucas | Ready for release, Close the point
C# and .net libraries | Jerker | No progress on this.
Updates to prototypes
C++ v4.2 | Szvetlin/Pal | No progress but still alive
GO version of mandatory core system | Jens/Pablo/JanvD | See above
Code generation from SysML | Geza/Saadia | No updates
Consumer code generation | Cristina | No update
WorkFlowManager | Jaime | No update
Contract Proxy | Ulf/Emanuel | No update
Autonomic adaptation | Hoa | No update,
Digital twin - Ditto | Johannes | A early proof of concept. Feature presentation next meeting
ESB-CPN, NodeRed | Felix | Demo in progress, a video will be produced.
Translation - sermantics | Jacob/Pedro/Rogerio | No updates
SysML 2 | Oystein/Geza | Tools and language is progressing still 12 months and more for prime time
Kura & Kapua | Paolo | No update
User authentication | Tomas/Jan | No update
OPC-UA adaptor | Aparajita | Waiting for CI/CD process to start
Z-wave adaptor | Salman | Z-wave demand response test on-going.
Modbus. adaptor | Salman
Thing of web adaptors | Federico/Szvetlin | In arrowhead-f repo.
ISO 10303 adaptor skeleton. | Kjell | Completed. Demo April 4 to be webcasted.
FMI adaptor | Jan vD | Resources now available to proceed.
Test-tool | Hans | Work on using a new Java version.
Sandboxing tool | Hans
Command line tool adaptor | Jan Feidor | Integration to Arrowhead work on-going
Power of attorny | Sree | Progress, protocol flow is in design.
NGAC - data sharing | Alex/Ulf | No update
QoS | Daniel | Finalising the QoS concept.
Adaptor list reporting | Mats | 26 adaptors and some few adapted tools.
Updates on engineering tools
Engineering process | Jan/Gianvito | Video in progress, draft in 2 weeks time
Engineering tool chain | Marek/Federico | Tools chain analysis to find tool interaction features.
Engineering tools | Hans/Pal | Description of market offer.
Model based engineering | Cristina | Eclipse Plug-in is progressing. Will be ready for demo in Coventry. Documentation and tutorial will ve ready for the next release
Web based SysML tool | Geza
Updates on training
Training HW,SW, database | Emmanuel | Request for documentation and training material.
Training tool, | Sebastian/Marcello/Saadia | Developments are on-track. Last effort to finish integration with the Studio4Education. When can this be show cased.
| Hans | Coventry info requested for ext meeting
Next meeting

## 220214
Table 1
Eclipse Arrowhead commercial eco system webinar March 30 | Jerker | Eclipse Arrowhead ecosystem webinar March 30 at 14.00
Feature presentation: Command-line tool adaptors, | Jan Feidor | OSLC used to integrate IDE with code analysis tools. Two tools Unite and UniC. Unite used with your command line tools. UniC used with Eclipse IDE,
Roadmap WG v5.0 | Jerker
Documentation wiki updates | Szvetlin
Basic documentation | Emanuel
Updates release candidates
SysML models/library/profile | Jerker/Geza | No update
Security mitigation tool | Silia | No updates
Security standard compliancy | Ani
Hawkbit, | Johannes/Sven/Lucas | No major update,
C# and .net libraries | Jerker | No updates
Updates to prototypes
C++ v4.2 | Szvetlin/Pal | No updates
GO version of mandatory core system | Jens/Pablo/JanvD | Feature presentation in 2 weeks time.
Code generation from SysML | Geza/Saadia | No updates
Consumer code generation | Cristina | No updates
WorkFlowManager | Jaime | No code updates
Contract Proxy | Ulf/Emanuel | Waiting for connection to usage scenario.
Autonomic adaptation | Hoa | System soon ready for release. Documentation still to be done. An Lan dissertation on Feb 22 at 10.00
Digital twin - Ditto | Johannes | No major updates. A major issue under agreements.
ESB-CPN, NodeRed | Felix | Working on demo and video for IEEE ICPS on NodeRed contribution
Translation - sermantics | Jacob/Pedro/Rogerio | No update. Update of the translation system will come from Thingwave.
SysML 2 | Oystein/Geza | No updates.
Kura & Kapua | Paolo | No updates
User authentication | Tomas/Jan | No updates
OPC-UA adaptor | Aparajita | Waiting for start o the CI/CD process.
Z-wave adaptor | Salman | No updates
Modbus. adaptor | Salman
Thing of web adaptors | Federico/Szvetlin | No updates
ISO 10303 adaptor skeleton. | Kjell | Ready for release and CI/CD process.
FMI adaptor | Jan vD | No update
Test-tool | Hans | No update
Sandboxing tool | Hans
Command line tool adaptor | Jan Feidor | See feature presentation
Power of attorny | Sree | Integration with On-boardning. Application and network layer on-boarding.
NGAC - data sharing | Alex/Ulf | Short presentation on use of NGAC for data sharing.
Digital twin | Abdulla/Olof
QoS | Daniel | Started.
Adaptor list reporting | Mats | More soide update in 2 weeks.
Updates on engineering tools
Engineering process | Jan/Gianvito
Engineering tool chain | Marek/Federico
Engineering tools | Hans/Pal
Model based engineering | Cristina
Web based SysML tool | Geza
Updates on training
Training HW,SW, database | Emmanuel
Training tool, | Sebastian/Marcello/Saadia
Market oriented action group | Kjell
Photos from Lubeck now in the Lubeck meeting folder of owncloud. | Javad
Next meeting

## 220201 - Table 1-1
Table 1-1
Eclipse Arrowhead v4.5/5.0 | Szvetlin | JD open an issue in GitHub on new core systems to be included in v4.5 and v5.0 release.
Roadmap WG v5.0 | Jerker | Updates to templates being made according to comment in issue #42 in the roadmap repo.
Documentation wiki updates | Szvetlin
Basic documentation | Emanuel
Updates release candidates
SysML models/library/profile | Jerker/Geza | No updates
Security mitigation tool | Silia | Still waiting for input from Mario
Security standard compliancy | Ani | Still waiting for input from Mario
Hawkbit, | Johannes/Sven/Lucas | Approved for 4.5 release
C# and .net libraries | Jerker | no updates
Updates to prototypes
C++ v4.2 | Szvetlin/Pal | No updates
GO version of mandatory core system | Jens/Pablo/JanvD | ServiceRegistry and Orchestration GO prototypes are working. Feature talk in 4 weeks by both Jens and Jan.
Code generation from SysML | Geza/Saadia | No update
Consumer code generation | Cristina | A student project just started on this.
WorkFlowManager | Jaime | No updates on the code. Paper submitted on Workflow paper + thesis is in the works
Contract Proxy | Ulf/Emanuel | No update
Autonomic adaptation | Hoa | Paper submitted to IEEE ICPS. An Lam paper published in IEEE IJIES + PhD thesis to be defended on Feb 22.
Digital twin - Ditto | Johannes | Updates approach compared to the one presented last meeting.
ESB-CPN, NodeRed | Felix | Works on a demo. Simulation of a workflow. Paper is in the work.
Translation - sermantics | Jacob/Pedro/Rogerio | No updates
SysML 2 | Oystein/Geza | No updates
Kura & Kapua | Paolo | No updates
User authentication | Tomas/Jan | No updates
OPC-UA adaptor | Aparajita | Waiting for move of code. Slack communication with Szvetlin
Z-wave adaptor | Salman | Currently in GitHub.
Modbus. adaptor | Salman | Will be taken up next week. A paper on cloud based learning. Willing to present in next bi-weekly.
Thing of web adaptors | Federico/Szvetlin | Szvetlin will make a request to Federico.
ISO 10303 adaptor skeleton. | Kjell | No updates
FMI adaptor | Jan vD | Delayed by 3 months
Test-tool | Hans | No updates
Sandboxing tool | Hans | No updates
X.509 profile | Emanuel | Done close the point.
Command line tool adaptor | Jan Feidor | No updates
Power of attorny | Sree | Feature presentation in 6 weeks
NGAC | Alex | Attribute access control and attribute access encryption.
Digital twin | Abdulla/Olof | See Ditto
Adaptor list reporting | Mats | e.g. NodeRed see. isse #41 in the roadmap.
Updates on engineering tools
Engineering process | Jan/Gianvito | Publication as a journal paper is restarted. A professionally made video is in progress
Engineering tool chain | Marek/Federico | No updates
Engineering tools | Hans/Pal | D5.6 is submitted
Model based engineering | Cristina | Plugins for Eclipse IDE now based on v4.4.1. The latest Papyrus libraries now used. Planed for the 4.5.0 release.
Web based SysML tool | Geza | No updates
Updates on training
Training HW,SW, database | Emmanuel | No updates
Training tool, | Sebastian/Marcello/Saadia | No update
Market oriented action group | Kjell | Release webinar for commercial eco system around Eclipse Arrowhead.
Photos from Lubeck now in the Lubeck meeting folder of owncloud. | Javad | Thanks
Next meeting

## 220118
Table 1
Eclispe Arrowhead v4.4.1 | Szvetlin | Log4J library dependency updated to a secure version fixing a security hole found in Dec 2021.
Collaboration with other projects | Jerker | Three EU project FA4.0 iRel4.0 and MIRAI have all asked for webinars on Eclispe Arrowhead other Arrowhead Tools technology
Eclipse Ditto integration into Eclipse Arrowhead | Johannes | Presentation of Eclispe Ditto and its planed integration into Eclipse Arrowhead. Complmented by Ditta usage in a general Digital Twin concept by Olov Schelen. Slides in todays folder at GitHub. We lok froward to the further report on this development.
Roadmap WG v5.0 | Jerker | New templates for SysD, SysDD, SD and IDD created and are located in the Eclipse-Arrowhead/roadmap repository at github.
Documentation wiki updates | Szvetlin | No updates
Basic documentation | Emanuel | Two new documents pre-release
Updates release candidates
SysML models/library/profile | Jerker/Geza | No updates
Security mitigation tool | Silia | No updates
Security standard compliancy | Ani | No updates
Hawkbit, | Johannes/Sven/Lucas | Pull request approved. Almost ready for the next official release. Open issue is on Json Web Tokens.
C# and .net libraries | Jerker | No updates
Updates to prototypes
C++ v4.2 | Szvetlin/Pal | No updates
Go version of mandatory core system | Jens/Pablo/JanvD | ServiceRegistry in GO i up for test next week. Orchestrator in the works, plus 2 application systems. Stability issues addressed by ThingWave and Jens.
Code generation from SysML | Geza/Saadia | RCP ready for release., jerker and Saadia to bring to release.
Consumer code generation | Cristina | Student work on mismatch identification will start this week. M.Sc thesis work ready by summer 2022.
WorkFlowManager | Jaime | No updates to the actual system. A paper discussion Workflow system, NodeRed and Choreography system to be submitted this week.
Contract Proxy | Ulf/Emanuel | No updates
Autonomic adaptation | Hoa | Working on a paper to demonstrate potential of the autonomic adaptation system. Using the crane on the ship.
Device hub and Ditto | Johannes
ESB-CPN, NodeRed | Felix | No update
Translation - sermantics | Jacob/Pedro/Rogerio | Working on a concept called knowledge graphs to enable translation between heterogenous devices. Based on a language model, first experiment results in about 80% of translation accuracy.
SysML 2 | Oystein/Geza | No updates
Kura & Kapua | Paolo | No updates
User authentication | Tomas/Jan | Work on integration with Eclipse Arrowhead. Question on configuration of the Orchestration system. Send question using the slack channel. Updates site for Eclispe arrowhead installations.
OPC-UA adaptor | Aparajita | No updates. Paper to ICPS. Open a pull request.
Z-wave adaptor | Salman | Paper for Z-wav adopter. The Z-wave adaptor is redesign and will enable adorer for ZigBee, Modbus and similar protocols.
Modbus. adaptor | Salman | See above
Thing of web adaptors | Federico/Szvetlin | published in arrowhead-f at GitHub. Jerker to contact Federico on updating this for the 4.4.1 Eclipse Arrowhead.
10303 adaptor | Kjell | No updates
FMI adaptor | Jan vD | No updates
Test-tool | Hans | No updates
Sandboxing tool | Hans | No updates
X.509 profile | Emanuel
Command line tool adaptor | Jan Feidor | See above from jan
Power of attorny | Sree | No updates
NGAC | Alex | Focus presently on exploring NGAC in combination with attribute encryption. A front end for configuration of NGAC for data sharing.
Digital twin | Abdulla/Olof | See today feature presentation
Updates on engineering tools
Engineering process | Jan/Gianvito | No updates. Video is initiated
Engineering tool chain | Marek/Federico | No updates
Engineering tools | Hans/Pal | No updates
Model based engineering | Cristina | Update of IDE plugins to the v4.4.1. Update to use the latest Papyrus profile. Documentation to be written.
Web based SysML tool | Geza | Plan to show a industrial relevant tool by end of June.
Updates on training
Training HW,SW, database | Emmanuel | Request for the training contributions to the database.
Training tool, | Sebastian/Marcello/Saadia | Sebastian working on the GUI in blocky.
Market oriented action group | Kjell
Next meeting

## 211221
Table 1
Meeting cancels due to Jerker became ill shortly before the meeting.

## 211207 - Table 1-1
Table 1
Arrowhead eweb | Jerker | Informed about the updates to the arrowhead.eu/eclipse-arrowhead web
Roadmap WG v5.0 | Jerker
Documentation wiki updates | Szvetlin | Meeting Dec 13 to decide on the details
Basic documentation | Emanuel | Draft sent out for comment. Will be brought up for decision in next Roadmap WG.
Updates release candidates
SysML models/library/profile | Jerker/Geza | No updates
Security mitigation tool | Silia | Small changes to be made to have them 4.4.0 complant. Will be ready for 4.5.0 release
Security standard compliancy | Ani | Small changes to be made to have them 4.4.0 complant
Hawkbit, | Johannes/Sven | Telco tomorrow. Merge with 4.4.0 version. Will be ready for 4.5.0 release
C# and .net libraries | Jerker | Will need update to 4.4.0
Updates to prototypes
C++ v4.2 | Szvetlin/Pal | No update
Go version of mandatory core system | Jens | In progress. Will be release as open source will take some time. The code is very fast and low on resources compared to the Java version.
Code generation from SysML | Geza/Saadia | Working from SysML 2 to generate an OPC-UA server.
Consumer code generation | Cristina | No update. Need to update to v4.4.0
WorkFlowManager | Jaime | No updates. New client lib release.
Contract Proxy | Ulf/Emanuel | No updates
Autonomic adaptation | Hua | Updated to 4.4.0. Will render som work towards a autonomic configuration system
Device hub and Ditto | Johannes | See HawBit
ESB-CPN, NodeRed | Felix | No updates
Translation - sermantics | Jacob/Pedro/Rogerio | New paper published
SysML 2 | Oystein/Geza | No updates
Kura & Kapua | Paolo | No updates
User authentication | Tomas/Jan | No updates
OPC-UA adaptor | Aparajita | Put for CD/CI process. Candidate for the 4.5.0
Z-wave adaptor | Salman | No update. In the process of uploading the code for CD/CI. Could be a candidate for the 4.5.0 release.
Modbus. adaptor | Salman | No update
Thing of web adaptors | Federico | Jerker to kick on Federico
103030 adaptor | Kjell | Adaptor to ÌSO 103030. A skeleton published. CD/CI review is done. Fixes has been made. Jotne has to sign the Eclipse contributor questioner.
FMI adaptor | Jan vD | Work to start Jan 2022
Test-tool | Hans | Upgrading to v4.4.0 in progress.
Sandboxing tool | Hans | On hold
X.509 profile | Emanuel | Waiting for feedback. Next is to bring it for decision in the roadmap WG
Command line tool adaptor | Jan Feidor | No updates
Power of attorny | Sree | Sreee got her Licentiate degree on Nov 25.
NGAC | Alex | Design of policy execution point is in progress.
Digital twin | Abdulla/Olof | Presents his licentiate thesis Dec 14.
Updates on engineering tools
Engineering process | Jan/Gianvito | No update
Engineering tool chain | Marek/Federico | No update
Engineering tools | Hans/Pal | Waiting for input D5.6
Model based engineering | Cristina | Plug-in for generating application systems. Need to update too v4.4.0. A guide for updating from 4.3.0 to 4.4.0 is needed. Will be provided by Szvetlin.
Web based SysML tool | Geza | No update
Updates on training
Training HW,SW, database | Emmanuel | No update
Training tool, | Sebastian/Marcello/Saadia | Sebastian is working go the Arrowhead interfaces.
Market oriented action group |  | 15+ companies responded to the questioner.
Next meeting

## 211123
Table 1
Release v4.4.0 | Szvetlin | Released. Can be downloaded from GIT
Roadmap WG v5.0 | Jerker
Documentation SoSDD update | Emanuel | Create a new guideline for documenting .
Updates release candidates
SysML models/library/profile | Jerker/Geza | Workshop done - Made a lot o progress . Work ongoing
Security mitigation tool | Silia | No Update
Security standard compliancy | Ani | No Update
Hawkbit, | Johannes/Sven | On Plan- A few changes needed according to pull request - Good progress
C# and .net libraries | Jerker | No Update
Updates to prototypes
C++ v4.2 | Szvetlin/Pal | Work ongoing
Code generation from SysML | Geza/Saadia | No Update
Consumer code generation | Cristina | No Update.
WorkFlowManager | Jaime | No Update
Contract Proxy | Ulf/Emanuel | Still Work with partner to develop.
Autonomic orchestration/configuration | Hua | No Updates
Device hub and Ditto | Johannes | No Update
ESB-CPN, NodeRed | Felix | No Major update. Work ongoing
Translation - sermantics | Jacob/Pedro/Rogerio | No Update. Working on integrate changes on Online tool
SysML 2 | Oystein/Geza | No Update
Kura & Kapua | Paolo | No Updates
User authentication | Tomas/Jan | No Updates
OPC-UA adaptor | Aparajita | Can soon be in the GIT Eclipse Arrowhead repository
Z-wave adaptor | Salman | Working on optimisation on Doc report
Test-tool | Hans | No Update since Lubeck
Sandboxing tool | Hans
X.509 profile | Emanuel | Profile for security cert. Sent for review.
Command line tool adaptor | Jan Feidor | No Updates
Power of attorny | Sree | No Update
NGAC | Alex | No Update. Student work on this.
Digital twin | Abdulla/Olof | No Update
Updates on engineering tools
Engineering process | Jan/Gianvito | No Update
Engineering tool chain | Marek/Federico | No Update
Engineering tools | Hans/Pal | D5.5 with list of 150 Tools can eb found in OwnCloud.
Model based engineering | Cristina | No Update
Web based SysML tool | Geza | No Update
Updates on training
Training HW,SW, database | Emmanuel | No Update
Training tool, | Sebastian/Marcello/Saadia | Still Working with Paparys. Working with GUI. A lot of work on Design. Publish a paper early next year
Next meeting

## 211026
Table 1
Arrowhead Tools WS Lubeck Oct 12-14 | Jerker | 84 participants. Very productive meeting. UzL is still working on the invoices.
Making command line tools Arrowhead compliant | Jan Feidor | Very nice presentation.
Roadmap WG v5.0 | Jerker
Release v4.4.0 |  | Still not ready from Eclipse
Documentation SoSDD update | Emanuel | Brief report from Emanuel
Updates release candidates
SysML models/library/profile | Jerker/Geza | Paprys plugin profile and code generation is now in github.
Security mitigation tool | Silia | No update
Security standard compliancy | Ani | No update
Hawkbit, | Johannes/Sven | F2F meeting with AITIA to clear Hawkbit.
C# and .net libraries | Jerker | No updates
Updates to prototypes
C++ v4.2 | Szvetlin/Pal | No updates
Code generation from SysML | Geza/Saadia | Now in Github.
Consumer code generation | Cristina | No updates
WorkFlowManager | Jaime | No updates
Contract Proxy | Ulf/Emanuel | Need further development to be used by commercial actors. Need addition of financial actors. Funding proposal for the continuation is on its way.
Autonomic orchestration/configuration | Hua | Will update the orchestration capabilities is needed to be completed. Need to address policies for re-orchestration.
Device hub and Ditto | Johannes | Waiting for HawkBit to get ready.
ESB-CPN, NodeRed | Felix | No updates
Translation - sermantics | Jacob/Pedro/Rogerio | Using ontologies to design graf structures to be used for the translating. MQTT translation is done, CoAP will be ready in a few weeks.
SysML 2 | Oystein/Geza | No updates
Kura & Kapua | Paolo | No updates
User authentication | Tomas/Jan | Potential connection to See and Olov S.
OPC-UA adaptor | Aparajita | WIll be uploaded to to Eclipse-Arrowhead second part pf Nov.
Z-wave adaptor | Salman | Working on documentation and final polishing. Time second part of Nov.
Test-tool | Hans | No update
Sandboxing tool | Hans | No update
X.509 profile | Emanuel | Waiting for review feedback from Szvetlin, Jens, …. Jens spent time on MQTT certificates.
Command line tool adaptor | Jan Feidor | See todays feature presentation.
Power of attorny | Sree | Digital version of PoA. This could be used in the onboarding procedure.
NGAC | Alex | Demo presented in Lubeck. Discussion on how to add NGAC to the Authorisation system.
Digital twin | Abdulla/Olof | Virtualising a device at the edge. Enabling improved security.
Updates on engineering tools
Engineering process | Jan/Gianvito | Video to be produced by LTU and Polito.
Engineering tool chain | Marek/Federico | No update
Engineering tools | Hans/Pal
Model based engineering | Cristina | The latest update presented in Lubeck. A version will be ready for release candiatea by end of Nov.
Web based SysML tool | Geza | No update
Updates on training
Training HW,SW, database | Emmanuel | No update
Training tool, | Sebastian/Marcello/Saadia | No update - demo made in Lubeck.
Next meeting |  | Nov 9 at 15.30. will be lead by Mats

## 211109
Table 1
Roadmap WG v5.0 | Jerker | No comments
Release v4.4.0 | Szvetlin | Approved by Eclipse. Core systems released, and client library. In master branch in GitHub.
Documentation SoSDD update | Emanuel | Overview and reference model presented. Work ongoing. How strict, purpose, mandatory? Who is the documentation targeting? Perhaps future model/database storage will simplify.
Updates release candidates
SysML models/library/profile | Jerker/Fadwa/Saadia | No comments
Security mitigation tool | Silia/Mario | Issues fixed.
Security standard compliancy | Ani | Issues fixed.
Hawkbit, | Johannes/Sven/Lukas | Planning Budapest workshop to finalise Hawkbit integration
C# and .net libraries | Jerker | No comments
Updates to prototypes
C++ v4.4 | Szvetlin/Pal | New momentum now. 2 guys working now. Orchestator now. Ready in a few months.
Go v4.4.0 | Jens/Jan | No comments
Code generation from SysML | Saadia/Fadwa | No comments
Consumer code generation | Cristina | No comments
WorkFlowManager | Jaime | No comments
Contract Proxy | Ulf/Emanuel | No updates since last time
Autonomic orchestration/configuration | Hua | No updates since last time
Device hub and Ditto | Johannes | No comments
ESB-CPN, NodeRed | Felix | NodeRed: visualisation functionality included. Plan to implement in embedded system
Translation - semantics | Jacob/Pedro/Rogerio | No comments
SysML 2 | Oystein/Geza | No comments
Kura & Kapua | Paolo | No comments
User authentication | Tomas/Jan | No comments
OPC-UA adaptor | Aparajita | Svetlin: A like to publish. Ongoing Aparajita to push the code.
Z-wave adaptor | Salman | No comments
Test-tool | Hans | No comments
Sandboxing tool | Hans | No comments
X.509 profile | Emanuel | No updates since last time. Any comments appriciated.
Command line tool adaptor | Jan Feidor | Svetlin: Meeting last week on how to implement Arrowhead compliant.
Power of attorny | Sree | Planning to integrat with Arrowhead and use this technique for inboarding.
NGAC | Alex | No updates since last time. Planning to implement NGAC into Auth system.
Digital twin | Abdulla/Olof | Work ongoing , will come back.
Updates on engineering tools
Engineering process | Jan/Gianvito | No comments
Engineering tool chain | Marek/Federico | No comments
Engineering tools | Hans/Pal | No comments
Model based engineering | Cristina | No comments
Web based SysML tool | Geza | No comments
Updates on training
Training HW,SW, database | Emmanuel | Deliverable D6.3 availible.
Training tool, | Sebastian/Marcello/Saadia | No comments
Lübeck WS | Javad | Invoices sent. Any questions can be addressed to Javad.
Next meeting |  | 2021-11-23 15.30 - 17.00. Feature presentation: No propsal.

## 210928
Table 1
NEWS | Kjell | Two hour session Sept 27 and 29, 300 people attended, Sept 29.https://events.webcast.no/jotne/kHIxlbiRjOtAPAQkYHlx/3wjNHNDNhuZhHo6OxuPl
Arrowhead Tools WS Lubeck Oct 12-14 | Jerker/Javad | 70 people registered. About 40 demos announced so far.
Making command line tools Arrowhead compliant | Jan Feidor | Presentation is in todays folder of the repository.
Roadmap WG v5.0 | Jerker | v4.4.0 release is still pending review from Eclipse.
Updates release candidates
SysML models/library/profile | Jerker/Geza | Work on profile
Security mitigation tool | Silia | No updates
Security standard compliancy | Ani | No updates
Hawkbit, | Johannes/Sven | Still working on passing the CI/CD process.
C# and .net libraries | Jerker | No updates
Updates to prototypes
C++ v4.2 | Szvetlin/Pal | No updates
Code generation from SysML | Geza/Saadia | Telco Oct 1
Consumer code generation | Cristina | No updates
WorkFlowManager | Jaime | No updates, minor addition still to be planed
Contract Proxy | Ulf/Emanuel | Contractual negotiation worked on in DigiPrime. Meeting necessary to catch up with Emanuel to make it a useful thing according to Emanuel.Ulf to take the lead on this.
Autonomic orchestration/configuration | Hua | Paper accepted to IECON 2021. Implemented semantics rules capabilities. Added the Datamanager to the solution. Demo in Lubeck
Hono and Ditto | Johannes | No updates
ESB-CPN, NodeRed | Felix | No major update. Poster and video demo for Lubeck is prepared.
Translation - sermantics | Jacob/Pedro/Rogerio | Jacob - Data on translation experiments starts to come and are positive. Demo will be made in Lubeck. Rogerio - Translation manager created. Integrated to Arrowhead. Demo in Lubeck.
SysML 2 | Oystein/Geza | No update
Kura & Kapua | Paolo | Demo in Lubeck
User authentication | Feidor | No update
OPC-UA adaptor | Aparajita | Implementation is done. Publication is in the works. In the process of pushing it for inclusion in the next release. Lubeck demo
Z-wave adaptor | Salman | Complete system implemented. Lubeck demo
Test-tool | Hans | Demo in Lubeck, discussion on making this open source
Sandboxing tool | Hans | No update
Updates on engineering tools
Engineering process | Jan/Gianvito | No updates
Engineering tool chain | Marek/Federico | No updates
Engineering tools | Hans/Pal | Collecting data on tools for the next delivery.
Model based engineering | Cristina | See todays feature presentation
Updates on training
Training HW,SW, database | Emmanuel | Synchronisation issues is currently address.
Training tool, | Sebastian/Marcello/Saadia | No updates
Next meeting |  | Next telco Oct 26 at 15.30

## 210914
Table 1
Arrowhead Tools WS Lubeck Oct 12-14 | Jerker/Javad
Eclipse booth at Open source experience, Paris, Nov 9-10
Configuration system | Jens | Sven and Jens to discuss, report on progress in Lubeck
TimeManger | Jens
Roadmap WG v5.0 | Jerker
Updates release candidates
SysML models/library/profile | Jerker/Geza | Pull request to get the Papyrus profile into GitHub.
PlantDescription | Olov/Johan
Security mitigation tool | Silia | Ready but not part of the 4.4.0 release
Security standard compliancy | Ani | No updates
Hawkbit, | Johannes/Sven | Kukas is integrating feedback. Internal testing is in progress.
C++ v4.2 | Szvetlin/Pal | No updates
C# and .net libraries | Jerker | Ready for pull request.
Updates to prototypes
Code generation from SysML | Geza/Saadia | OpenAPI generator from CEA is ready. Joint demo with CEA, Crisitna and Geza in Lubeck, code generator to OPC-UA.
Consumer code generation | Cristina | No update
Model based engineering | Cristina | No update
WorkFlowManager | Jaime | No update
ExchangeNetwork | Ulf/Emanuel | No update
Autonomic orchestration/configuration | Hua | No update
Hono and Ditto | Johannes | No update
ESB-CPN, NodeRed | Felix | Video on NodeRed demo. WorkflowManager built in NodeRed is in a first version for testing. LInk https://www.youtube.com/watch?v=fImEkGwR2oA
Translation - sermantics | Jacob/Pedro/Rogerio | Recently resubmission on ML methods. Experiments does not have results yet.
SysML 2 | Oystein/Geza | No updates
Kura & Kapua | Paolo | Will be demoed in Lubeck
User authentication |  | No update
Test-tool | Hans | No update
Sandboxing tool | Hans | No update
Updates on engineering tools
Engineering process | Jan/Gianvito | This work is closed in Arrowhead Tools for now.
Engineering tool chain | Marek/Federico | A larger report is in preparation for end of Oct.
Engineering tools | Hans/Pal | A larger report is in preparation for end of Oct.
SoS generation from SysML | Cristina | No updates
Updates on training
Training HW,SW, database | Emmanuel | A larger report is in preparation for end of Oct.
Training tool, | Sebastian/Marcello/Saadia | Working full communication for integrating Papyrus and Blockly. Demo at Lubeck WS
News
Jotne | Kjell
Next meeting

## 210831
Table 1
Arrowhead Tools WS Lubeck Oct 12-14 | Jerker/Javad | Register ASAP and book your hotel to good prices NOW.
Configuration system | Jens | Canceld
TimeManger | Jens | Canceld
Roadmap WG v5.0 | Jerker | Release as possible, documentation will be updated. Release note to be compiled by Szvetlin. Then we push the v4.4.0 for final clearance from Eclipse.
Updates release candidates
SysML models/library/profile | Jerker/Geza | Core system library update in progress with TimeManager and Configuration system will be pushed to GitHub in a few days. A WS is planed Nov 3-5 at CEA hosted by Saadia.
PlantDescription | Olov/Johan | v4.40 release
Security mitigation tool | Silia | in CI/CD process
Security standard compliancy | Ani | v.4.4.0 release
Hawkbit, | Johannes/Sven | CI/CD process in final stages
Test-tool | Hans | Demo in Lubeck
Sandboxing tool | Hans
C++ v4.2 | Szvetlin/Pal
C# and .net libraries | Jerker | C# and .net lib are ready at same level as AITAI Java lib, code review by Emanuel revealed 7 point which are now being addressed with extension to the lib. Timneline about 4 weeks.
Updates to prototypes
Code generation from SysML | Geza/Saadia | No update
Consumer code generation | Cristina | Refactoring of code. Manuel test iso code is still testing. Will require compatibility analysis and interaction model.
Model based engineering | Cristina | Progress. Release plug cane ready for release v5.0.0
WorkFlowManager | Jaime
ExchangeNetwork | Ulf/Emanuel | No update.
Autonomic orchestration/configuration | Hua | Implementing code. Deomonstrating at Lubeck WS.
Hono an dDitto | Johannes | New colleague. Hono is in good progress. Pull request inprogress possibly before the Lubeck meeting
ESB-CPN, NodeRed | Felix | No updates
Translation - sermantics | Jacob/Pedro/Rogerio | No update
SysML 2 | Oystein/Geza | SysML is progressing, tooling is in progress Some technology details is still in debate.
Kura & Kapua | Paolo | No update
User authentication |  | No update
Updates on engineering tools
Engineering process | Jan/Gianvito | No update
Engineering tool chain | Marek/Federico | No update
Engineering tools | Hans/Pal | Planing for demos at Lubeck WS
SoS generation from SysML | Cristina
Updates on training
Training HW,SW, database | Emmanuel | Updates based on partner input is made. Progress according to exceptions from reviewers.
Training tool, | Sebastian/Marcello/Saadia
News
Jotne | Kjell | ISO conference WS by Jotne including multiple presentations on Arrowhead
Next meeting |  | Sept 14 at 15.30

## 210817
Table 1
Arrowhead Tools WS Lubeck Oct 12-14 |  | Request for people to sign up for the Lubeck WS. Please provide requests for Tranings session.
Review report Arrowhead Tools | Jerker | Brief report on the review outcome. Very clean review report and all deliverables + PPR2 accepted.
Configuration system | Jens | -
Hawkbit | Sven/Johannes | Demo video shown by Johannes. Video in todays directory.
Roadmap WG v5.0 | Jerker
Updates to prototypes
Code generation from SysML | Geza/Saadia | No update
Consumer code generation | Cristina | No update
PlantDescription | Olov/Johan | Ready for 4.4.0 release. Next step to be defined in discussion.
ExchangeNetwork | Ulf/Emanuel | No update. Work on X.509 profiles, https://github.com/arrowhead-f/x509-profiles. A demo provided with the Hungary national bank based on smart contract based on Arrowhead SoS. Connection to Digital currency in another blockchain. Pal to create a news article and press release.
Autonomic orchestration/configuration | Hua | Paper for IECON submitted. Journal paper in process.
Security mitigation tool | Silia | Code is review by AITIA. Journal peer submitted.
Security standard compliancy | Ani | Code is review by AITIA.
Hono, Hawkbit, Ditto, …. | Johannes/Sven | No update
ESB-CPN, NodeRed | Felix | No update
Translation - sermantics | Jacob/Pedro/Rogerio | Working on experiments. Considering a translator analysing a vector format of JSON messages. First data is expected in a few weeks.
SysML 2 | Oystein/Geza | No update
C# and .net libraries | Jerker | Code in github.com/arrowhead.f repo.
Kura & Kapua | Paolo | No updates
Updates on engineering tools
Engineering process | Jan/Gianvito | No updates
Engineering tool chain | Marek/Federico | No updates
Engineering tools | Hans/Pal | 130 tools has been worked with.
SoS generation from SysML | Cristina | No updates
Updates on training
Training HW,SW, database | Emmanuel | No updates
Training tool, | Sebastian/Marcello/Saadia | No updates
Jotne | Kjell | Jotne have a very strong g presentation at ISO - IoT - PLM WS Sept 27 & 29.
Next meeting |  | August 31 at 15.30
TimeManger
Translation | Pablo
WiFi sensor | Thingwave
Backen solution | Thingwave

## 210706
Table 1
Studio4Education | Sebastian | Demo of both the web and standalon S4E version.
WG v5.0 | Jerker
Updates release candidates
SysML models/library/profile | Jerker/Geza
WorkFlowManager | Jaime | No update, work on paper between MGEP, BME, LTU
Test-tool | Hans | Works with also Consul SR and MQTT and OPC-UA.
Sandboxing tool | Hans
C++ v4.2 | Szvetlin/Pal | No updates
Updates to prototypes
Code generation from SysML | Geza/Saadia | A web based interface for the code generation is made for MagicDraw
Consumer code generation | Cristina | Refactoring the code
PlantDescription | Olov/Johan | Small testing ready for v4.4.0 release
ExchangeNetwork | Ulf/Emanuel | No updates
Autonomic orchestration/configuration | Hua | investigating the use of the DataManager
Security mitigation tool | Silia | Expect to send code for review in July. Paper.
Security standard compliancy | Ani
Hono, Hawkbit, Ditto, …. | Johannes/Sven | Most likely ready for 4.4.0 release
ESB-CPN, NodeRed | Felix | First version of NodeRed capable of reading BPMN recipes. Need a use case for further tests.
Translation - sermantics | Jacob/Pedro/Rogerio | Work to use JSON in addition to XML.
SysML 2 | Oystein/Geza | Industry in waiting mode for a more defined and stable SysML-2.
C# and .net libraries | Jerker | Started last week. Will be ready by mid August for the 4.4.0 release.
SafetyManager | Mirren/Daniela | On hold
Kura & Kapua | Paolo | No update on Arrowhead Interoperability. New Kura version on eclipse.
Updates on engineering tools
Engineering process | Jan/Gianvito | Papaer t0 be redirected to another journal.
Engineering tool chain | Marek/Federico | No update
Engineering tools | Hans/Pal | Collecting partners to make demos at Lubeck WS. 5 demos already signed up for live demos.
SoS generation from SysML | Cristina | Plugins being updates and refined.
Updates on training
Training HW,SW, database | Emmanuel
Training tool, | Sebastian/Marcello/Saadia | See the feature demo.
Jotne | Kjell
Next meeting
TimeManger
Translation | Pablo
WiFi sensor | Thingwave
Backen solution | Thingwave

## 210622
Table 1
Review Arrowhead Tools | Jerker | Very good feedback from ECSEL-JU and reviewers
NodeRed, BEIA | George | George Lordache presented the BEIA work on NODE-RED integration to Arrowhead. Comments on usage of upcoming MQTT support by the corer systems.
Tools integration | Ciprian | Presentation on ROBOFUSE.COM tool by Ropardo. Discussion on documentation and creation of SysML models. In addition Kjell showed a way of documenting services, devices etc., being Arrowhead compliant
OPC-UA adaptor | Aparajita | Presentation of the OPC-UA adaptor.
WG v5.0 | Jerker | Focus on documentation
Architecture details
Lowering the entry step
Robustness plan
Issue list will become roadmap
Updates release candidates
SysML models/library/profile | Jerker/Geza | Updates to profile to fix buggs and harmonise Papyrus and MagicDraw versions.
WorkFlowManager | Jaime | Working on a paper
Test-tool | Hans | Now Test Tool can use Consul service register. That means that Test Tool can be run att following service register Arrowhead, DNS-SD and Consul Work on new Cominucation Profile MQTT and OPC-UA ongoing
Sandboxing tool | Hans
C++ v4.2 | Szvetlin/Pal | No update
Updates to prototypes
Code generation from SysML | Geza/Saadia | Looking into v87 of the profile.
Consumer code generation | Cristina | Plugin for IDE and Papyrus, updating code generation.
PlantDescription | Olov/Johan | Ready for v4.4.0 release
ExchangeNetwork | Ulf/Emanuel | No update on code, works on papers and thesis
Autonomic orchestration/configuration | Hoa | Will include the DataManager. Hoa will take over this development.
Security mitigation tool | Silia | No update
Security standard compliancy | Ani | No update
Hono, Hawkbit, Ditto, …. | Johannes/Sven | HawBit contribute to the. CI/CD process. Working to resolve the review comments. Plan to be part of the v4.4.0 release. Next component will Eclipse Hono.
ESB-CPN, NodeRed | Felix | Node-Red version that read BPMN recipes
Translation - sermantics | Jacob/Pedro/Rogerio | Fundamental paper re-submitted to IEEE Communication and tutorials.
SysML 2 | Oystein/Geza | No updates
C# and .net libraries | Jerker | Start next week. Target is v.4.5.0 release.
SafetyManager | Mirren/Daniela | On hold
Kura & Kapua | Paolo | No news
Updates on engineering tools
Engineering process | Jan/Gianvito | No updates
Engineering tool chain | Marek/Federico | No updates
Engineering tools | Hans/Pal | No updates
Updates on training
Training HW,SW, database | Emmanuel | Request for input to the training matrix, email to emmanuel.Vaumorin@arteris.com
Training tool, | Sebastian/Marcello/Saadia | Working code for Studio4Education. Problems with NODE-JS. Close to have a working demo.
Jotne | Kjell | Congress NWS World Congress, presentation: Standard based Digital Twin - making …. . 10-15 sensors connected to a CNC machine. Integration made in 4 hours. KYKLOS4.0 project.
Next meeting |  | July 6 at 15.30. Feature presentation by Sebastian Canet on Studio4Education.
TimeManger
Translation | Pablo
WiFi sensor | Thingwave
Backen solution | Thingwave

## 210608
Table 1
EclispeCon | Jerker
NodeRed | Felix | Adaptors for NodeRed to Arrowhead. Presentation on GitHub.com/eclispe-arrowhead/roadmap. Video and documentation links in documentation.
Norwegian use case integration | Hua | Presentation on GitHub.com/eclispe-arrowhead/roadmap
Spinn-off from BnearIT | Karl | Presentation on GitHub.com/eclispe-arrowhead/roadmap
WG v5.0 | Jerker
Architecture details
Lowering the entry step
Robustness plan
Issue list will become roadmap
Updates release candidates
SysML models/library/profile | Jerker/Geza | SysML 1.6 release is soon
WorkFlowManager | Jaime | No update
Test-tool | Hans | Status on Test Tool Working with new communication profile: MQTT (Almost done)OPC-UA (will do POC soon. Had some help from Jan van Deventer)Also implement possibility for new SR based on Consul (Almost done)
Sandboxing tool | Hans
C++ v4.2 | Szvetlin/Pal | No update
Updates to prototypes
Code generation from SysML | Geza/Saadia | No update
Consumer code generation | Cristina | Dmoe in preparation for the review. Talk to Eclispe Con submitted
PlantDescription | Olov/Johan | Testing. Fix to the Kalix lib is needed. The PDE will then v4.4.0.
ExchangeNetwork | Ulf/Emanuel | Two papers accepted. IEEE ICPS, IEEE Access journal paper to be resubmitted. Dissertation Sept 15.
Autonomic orchestration/configuration | An | See presentation of Norwegian use case
Security mitigation tool | Silia | Dmonstrator for smart agricultural test case.
Security standard compliancy | Ani | Code for review with Szvetlin team.
Hono, Hawkbit, Ditto, …. | Johannes/Sven | HawkBit integration to Arrowhead submitted.
ESB-CPN, NodeRed | Felix | See presentation at item 2 of the agenda
Translation - sermantics | Jacob/Pedro/Rogerio | Paper submitted to IEEE IoT journal. Some sort of cognitive architecture is the major direction for a solution.
SysML 2 | Oystein/Geza | Still one year into the future.
C# and .net libraries | Jerker | Start June 2021
SafetyManager | Mirren/Daniela | On hold
Kura & Kapua | Paolo | No update
Updates on engineering tools
Engineering process | Jan/Gianvito | D.2.2 report submitted. No update on the submitted paper.
Engineering tool chain | Marek/Federico | No update
Engineering tools | Hans/Pal | No update
Updates on training
Training HW,SW, database | Emmanuel | Update of the training matrix.
Training tool, | Sebastian/Marcello/Saadia | Studio4Education. Release candidate seams to be there. Connection to NodeRed tools. Intergretion to the management tool is still pending.
Next meeting |  | Next telco June 22 Feature contributions: OPC-UA, Aparajita NodeRed by Beia Tool interoperability Ropardo
TimeManger |  | Inprogress, time request and time errors.
Translation | Pablo | Adding MQTT and web socket. Producers and consumers for all protocols including test for translation tests. Security still to be solved.
WiFi sensor | Thingwave | Arrowhead based. Configuration system used to configure sensors.
Backen solution | Thingwave | High performance back end solution. 2 message/ms in early tests.

## 210525
Table 1
Authorisation of users | Feidor | Integrating Analysis Tools into Eclipse IDE using Eclipse Arrowhead. See presentation.
Norwegian use case integration | Hua | Postphoned to next bi-weekly
PlantDescription | Olov/Niclas | PlntDescriptioEngine high level presentation, slides in repo. Live demo of the PDE functionality.
WG v5.0 | Jerker
Architecture details
Lowering the entry step
Robustness plan
Issue list will become roadmap
Updates release candidates
SysML models/library/profile | Jerker/Geza | Updates to the profile to be coherent with UML specifications. Papyrus version is release in GitHub. Will be integrated into Eclipse-Arrowhead
WorkFlowManager | Jaime | No updates
Test-tool | Hans | No updates
Sandboxing tool | Hans
C++ v4.2 | Szvetlin/Pal | Minor updates, ServiceRegistry is improved but not ready for prime time.
Updates to prototypes
Code generation from SysML | Geza/Saadia | No updates.
Consumer code generation | Cristina | On hold - SysML model to create local clouds.
PlantDescription | Olov/Johan
ExchangeNetwork | Ulf/Emanuel | No updates
Autonomic orchestration/configuration | An | No updates
Security mitigation tool | Silia | No updates
Security standard compliancy | Ani | No updates
Hono, Hawkbit, Ditto, …. | Johannes/Sven | No updates
ESB-CPN, NodeRed | Felix | NodeRed with certificates. Rebuild of the NodeRed contribution module. Workflow manager in relation to NodeRed using BPMN.
Translation - sermantics | Jacob/Pedro/Rogerio | ML algorithm review of ML translation of data models. Rogerio - documentation in progress, XML schema for now, working with JSON.
SysML 2 | Oystein/Geza | Work on a general design of modelling workbench. SysML v2 integration with Jupyther.
C# and .net libraries | Jerker | Results expected by July 2021.
SafetyManager | Mirren/Daniela | on-hold
Kura & Kapua | Paolo | No updates
Updates on engineering tools
Engineering process | Jan/Gianvito | No updates
Engineering tool chain | Marek/Federico | No updates
Engineering tools | Hans/Pal | No updates
Updates on training
Training HW,SW, database | Emmanuel | Quality of the training quality is progressing.
Training tool, | Sebastian/Marcello/Saadia | No updates
Next meeting |  | June 8, Feature contributions: OPC-UA, Aparajita NodeRed, Felix

## 210511
Table 1
Major achievement | Jerker | Smaller updates to documentation, etc is still pending. Pal and Jerker meeting Monday April 26 to push these improvements such that we can go more official with the v4.3.0 release.
New interoperability support and tools | Jerker
How do we move from a coding project to a solution ecosystem? | Jerker | Consul Service Registry, 9 action points task force lead by Kjell Bengtsson, Jotne A/S. Important to be Open source and clearly define adaptors and interface, by clear documentation and code. The wiki is an important tool to find sought for information particularly for application solution builders. Slack is used to some extent.
WG v5.0 | Jerker | No updates
Architecture details
Lowering the entry step
Robustness plan
Issue list will become roadmap
Updates release candidates
SysML models/library/profile | Jerker/Geza | Profiel updates to become more UML/SysML correct.
WorkFlowManager | Jaime | Paper on the Arrowhead workflow approach.
Test-tool | Hans | See slide 13 in agenda, Contact to be made to Aparajita for OPC-UA and JEns/Pable for MQTT.
Sandboxing tool | Hans
C++ v4.2 | Szvetlin/Pal | See slides in repo. Minimal memory footprint. Linux is the only OS supported by now. IP checking made so no licensing issues are foreseen. C-lang compiler used.
Updates to prototypes
Code generation from SysML | Geza/Saadia | Code generator being upgrade to work with the Arrowehad profile v86.
Consumer code generation | Cristina | No updates
PlantDescription | Olov/Johan | Initial work started.
ExchangeNetwork | Ulf/Emanuel | System testing in progress. Works with the other core systems. Serious system testing in progress. Presentation in two weeks time.
Autonomic orchestration/configuration | An | No code updates. Paper accepted. ISIE 2021 paper accepted. Journal paper under review.
Security mitigation tool | Silia | Updated architecture and code unervay
Security standard compliancy | Ani | Journal paper usage in use case, IDD in progress, SysD available
Hono, Hawkbit, Ditto, …. | Johannes/Sven | IDD inprogress, SysD avialable-
ESB-CPN, NodeRed | Felix | Journal submitted.
Translation - sermantics | Jacob/Pedro | No update
SysML 2 | Oystein/Geza | To be shown next time.
C# and .net libraries | Jerker | NodeRed adaptor made public. Work on certificates enabling secure mode.
SafetyManager | Mirren/Daniela | Rogerio, documentation,
Kura & Kapua | Paolo | No updates
No updates
Updates on engineering tools |  | on hold
Engineering process | Jan/Gianvito | No updates
Engineering tool chain | Marek/Federico
Engineering tools | Hans/Pal
No update
Updates on training |  | No update
Training HW,SW, database | Emmanuel | No updates
Training tool, | Sebastian/Marcello/Saadia
Enhance repository quality. Improving the training material to lower the entry step.
Next meeting |  | Including VM to enable the system for education.
May 25 at 15.30. Feture presentations on Plant Description and User authentication.

## 210427
Table 1
v4.3.0 released | Jerker, Szvetlin | Smaller updates to documentation, etc is still pending. Pal and Jerker meeting Monday April 26 to push these improvements such that we can go more official with the v4.3.0 release.
How do we move from a coding project to a solution ecosystem? | Jerker | Consul Service Registry, 9 action points task force lead by Kjell Bengtsson, Jotne A/S. Important to be Open source and clearly define adaptors and interface, by clear documentation and code. The wiki is an important tool to find sought for information particularly for application solution builders. Slack is used to some extent.
WG v5.0 | Jerker | No updates
Architecture details
Lowering the entry step
Robustness plan
Issue list will become roadmap
Updates release candidates
SysML models/library/profile | Jerker/Geza | Profiel updates to become more UML/SysML correct.
WorkFlowManager | Jaime | Paper on the Arrowhead workflow approach.
Test-tool | Hans | See slide 13 in agenda, Contact to be made to Aparajita for OPC-UA and JEns/Pable for MQTT.
Sandboxing tool | Hans
C++ v4.2 | Szvetlin/Pal | See slides in repo. Minimal memory footprint. Linux is the only OS supported by now. IP checking made so no licensing issues are foreseen. C-lang compiler used.
Updates to prototypes
Code generation from SysML | Geza/Saadia | Code generator being upgrade to work with the Arrowehad profile v86.
Consumer code generation | Cristina | No updates
Plug-in for Paparys/Cameo | Cristina | Initial work started.
PlantDescription | Olov/Johan | System testing in progress. Works with the other core systems. Serious system testing in progress. Presentation in two weeks time.
ExchangeNetwork | Ulf/Emanuel | No code updates. Paper accepted. ISIE 2021 paper accepted. Journal paper under review.
Autonomic orchestration/configuration | An | Updated architecture and code unervay
Security mitigation tool | Silia | Journal paper usage in use case, IDD in progress, SysD available
Security standard compliancy | Ani | IDD inprogress, SysD avialable-
Onboarding system, | Silia | Journal submitted.
Hono, Hawkbit, Ditto, …. | Johannes/Sven | No update
Node read by BEIA | Petrache | To be shown next time.
ESB-CPN, NodeRed | Felix | NodeRed adaptor made public. Work on certificates enabling secure mode.
Translation - sermantics | Jacob/Pedro | Rogerio, documentation,
SysML 2 | Oystein/Geza | No updates
C# and .net libraries | Jerker | No updates
SafetyManager | Mirren/Daniela | on hold
Kura & Kapua | Paolo | No updates
Updates on engineering tools
Engineering process | Jan/Gianvito | No update
Engineering tool chain | Marek/Federico | No update
Engineering tools | Hans/Pal | No updates
Updates on training
Training HW,SW, database | Emmanuel | Enhance repository quality. Improving the training material to lower the entry step.
Training tool, | Sebastian/Marcello/Saadia | Including VM to enable the system for education.
Next meeting |  | May 25 at 15.30. Feture presentations on Plant Description and User authentication.

## 210316
Table 1
v4.3.0 released | Jerker, Szvetlin
Datamanager with web-socket | Jens
Configuration system | Jens
WG v5.0 | Jerker
Architecture details
Lowering the entry step
Robustness plan
Issue list will become roadmap
Updates release candidates
SysML models/library/profile | Jerker/Geza | Library v16, profile v 85, webinar by Jerker on Friday at 10.00
WorkFlowManager | Jaime | No updates
Test-tool | Hans | No updates
Sandboxing tool | Hans | No updates
C++ v4.2 | Szvetlin/Pal | No updates, code avialbla in the old repo. https://github.com/arrowhead-f/core-cpp
Updates to prototypes
ESB-CPN, NodeRed | Felix | Paper in the works related to Workflow management team
Code generation from SysML | Geza/Saadia | Code generation to OPEN API is working. Orchestration from SysML. Meeting Friday on linking Cristinas code germination for Consumers.
Consumer code generation | Cristina | Documentation in progress. Meeting on code germination from SysML from papyrus
PlantDescription | Olov/Johan | Design document agreed between Aitia and Xarepo. JD TO REVIEW
ExchangeNetwork | Ulf/Emanuel | More papers be written. Extension to normal e-contract is investigated.
Autonomic orchestration/configuration | An | Documentation in progress, SysD, SD in own cloud
Security mitigation tool | Silia | Documentation in progress, SysD in own cloud
Security standard compliancy | Ani | Documentation in progress, SysD, in own cloud
Hono, Hawkbit, Ditto, …. | Johannes/Sven | Request for documentation from jerker. Sven will look into the status with Johannes
Translation - sermantics | Jacob/Pedro | No updates
SysML 2 | Oystein/Geza | Work ongoing with OMG SysML 2 team
C# and .net libraries | Jerker | Resources secured for development work in June 2021.
SafetyManager | Mirren/Daniela | No updates
Kura & Kapua | Paolo | No updates
Updates on engineering tools
Engineering process | Jan/Gianvito | Long paper ready for submission
Engineering tool chain | Marek/Federico | No updates
Engineering tools | Hans/Pal | D5.4 released. Tool list. Some tool will be Arrowhead compliant. Adaptors for some tools will be available.
Updates on training
Training HW,SW, database | Emmanuel | Organisation of training material. Preparation fo a single entry for training material.
Training tool, | Sebastian/Marcello/Saadia | Videos and demos are available. Studio4Education will be Arrowhead complaint. Great opportunity for widen the adoption in the Eclipse community.
Request for other resources | Jerker
Video | Jerker
Next meeting |  | 2021-04-01

## 210302
Table 1
Ecplise process | Marco/Jerker | QoS system removed due to IPR licence reason, ICMP, lib LPGL 3.0. Request fro people to sign up with Eclipse account and notify Jerker
Released Core Systems | Szvetlin | Updating documentation, JD to check on EventHandler system.
WG v5.0 | Jerker | Bi-weekly meeting,
Architecture details
Lowering the entry step
Robustness plan
Development issue list
Updates release candidates
WorkFlowManager | Jaime | Paper focus
OPC-UA | LTU/Pal | No updates
Test-tool | Hans | Continuing test
Sandboxing tool | Hans | Continuing test
Modbus TCP | Irenius | JD in contact with TWT
SysML models/library/profile | Jerker/Geza | JD to invite to webinar on SoS use case modeling using SysML
C++ v4.2 | Szvetlin/Pal | No updates
Updates to prototypes
ESB-CPN, NodeRed | Felix | No updates
PlantDescription | Olov/Johan | Regular meeting on PD specs. Defined initial data based table. JSON structures for endpoints. PDE proposal Friday this week.
Configuration | Javad | JD to kick on Jens to contact Javad.
Engineering tool for legacy adapters | Mario | JD to contact Mario of IFAK
Datastructure Editor | Mario
Device description editor | Mario
Code generator | Mario
Consumer code generation | Cristina | Code updates, tests based on examples. Paper for INDIN and TII journal
ContractProxy | Ulf/Emanuel | No updates. Emanuell is finishing his PhD. thesis
SafetyManager | Mirren/Daniela
Autonomic orchestration/configuration | An | No updates on code. Paper writing
Security mitigation tool | Silia | Paper accepted and IEEE IM WS, code updates
Security standard compliancy | Ani | Journal paper accepted IEEE Systems, some more automated test still to be made before CI/CD process.
Translation - sermantics | Jacob/Pedro | Paper manuscript in closing a phase. A larger experiment for data model translation to be designed. A video for April WS.
SysML 2 | Oystein/Geza | A SysML v2 Arrowhead profile and library. More efficient code reuse. Code generation from SysML models.
Code generation from SysML | Geza/Saadia | Working on exposing the configuration files generated by Papyrus as an Arrwohead service. Working also in modeling the crane case study using Arrowhead Profile
Hono, Hawkbit, Ditto, …. | Johannes/Sven | Thanks to Szvetlin for updating of Eclipse Arrowhead repo. Internal release of Hono.
Kura & Kapua | Paolo
Updates on engineering tools
Engineering process | Jan/Gianvito | No updates
Engineering tool chain | Marek/Federico | No updates
Engineering tools | Hans/Pal | Working on exposing the configuration files generated by Papyrus as an Arrwohead service. Working also in modeling the crane case study using Arrowhead Profile
Updates on training
Training HW,SW, database | Emmanuel | Contributions to the technology artefact list. WP6 to define trainings material groups for different topics and receivers.
Training tool, | Sebastian/Marcello/Saadia | No updates
Request for other resources | Jerker | .net lib to be developed via LTU over summer.
Video | Jerker | Video pitch 1 min was show cased by Jerker. Comments highly welcome this week.
Next meeting |  | 2021-03-16

## 210216
Table 1
Ecplise process | Marco/Jerker | Commiter session by Marco. Decission on IPR by the board by Feb 17.
Released Core Systems | Szvetlin | Working on documentation
WG v5.0 | Jerker | Next meeting Wednesday Feb 17 at 15.00 Contact Jerker if you like to participate.
Updates release candidates
Translator | Pablo/Jerker/Szvetlin
FiWare interoperability | Pablo/Jerker/Jonny
WorkFlowManager | Jaime | Writing papers on workflow management in general
OPC-UA | LTU/Pal | v4.1.3 compatible version now - move to a v4.4.0 release.
Test-tool | Hans | Now update
Sandboxing tool | Hans | Now update
Modbus TCP | Irenius | Jerker to get in contact with them for a v4.4.0 relase
SysML models/library/profile | Jerker/Geza | Webinar for mid March planed by JD.
C++ v4.2 | Szvetlin/Pal | Not ready. ServiceRegistry , Authorisation system, done. Memory foot print much smaller than the Java sprint.
Updates to prototypes
ESB-CPN, NodeRed | Felix | Writing papers on workflow management in general
PlantDescription | Olov/Johan | Work on-going, plan with AITIA. Agreement on additions to the orchestration system made.
Configuration | Javad | Paper writing. Initial Code from Jens E avaialble
Engineering tool for legacy adapters | Mario | JD to take direct contra to Marioa
Datastructure Editor | Mario
Device description editor | Mario
Code generator | Mario
Consumer code generation | Cristina | No updates
ContractProxy | Ulf/Emanuel | No real development right now.
SafetyManager | Mirren/Daniela | Still on hold
Autonomic orchestration/configuration | An | No updates
Security mitigation tool | Silia | System documentation updates
Security standard compliancy | Ani | System documentation updates
Translation - sermantics | Jacob/Pedro | Tests on-going. larger presentation to come in a few weeks.
SysML 2 | Oystein/Geza | Arrowhead modelling with SysML 2 by Oystein.
Code generation from SysML | Geza/Saadia | Geza to work on a web based modelling approach. Interoperability workbench based on Jupiter. Saadia: a version of SysML code generation using OpenAPI is already functional. Now upgrades of the latest profile. Generation of configuration data for Studio for education.
Hono, Hawkbit, Ditto, …. | Johannes/Sven | Hono almost ready to be a release candidate. HawkBit on its way. Updates needed for some Apache license stuff.
Kura & Kapua | Paolo | No updates
Updates on engineering tools
Engineering process | Jan/Gianvito | Most use cases of Arrowhead Tools connected to the Eclispe Arrowhead engineering process.
Engineering tool chain | Marek/Federico | No update - Tool chain demo planed for April
Engineering tools | Hans/Pal | 104 tools used by Arrowhead Tools. Categorisation on Arrowhead compliance. Possible presentation at next bi-weekly.
Updates on training
Training HW,SW, database | Emmanuel | Promote a Hackaton training. Group experts and non-experts to solve a specific problem. Enhance training material. Invitation to partners to test training and comment on material.
Training tool, | Sebastian/Marcello/Saadia | Worked on scenaria where Papyrus and Studio4Education can integrate using Eclipse Arrowhead. Configuration file will be exposed as a service to be consumed by Studio4 Education. Demo in April.
Request for other resources | Jerker
QoS paper | Haris
Management of Industry4.0 WS | markus
Arrowhead Tools Y2 pro conf | Jerker
Next meeting

## 210202
Table 1
Ecplise process | Marco/Jerker | Decision at the board regarding usage of LGPL for QoS.
Released Core Systems | Szvetlin | Document review ongoing.
WG v5.0 | Jerker | Latest Roadmap shown
Updates release candidates
Translator | Pablo/Jerker/Szvetlin
FiWare interoperability | Pablo/Jerker/Jonny
WorkFlowManager | Jaime | No updates
PLC integration IEC 61499 | Jose/Kirill | Release with Eclipse 4diac, link to this at goithub and Eclipse site
OPC-UA | LTU | No updates
Test-tool | Hans | No updates
Sandboxing tool | Hans | No updates
Modbus TCP | Irenius | Jerker to contact Ireneus for starting Ci/CD process.
SysML models/library/profile | Jerker/Geza | SysMLL 1.5 profile and library now at GitHub, Webinar by end of Feb by Jerker
C++ v4.2 | Szvetlin | No updates
Updates to prototypes
ESB-CPN, NodeRed | Felix | Meeting in Workflow group, use case integration different possibilities, proposal for WS at April Arrowhead Tools meeting
PlantDescription | Olov/Johan | Meeting AITIA and Xarepo. Will require update on Orchestration.
Configuration | Javad | Javad and Jens to meet regarding their different developments
Engineering tool for legacy adapters | Mario | No updates, Jerker to check on the rerelease on this tool.
Datastructure Editor | Mario | No updates, Jerker to check on the rerelease on this tool.
Device description editor | Mario | No updates, Jerker to check on the rerelease on this tool.
Code generator | Mario
Consumer code generation | Cristina | Code development, papers in the work
ContractProxy | Ulf/Emanuel | No updates
SafetyManager | Mirren/Daniela | No updates
Autonomic orchestration/configuration | An | Uploaded SysD documentation in Owncloud, updates of the code accordingly
Security mitigation tool | Silia | Mario is testing the system prototyp, SD, IDD document in the works.
Security standard compliancy | Ani | System ready for release, Contact to Szvetlin too for CI/CD process. Documentation to Jerker for SysML modelling
Translation - sermantics | Jacob/Pedro | Cool manuscript in the works. Plan for a demo in April.
SysML 2 | Oystein/Geza | Use case model of 1.6 and v2 models.
Code generation from SysML | Geza/Saadia | Meeting last week, next meeting Feb 12. Making profile and library tool independent, MagicDraw and Papayrus. Planes to make a web based code generation tool from Geza.
Hono, Hawkbit, Ditto, …. | Johannes/Sven | Finalising contribution, HawkBit , Hono. How to make SysML model for these contributions, Lukas to come back to Jerker on this.
Kura & Kapua | Paolo | No update
Updates on engineering tools
Engineering process | Jan/Gianvito | Gianvito, working on D2.2, deadline April. Jan to bring this up with Gianvito and his team regarding SysML modelling off the engineering.
Engineering tool chain | Marek/Federico | Demo for April is planed.
Engineering tools | Hans/Pal | Questioner regarding tools and tool chains. Merging all data will happen this week.
Updates on training
Training HW,SW, database | Mathew/Mats | No update
Training tool, | Sebastian/Marcello/Saadia | Local Arrowhead server i installed with the CANET. Which service will be exposed to the local cloud. Application system and Tool chain can be exposed to the Arrowhead local cloud
QoS paper | Haris | Published papers, ICIT in Valencia.
Management of Industry4.0 WS | markus | 11 manuscript submitted.
Arrowhead Tools Y2 pro conf | Jerker | Request from jerker to Arrowhead Tools participants to submit proposals for technology breakout session for April 14.
Next meeting |  | Feb 15 at 15.30

## 210119
Table 1
43 participants
Ecplise process | Marco/Jerker | Updates requested from Bosch regarding licenses etc. mail from Lukas R. arrowhead.eu will be updated, Eclispe Arrowhead page to be updated by Pal. Still a problem with LGL3 licensensfor one lib. 3 solution directions will be solved within 1-12 weeks.
Released Core Systems | Szvetlin | Documentation updates
WG v5.0 | Jerker | Slight updates
Updates release candidates
Translator | Pablo/Jerker/Szvetlin | For 4.3.0. release
FiWare interoperability | Pablo/Jerker/Jonny | For 4.3.0 release
WorkFlowManager | Jaime | No update
PLC integration IEC 61499 | Jose/Kirill | Need to establish the proper link between Arrowhead and 4DIAC
OPC-UA | LTU | No update
Test-tool | Hans | Internal test and V&V case. Demo April
Sandboxing tool | Hans | Internal test and V&V case.
Modbus TCP | Irenius | v4.4.0 release plan.
SysML models/library/profile | Jerker/Geza | SysML 1.6 profile and lib intended fo 4.3.0 release.
C++ v4.2 | Szvetlin | Some updates, now code is posted not ready to release.
Updates to prototypes
ESB-CPN | Felix | No update, meeting scheduled for Thursday this week.
NodeRed | Felix | No update, meeting scheduled for Thursday this week.
PlantDescription | Olov/Johan | v4.4.0 release plan. Calls for bi-weekly meeting to continue
Configuration | Javad | Defining a robot use case for the configuration system. LTU have procured Thingwave to suppor ton the configuration system
Engineering tool for legacy adapters | Mario | No update
Datastructure Editor | Mario | No update
Device description editor | Mario | No update
Code generator | Mario | No update
Consumer code generation | Cristina | Security is now included. More tests with more coding protocols.
ContractProxy | Ulf/Emanuel | No major updates.
SafetyManager | Mirren/Daniela | No updates, on hold for the moment
Autonomic orchestration/configuration | An | Updates documentation. To be used of SysML models
Security mitigation tool | Silia | Code updates + paper with a drown
Security standard compliancy | Ani | Paper submitted
Onboarding procedure |  | Paper submitted
Translation - sermantics | Jacob/Pedro | Manuscript in process from LTU team. Prototype from Lisbon group. Some first results may be shared in a few weeks.
SysML 2 | Oystein/Geza | Paper in the works. Official v2 in fall 2021. Development around API. Language is not yet final. Some fundamental discussion remains. Focus to web and cloud based SysML tooling.
Code generation from SysML | Geza/Saadia | Students at Aalborg, Code generation made in Papyrus. CEA integration of SysML profile to Papyrus. Saadia to organise a coordination meeting
Hono, Hawkbit, Ditto, …. | Johannes/Sven | Preparing the pull request for integrating Hono, and Hawkbit. May need Kybernetics, investigations on-going. Vorto together with SysML, …
Kura & Kapua | Paolo | No update
Updates on engineering tools
Engineering process | Jan/Gianvito | Metting tomorrow
Engineering tool chain | Marek/Federico | Regular meetings - still aiming for generic demo i April.
Engineering tools | Hans/Pal | Tool catalogs related to use cases is being produced.
Updates on training
Training HW,SW, database | Mathew/Mats | Meetings every week. Bologna server has been down. Local server is being considered. Marco to see if Eclispe ca host an open Arrowhead Framework instalation
Training tool, | Sebastian/Marcello/Saadia
Management of Industry4.0 WS | markus
Arrowhead Tools Y2 pro conf | Jerker | 2015-04-13
Next meeting