## Roadmap
Table 1
Core systems |  | v4.2.0 | documentation | v4.3.0 | Revisions | v4.4.0 | Update plan | v4.5.0 |  | 5.0.0 | Update plan
| Who |  |  | Dec, 2020 |  | May, 2021 |  |  |  | Dec, 2021 |  | Cordination by
ServiceRegistry | Szvetlin/Aparajita | 4.2.0 | TBU | Fork from Appy | Documentation update. Multiple instances of same service from one system. - DONE | TBD | Naming convention updated: Underscore not allowed in device namn. Mandatory meta data. Separated data base. Fix for timestamp bug. Validation of IP addresses: Correct IP, Correct host name, Illegal IP addresses e.g. broadcast or multicast.
Authorisation | Szvetlin | 4.2.0 | TBU |  | Documentation update. Updates roadmap related to the Combitech security assessment report. DONE | TBD | Support for NGAC. CertificateKind updated to Secure, Non-Secure, Separated data base. Security update relative to Combitech security analysis: Compile a list of security best practices and deployment Traning video |  |  |  | Security update relative to Combitech security analysis: - Discussion about a Central Identity Registry (Arrowhead 5.0 WG) | Jerker
Orchestration | Szvetlin/Aparajita | 4.2.0 | TBU | Fork by Appy | Documentation update. DONE | TBD | Separated data base. Metadata based orchestration priority
CertificateAuthority | Gabor | 4.2.0 | TBU |  | Documentation update | TBD
OnBoarding | Mario | 4.2.0 | TBU |  | Documentation update | TBD
SystemRegistry | Mario | 4.2.0 | TBU |  | Documentation update. | TBD | Naming convention updated: Underscore not allowed in device namn.
DeviceRegistry | Mario | 4.2.0 | TBU |  | Documentation update. | TBD | Naming convention updated: MAC protocol deleted, Underscore not allowed in device namn.
GateKeeper | Szvetlin | 4.2.0 | TBU |  | Documentation update | TBD
Gateway | Szvetlin | 4.2.0 | TBU |  | Documentation update | TBD
Choreographer |  | 4.2.0 | TBU |  | Documentation update | TBD
EventHandler | Szvetlin | 4.2.0 | TBU |  | Documentation update | TBD
QoS | Szvetlin | 4.2.0 | TBU |  | Documentation update | TBD
Management Tool | Szvetlin | 4.2.0 | TBU |  | Documentation update | TBD
DataManager | Jens |  |  | 4.3.0-RC | Passed CI/CD. Access control to be added. | TBD
Translator | Pablo |  |  | 4.3.0-RC | IN CI/CD - | TBD
FiWare interoperability | Pablo |  |  | 4.3.0-RC | IN CI/CD | TBD
Client libs
Kalix library | Emanuel |  |  |  |  | v4.4.0-RC | to CI/CD process. Documentation update. Support for core systems: …. |  |  |  |  | Jerker
C++ Qt | Balint/Szvetlin |  |  | 4.3.0-RC | to CI/CD process. Documentation update.
Phyton | Jacob |  |  |  |  | v4.4.0-RC | to CI/CD process. Documentation update. |  |  |  |  | Jerker
Java HTTP | Szvetlin |  |  | 4.3.0-RC | to CI/CD process. Documentation update.
Java/Go Websocket | Jens/Pablo |  |  |  |  | v4.4.0-RC | to CI/CD process. Documentation update. |  |  |  |  | OK Szvetlin
Node-JS | Szvetlin |  |  |  |  | v4.4.0-RC | to CI/CD process. Documentation update. |  |  |  |  | Szvetlin
Client skeletons
Java | Szvetlin |  |  | 4.3.0-RC | to CI/CD process. Documentation update.
Additional core systems
Modbus-TCP | Irenius/Zhang |  |  |  |  | v4.4.0-RC | to CI/CD process. Documentation update. |  |  |  |  | Jerker
OPC-UA | Aparjita/…. |  |  |  |  | v4.4.0-RC | to CI/CD process. Documentation update. |  |  |  |  | Jerker
WorkflowManager | Jamie |  |  |  |  | v4.4.0-RC | to CI/CD process. Documentation update. |  |  |  |  | OK Jaime
WorkflowExecutor | Jamie |  |  |  |  | v4.4.0-RC | to CI/CD process. Documentation update. |  |  |  |  | OK Jaime
ContractProxy | Emanuel |  |  |  |  | v4.4.0-RC | to CI/CD process. Documentation update. |  |  |  |  | OK Jerker
Consumer code generation | Cristina |  |  |  |  | v4.4.0-RC | to CI/CD process. Documentation update. |  |  |  |  | Jerker
C++ mandatory core systems | Szvetlin |  |  |  |  | v4.4.0-RC | to CI/CD process. Documentation update. |  |  |  |  | Szvetlin
SecurityStandardCompliance | Ani/Mario | [6 empty] | v4.5.0-RC | to CI/CD process. Documentation update. |  |  | OK jerker
SecurityMitigationGAMS | Silia/Mario | [6 empty] | v4.5.0-RC | to CI/CD process. Documentation update. |  |  | OK Jerker
SafetyManger | Mirren
PlantDescription | Olov/Johan |  |  |  |  | v4.4.0-RC | to CI/CD process. Documentation update.
Autonomous Orchestration mitigation | An |  |  |  |  | v4.4.0-RC | to CI/CD process. Documentation update. |  |  |  |  | OK
Eclipse projects … | [5 empty] | v4.4.0-RC | to CI/CD process. Documentation update. |  |  |  |  | Jerker
Hono | Lucas |  |  |  |  | v4.4.0-RC | to CI/CD process. Documentation update. |  |  |  |  | Jerker
Hawkbit | Johannes |  |  |  |  | v4.4.0-RC | to CI/CD process. Documentation update. |  |  |  |  | Jerker
KeyCloak | Sven-Erik |  |  |  |  | v4.4.0-RC | to CI/CD process. Documentation update. |  |  |  |  | Jerker
Vorto? | [5 empty] | v4.4.0-RC | to CI/CD process. Documentation update. |  |  |  |  | Jerker
???
Modeling
SysML1.6 profile | Jerker |  |  | 4.3.0-RC | DONE | v4.4.0-RC | System modeling and deployment, LC modeling and deployment, SoLC modelling and deployment |  |  |  |  | OK Jerker
SysML 1.6 library | Jerker |  |  | 4.3.0-RC | DONE | v4.4.0-RC | All 4.3.0 core systems and 4.4.0 core systems |  |  |  |  | OK Jerker
Code generation from SysML | Saadia/Geza/Cristina |  |  |  |  | v4.4.0-RC | Autogeneration of docker containers with chosen core systems and Producer and Consumer service interface code |  |  |  |  | Jerker
Tools
Tool chain interoperability architecture and reference implementation | [5 empty] | v4.4.0-RC | WP4 |  |  |  |  | Jerker
Blockly coding | Sebastian Canet |  |  |  |  | v4.4.0-RC | Blockly coding of Arrowhead compliant application systems. |  |  |  |  | Jerker/Daniela
Tools made Arrowhead compliant | [5 empty] | v4.4.0-RC | Which tools? WP5 |  |  |  |  | Hans
Test Tool | [5 empty] | v4.40-RC | BnearIT test tools |  |  |  |  | Hans
Engineering
Arrowhead engineering model | [5 empty] | v4.4.0-RC | From WP2 |  |  |  |  | Jerker
Security best practice | Szvetlin |  |  |  |  | V4.4.0 RC | Based on Combitech report from Productive 4.0 |  |  |  |  | OK
Training videos
Other issues
Language agnostics | [9 empty] | XXXX |  | Jens